DEENDAYAL PORT TRUST

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 31.01.2020

| Sr. No. | Name of work and location | Estimated cost (Rs.) in lakh | Tendered Cost (Rs.) in lakh | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M. | 8181.98 | 6359.61 | 18.91 Below | EL/WK/2472/480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | 07/05/2017 | Shri D.K. Hazra, XEN(E) Shri Anil Rautiya, AE (E) | Comprehensive AMC work in progress. |
| 2. | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 15570.46 | 14446.38 9685.90 towards capital cost & 4760.48 towards O&M Charges. | 7.22 Below | EL/WK/2491/1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | 14/05/2018 Contract extended up to 14/04/2019 | Shri D.K. Hazra, XEN(E) | Work completed on 30/03/2019. Maintenance period of 2 years is in progress. |
| 3. | Maintenance Contract of 03 Nos. ELL Wharf Cranes of 25T capacity 4 Rope of M/s. TIL make alongwith Grab inside Cargo Jetty Area for a period of 2 years. | 360.00 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Tender discharged and re-invited on 16/01/2020 |
| 4. | Design, Manufacture, Supply, Erection, Testing, Commissioning & Operation of 02 Nos. of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 5 Years. | 9181.77 | Euro 79.31 Lakhs + Customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs. 93.15 crore (While evaluation of bid) | 0.73 Below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru s.r.l., Italy | w.e.f. date of opening of Letter of Credit (LC). | 08 months from the date of opening of Letter of Credit (LC). | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | CAMC work in progress. |
| 5. | Repairs to 30 Mtr. High Mast Towers & AMC of Area Lighting at inside Cargo Jetty Area for a period of Two Years. | 350.44 | 312.60 | 10.18% below | EL/AC/2538/138 dated 01/01/2020 | M/s. C.K. Electricals, Surat. | w.e.f. date of issue of work order | 2 years from the date of issue of work order | Shri D.K. Hazra, XEN(E) Shri Chitrang Vyas, AXEN(E) | Work Order issued on 01/01/2020. |
| 6. | Maintenance Contract of 03 Nos. 25T and 2 Nos. 16T capacity MBE make wharf cranes, alongwith Grabs for a period of two years at inside Cargo Jetty area. | 632.40 | 630.00 | 0.38% below | EL/AC/ 2549/604 dated 02/09/2019 | M/s. R.S. Electricals, Gandhidham. | 16/08/2019 | 15/08/2021 | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Work in progress. |
| 7. | Maintenance Contract of 04 Nos. of Mukund Cranes of 12T (2 Nos.) capacities ELL Cranes, alongwith Grabs for a period of two years at inside Cargo Jetty area. | 474.67 | 364.80 | 23.15% Below | No. EL/AC/ 2531/503 dated 13/08/2019 | M/s. R.S. Electricals, Gandhidham. | 20/07/2019 | 19/07/2021 | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Work in progress. |
| 8. | Electrification work at Location of 5 Nos. New Weigh Bridge at DPT. | 95.10 | 68.96 | 27.48% Below | EL/AC/2536/269 dated 23/01/2020 | M/s. C.K. Electricals, Surat | 23/01/2020 | 21/04/2020 | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Work Order issued on 23/01/2020. |
| 9. | Revamping of 2 Nos. of TIL Make 25T ELL Crane No. 10 & 11 with latest version of VVVF Drives at DPT. | 256.26 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Tender discharged and re-invited on 27/12/2019 & opened on 31/01/2020. |
| 10 | Annual Maintenance Contract of Liebherr make HMC :-LHM 550-S/N: 141143 & LHM 550-S/N:- 141169 for the period of two years at Berth No. 13 inside Cargo Jetty area. | 484.16 | 312.00 | 35.56% Below | N.A. | M/s. R.S. Electricals, Gandhidham. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | LOI issued on 31/07/2019. Work Order to be issued after putting the cranes in working condition. |
| 11 | Supply, installation, testing and commissioning of Power Trans-former at 66 KV Switchyard. | 122.96 | 127.65 | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Price bid opened on 24/12/2019. L1 Offer is for Rs. 1,27,65,401 - Note to TC for Price Bid evaluation is sent on 20/01/2020. |
| 12 | Improving and reconditioning of 66/11 KV Switchyard and 66/11 KV Sub-Station strengthening of 66/11 KV Switchyard & Substation at inside Cargo Jetty Area thereof. | 239.46 | 221.41 | 6.28% below | EL/WK/2543/412 dated 18/11/2019 | M/s. Onix Structure Pvt. Ltd., Rajkot. | 18/11/2019 | 17/07/2020 | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Work in progress. |
| 13 | Restoration of power supply & Re-conditioning of Electrical installation at Berth No. 13 & 15 inside Cargo Jetty Area. | 259.76 | 186.36 | 28.26% below | EL/AC/2539/268 dated 23/01/2020 | M/s. C.K. Electricals, Surat | 23/01/2020 | 22/09/2020 | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Work Order issued on 23/01/2020. |
| 14 | Refurbishing of Power Supply system & lighting system of entire Oil Jetty area. | 252.52 | 174.45 | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.S. Kumekar, JE (E) | LOI issued on 01/01/2020. |
| 15 | Providing lighting arrangement on the stretch of 4.5 Kilometres area from Salt to West Gate-2. | 247.81 | 134.59 | 45.68% below | N.A. | M/s. Radadiya Paresh K, Rajkot. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri Anil Rautiya, AE (E) | Proposal for acceptance of L1 Offer amounting to Rs. 1,34,59,500 - Submitted on 27/01/20. |
| 16 | Upgradation of TS-IV, 7th Berth, Marine Unloader, Old NDA Area - Strengthening of down Stream 11KV Substations at Cargo Jetty Area. | 322.14 | 210.46 | 34.67% below | N.A. | M/s. GPI Projects Pvt. Ltd., Ahmedabad. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | LOI issued on 18/01/2020. |
| 17 | Maintenance Contract for HT & LT Electrical Installations including Substations, Overhead Lines, Residential, Non-residen-tial, Hospital and School Build-ings outside Cargo Jetty Area. | 398.48 | 357.89 | 10.18% below | EL/AC/2557(h) /119 dated 24/12/2019 | M/s. Sterling & Wilson Ltd. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | LOI issued on 24/12/2019. |
| 18 | Supply Installation, Testing & Commissioning of 3 Nos. of 800 KVA, 11/0.433 KV Dry Type Resin Cast Transformer. | 60.61 | 48.51 | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri A.K. Sharma AE (E) | Price Bid opened on 19/12/2019. L-1 Offer Rs. 48,51,000/- - Confirmation of credentials from third party is awaited. |
| 19 | Operation and Maintenance of 66/11kv and 11/0.433KV Sub-station inside Cargo Jetty area at DPT, for a period of 2 years. | 312.46 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri Chitrang Vyas, AXEN(E) | Tender opened on 07/12/2019 and shortfall documents called for from the Bidders. Legal opinion regarding bid evaluation is awaited. |
| 20 | Annual Rate contract for supply and laying of HT / LT underground cables at inside and outside Cargo Jetty area. | 261.18 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri Chitrang Vyas, AXEN(E) | Pre-Bid meeting held on 30/12/2019. Date of opening of tender is extended upto 07/02/2020, as pre-bid clarification is being submitted for approval. |
| 21 | Supply, Installation, Testing & Commissioning of 11 KV overhead line from new port colony to SIPC Area | 64.01 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri D.K. Hazra, XEN(E) Shri Chitrang Vyas, AXEN(E) | Technical bid opened on 27/01/2020. |
| 22 | Supply Installation, Testing & Commissioning of 5 Nos. of 100 MT Capacity, Pit-less type, fully electronic Road Weighbridges with 5 years comprehensive maintenance contract after expiry of 2 years Guarantee period. | 91.15 | 74.85 | 17.88% below | ML/WK/ 3942/596 dated 16/12/2019. | M/s. Techno Scale Industries, Ahmedabad. | 16/12/2019 | 120 days i.e., 13/04/2020. | Shri B.J. Solanki, SE(M) Shri Himmat Makwana, AE (M) | Work Order issued on 16/12/2019. |
| 23 | Supply Installation, Testing & Commissioning of 4 Nos. Pitless type electronic In motion Railway Weighbridges (15Kmph speed)of 140 Mt capacities including comprehensive maintenance contract for a period of 5 years after expiry of 2 years Guarantee period. | 150.79 | 147.67 | (-)2.07% below | W.O. No. ML/WK/3916-II/738 dated 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., E-1, TVK Industrial Estate, Guindy, Chennai-600032. | 05/01/2019 | 120 days i.e., 04/05/2019 | Shri B.J. Solanki, SE(M) Shri Himmat Makwana, AE (M) | Work delayed due to non-clearance from Civil Engineering Department. Level of existing rail lines may change. |
| 24 | Supply Installation, Testing & Commissioning of 2 Nos. Mather & Platt Make vertical turbine fire fighting pumps at Cargo Jetty No. 10 | 237.48 | 237.48 | 0% | ML/WK/3929/Gim-120 dated 30/03/2019 | M/s. Milan Marketing, Ahmedabad-380015 | 30/03/2019 | 129 days i.e., 28/07/2019 | Shri B.J. Solanki, SE(M) Shri Aman, AE (M) | Work Completed. |
| 25 | Development, Operation and Maintenance of Container Terminal at Berth Nos. 11 & 12 at Kandla Port on PPP Mode. | 15981.00 | 15981.00 | -- | MS/WK/4003-V/357 dtd.19/2/2016 | M/s. Kandla International Container Terminal | 29/02/2016 | 15/02/2018 | Shri B.J. Solanki, SE(M) Shri Aman, AE (M) | LOI issued. Concession Agreement signed on 29/02/2016. Project fully commi-ssioned on 15/02/2018. |
| 26 | Appointment of Consultant for the work of Mechanization of handling of Fertilizers at Kandla Port | 166.67 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Dana Manohar, XEN(M) Shri Aman, AE (M) | Proposal for re-inviting the tender from IPA empanelled consultants (for project of Mechanization of fertilizer handling facility at Berth No. 14 Deendayal Port on PPP Mode) is submitted for finance concurrence. |
| 27 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Main-tenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 12094.14 | 12232.53 | 0.9% above the estimated cost | LoA issued vide No. MS/WK/4025-II/GIM-265 dtd. 31/03/2017 | M/s. Rishi Shipping, Gandhidham | 31/03/2017 | 31/03/2018 | Shri Dana Manohar, XEN(M) Shri Aman, AE (M) | LOA issued on 31/03/2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O & M contract is in effect. |
| 28 | Mechanization of Fertilizer handling facility at Berth No. 14 at Deendayal Port. | 27709.94 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME Shri Aman, AE (M) | As per the direction of the Secretary (Shipping) in the meeting dated 03/01/2020, the project will be carried out on PPP Mode |
| 29 | Appointment of Consultant for the work of Mechanization of Handling of Coal (including pollution control measures at Deendayal Port. | 438.66 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Dana Manohar, XEN(M) Shri Aman, AE (M) | After approval of competent authority, previous single tender is re-invited on 26/09/2019. Technical bids have been opened and evaluation is under process. |
| 30 | Procurement of Flameproof LED light fitting for Oil Jetty, New Kandla. | 74.80 | 29.56 | 55.74% below. | ST/PU/19048(28) dated 16/09/2019 | 1) M/s. Sudhir Switchgear Pvt. Ltd., Mumbai. 2) M/s. Shrejya Ex-Tech. Pvt. Ltd., Vadodhara | 16/09/2019 | 90 days | Shri Dana Manohar, XEN (M) Shri Rajesh Roat, AXEN (M) | Material received. |
| 31 | Procurement of Single phase & Three Phase Digital Energy Meters and Meter Box | 53.59 | N.A. | N.A. | N.A. | N.A. | N.A. | 120 days | Shri Rajesh Roat, Dy.MM | Technical bid opened on 06/01/2020. Shortfall documents received from eligible bidders are under scrutiny. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 31.01.2020

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | -- | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri R.K. Gurav, COM, OOT, Vadinar. Shri Narendra Naik, ME (Gr. I), OOT, Vadinar. | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 2 | Providing, Operating and Maintaining of 1 No. 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of three years. Estimate:Rs.70,56,000/- | 0.71 Cr. | 0.699 Cr. | 0.899% below | -- | M/s. New Divya Tours & Travels, Jamnagar. | 05/01/2019 | 3 years | Shri R.K. Verma, XEN (E&M) OOT, Vadinar. Shri Gopal Matha, JE (M) | Work Order issued vide No. OOT/ME/WK/RM/6004-I/658 dated 04/01/2019. |
| 3 | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | -- | M/s. Aeromarine Pvt. Ltd., Mumbai | -- | 3 years | Shri Narendra Naik, ME (Gr. I), OOT, Vadinar. | LOA issued vide No. OOT/ME/WK/RM/8009/1489 dated 07/12/2019. |
| 4. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | -- | -- | -- | -- | -- | 18 months | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri M.A. Jadav, AXEN(C) | i) Technical Bid opened and 4 (four) parties submitted their offers and Technical Bid is under scrutiny. ii) Tender is discharged re-invited. Pre-Bid meeting held on 20/12/2019. iii) Reply to pre-bid query and corrigendum issued on 03/02/2020, due date of opening of technical bid on 14/02/2020. |
| 5 | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1,62 | 5.01 % above | -- | M/s. Shubham Inc., Ahmedabad. | -- | 5 years | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri S.C. Vishwas AE (C) | i) Technical Bid opened and 3 (three) parties submitted their offers. ii) Letter of Acceptance issued vide No. OOT/C-NPS/GPCB/1234-I/1487 dated 06/12/2019. iii) Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. |
| 6. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | -- | -- | -- | -- | -- | 2 years | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri S.C. Vishwas AE (C) | i) Technical Bid opened and 10 (ten) parties submitted their offers. ii) Price Bid opened and submitted to competent authority for approval. |
| 7. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 | 6.01 % below | -- | M/s. Safari Travels, Balasinor | -- | 3 years | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri Gopal Matha, JE (M) | i) Technical Bid opened and 3 (three)parties submitted their offers. ii) Letter of Acceptance issued vide No. OOT/ME/WK/6008/1590 dated 01/01/2020. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 31.01.2020

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agree ment No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | AMC for cleaning & house keeping works of DPT Hospital and isolation ward at Gopalpuri and Kandla (For two years) | 0.65 Cr. | 0.46 Cr. | 29.01% Below | TW/WK/ 7735-I/192 dated 25/10/2018 | M/s. Praful A. Parmar | 10/11/2018 | 09/11/2020 | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Work in progress. |
| 2. | AMC for Residential and Non-Residential Building at Gopalpuri & AO Building, Gandhidham. | 0.97 Cr. | 0.79 Cr. | 18% below | TW/WK/ 7724-I/320 dated 01/01/2019 | M/s. Pars Enterprise, Gandhidham | 02/01/2019 | 01/01/2020 | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Work completed on 02/01/2020. |
| 3. | Construction of Dr. Babsheb Ambedker Convention Centre, Gandhidham. | 33.08 Cr. | 28.83 Cr. | 12.84% below | TW/WK/ 7715-I/410 dated 07/02/2019 | M/s. Dipesh Construction Co., Anjar | 15/02/2019 | 04/02/2021 | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Work in progress. |
| 4. | R/M of Arboriculture / Horticulture work in public building at Gopalpuri Port Colony for year 2018-19 | 0.60 Cr. | 0.40 Cr, | 33.30% below | TW/WK/ 7721-II/640 dated 12/06/2019 | M/s. Mahesh Construction | 12/06/2019 | 11/06/2020 | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Work in progress. |
| 5. | AMC for Gardens at Shaktinagar & A.O Building for the period of 2 years | 0.61 Cr. | 0.41 Cr. | 34.51% below | TW/WK/ 7734-/174 dated 02/11/2019 | M/s. Praful A. Parmar | 01/08/2019 | 31/07/2021 | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Work in progress. |
| 6. | Modernization of AO Building at Gandhidham, Stage-II. | 1.26 Cr. | 0.88 Cr. | 33.00% below | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Price Bid opened on 18/11/2019. L-1 not extended bid validity. Submitted for discharge of tender. |
| 7. | Annual maintenance contract for Sports Complex at Gopalpuri for the period of 02 years | 0.66 Cr. | -- | -- | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Price bid opened on 31/01/2020. |
| 8. | AMC for Whitewashing, Distempering & Painting to Resi. & NRB at Gopalpuri. KDLB, Gandhidham & Adipur for the year 2019-20. | 0.92 Cr. | -- | -- | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Technical Bid opened on 11/11/2019. Pre-security processed. |
| 9. | Maintenance of Public Health & Underground Drainage at Gopalpuri Port Colony & KDLB Colony for the period of two years. | 2.52 Cr. | 1.33 | 47.12% | TW/WK/ 7757-I/229 dated 05/12/2019 | M/s. Patel Construction, Gandhidham | 09/12/2019 | 08/12/2020 | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Work Order issued. Work in progress. |
| 10. | Strengthening of Canteen, Sub-station and Store at AO Building at Gandhidham. | 0.61 Cr. | -- | -- | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) Shri M.A. Lilwani AE (C) | Technical bid opened on 15/11/2019. Bid opened processed. |
| 11. | Dredging in the Navigational Channel and alongside Cargo Berth / Oil Jetties at Kandla Port Trust (year 2017-20) Location at Kandla | 514.00 | 338.01 | 34.20% below | LOA No. EG/ WK/ 5226/ 257 dated 04/07/2017 WO No. MW/ WK/ 8274-V/5195A dated 24/07/2017 | M/s. Van Oord India Pvt. Ltd., Mumbai | 03/07/2017 | 36 months | M/s. AECOM India Pvt. Ltd., Haryana. Shri A.P. Trivedi, XEN(KL) Shri Munib Ansari, AXEN (C) | Work in progress by M/s. Van Oord India Pvt. Ltd., Mumbai. |
| 12. | RFP for Service of Third Party Government Survey Agency for the Dredging at Kandla Port (2017-2020) | 3.63 Cr. | 2.33 Cr. | 35.73% Below | LOA No. EG/WK/ 5335/579 dated 24/11/2017 | M/s. Wapcos Ltd., Gurgaon-122015 Haryana | 29/11/2017 | 36 months | Shri A.P. Trivedi, XEN(KL) Shri Munib Ansari, AXEN (C) | Work in progress. |
| 13. | Appointment of Project Management Consultant (PMC) for capital & maintenance dredging work of DPT from firms / consortiums empanelled consultants from dredging work (Class-A, Category-A) by Indian Ports Association, New Delhi. | 6.36 Cr. | 5.38 Cr. | 15.32% below | LOA No. EG/WK/6112 /333 dated 15/11/2019 | M/s. AECOM India Pvt. Ltd., Gurgaon | 25/11/2019 | 36 months | Shri A.P. Trivedi, XEN(KL) Shri Munib Ansari, AXEN (C) | Work in progress. |
| 14. | Two years maintenance contract for railway track leading to Tuna from 0 to 11 Km DPT line (Take off point at 2.573 Km at GIM Yard to 13.54 Km including LC-1, LC-2. | 1.15 Cr. | 0.99 Cr. | 14% below | HW/WK/2391-I/14(A) dated 02/02/2019 | N/s. Dharti Construction | 11/02/2019 | 24 months | Shri V.R. Reddy Dy. C.E. (H) Shri M.R. Makhijani, AXEN (C) | Work in progress. |
| 15. | Two years maintenance contract for Non-Residential Building inside Cargo Jetty area (Civil Work). | 0.88 Cr. | Part-A 0.58 Part-B 0.01 Neet 0.57 Cr. | 33.33% below | NA | M/s. Shree Ganesh Construction, Anjar | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | TCN held on 21/01/2020 to recommend the acceptance of L-1 Offer. |
| 16. | Modification, alternation and addition to Godown No. 34 inside cargo jetty area | 1.78 Cr. | 1.15 Cr. | 35.34% below | HW/WK/2407-I/55 dated 01/07/2019 | M/s. Mepabhai Mandan & Co. | 01/07/2019 | 29/02/2020 (8 months) | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Work in progress. |
| 17 | Two years maintenance contract for cleaning and sweeping of office building & surrounding outside at New Kandla. | 1.67 Cr. | 0.99 Cr. | 41.11% Below | HW/WK/ dated 30/07/2019 | M/s. Dhanjibhai K. Patel. | 30/07/2019 | 29/07/2021 (24 months) | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Work in progress. |
| 18. | Annual Maintenance contract of Fender inside cargo jetty area (HD-01/19) | 1.28 Cr. | 1.51 Cr. | 18.35% above | EG/WK/1132 / 325 dated 11/11/2019 | M/s. Patel Construction Co. | 13/12/2019 | 12/12/2020 (12 months) | Shri V.R. Reddy Dy. C.E. (H) Shri M.R. Makhijani, AXEN (C) | Work in progress. |
| 19. | Annual Maintenance contract for Godown inside cargo jetty area for two years | 1.96 Cr. | 1.28 Cr. | 34.44% below | EG/WK/1125/327 dated 11/11/2019 | M/s. Mepabhai Mandan & Co. | 13/12/2019 | 12/12/2021 (24 months) | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Work in progress. |
| 20. | Maintenance contract for quay and transit area inside cargo jetty area for two years (05/19) | 1.14 Cr. | 0.99 Cr. | 13.00% below | HW/WK/2402-II/236 dated 19/09/2019 | M/s. Mahesh Construction, Adipur. | 18/09/2019 | 17/09/2021 (24 months) | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Work in progress. |
| 21. | Tree plantation near offices other buildings along roads etc. including two years maintenance contract at New Kandla (HD-06/19) | 0.96 Cr. | 0.71 Cr. | 25.16% | NA | M/s. Dhanji K Patel, Anjar | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Competent authority has raised some observations, which are under compliance. |
| 22. | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla (HD-08/19). | 1.12 Cr. | 1.20 Cr. | 7.21% above | EG/WK/1130 /326 dated 11/11/2019 | M/s. Patel Construction Co. | 18/12/2019 | 17/12/2019 (12 months) | Shri V.R. Reddy Dy. C.E. (H) Shri M.R. Makhijani, AXEN (C) | LOA issued on 11/11/2019. |
| 23. | Providing screen wall of M.S. Structure to protect West Gate-III office Building from dust (HD-08/19). | 0.78 Cr. | 0.74 Cr. | 5% below | NA | M/. Viyuha Infrabuild, Adipur | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Acceptance of L1 Offer approved by the competent authority. |
| 24. | Housekeeping and cleaning of office building inside Cargo Jetty Area for 2 years (HD-10/19). | 0.54 Cr. | NA | NA | NA | NA | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | TC Note sent for technically qualifying the bidders. |
| 25. | Two years maintenance contract for office building outside Port area (Civil Work) HD-02/19 | 0.89 Cr. | 0.64 Cr. | 27.27% below | EG/WK/ dated 30/11/2019 | M/s. Mohit Construction | 13/12/2019 | 12/12/2021 (24 months) | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Work Order issued on 13/12/2019. Work in progress. |
| 26. | Improving the road network inside cargo jetty area. Providing RCC paving HD-12/19 | 8.01 Cr. | 5.05 Cr. | 39.02% | NA | M/s. Patel Construction Co., Gandhidham. | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri M.R. Makhijani, AXEN (C) | Proposal for acceptance of L1 offer sent to Finance. |
| 27. | Improving the fendering arrangement inside cargo jetty area HD-14/19. | 2.85 Cr. | 3.61 Cr. Part-A 3.54 Cr. Part-B 0.07 Cr. | Part-A 26.99% above & Part- B (Credit Item) 59.03% below | NA | M/s. Patel Construction Co., Gandhidham. | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri M.R. Makhijani, AXEN (C) | TC recommended to call the L-1 bidder for negotiation. |
| 28. | Development of equipment to remove cargo / solid waste periodically from road to maintain high standard of hygienic and to avoid pollution and contamination of cargo in Port area HD-15/19. | 1.34 Cr. | NA | NA | NA | NA | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | Shortfall / clarification sought from the bidders. |
| 29. | Improving the road network inside cargo jetty area. Providing Asphalt paving (Stage-II) HD-16/19 | 7.34 Cr. | NA | NA | NA | NA | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | TCN to pre-qualify the bidders is being sent. |
| 30. | Up-gradation of open plot at Bunder Basin. HD-17/19 | 7.98 Cr. | NA | NA | NA | NA | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | TCN to pre-qualify the bidders is being forwarded. |
| 31. | Development of equipment for cleaning of all toilet block inside Orit area to maintain high standard of hygienic and to avoid pollution . (HD-20/19) | 1.88 Cr. | NA | NA | NA | NA | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | TCN to pre-qualify the bidders is being forwarded. |
| 32. | AMC for weigh bridges (Civil Work) inside Cargo Jetty Area | 0.71 | NA | NA | NA | NA | NA | NA | Shri V.R. Reddy Dy. C.E. (H) Shri Suresh Thacker, AE (C) | TCN to pre-qualify the bidders is being forwarded. |
| 33. | Construction of Oil Jetty No.7 at Kandla | 44.59 Cr. | 42.40 Cr. | (-) 4.93% below | CN-I/WK/ 1553/81 dated 26/10/2015 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | -- | -- | Shri Srinivas Rao, SE (PL) Shri Rajesh Meghani AXEN (C) | The work not yet started due to non-clearance of Environment and CRZ Clearance from concerned authorities. |
| 34. | Construction of Oil Jetty No:8 at Old Kandla | 110.84 Cr. | 99.08 Cr. | (-) 6.085% Below | No. EG/WK/9105/75 dated 28.02.2019 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | -- | _ | Shri Srinivas Rao, SE (PL) Shri Rajesh Meghani AXEN (C) | The work is awarded to M/s. Kargwal KM Joint Venture, Mumbai and approval letter No.EG/WK/9105/75 dated 28/02/19. The Work shall be started after receipt of environ-ment clearance from the concerned authorities. |
| 35. | Replacement and revamping of pipeline network at Oil Jetty area, Kandla (i) Appointment of Technical Advisor for the preparation of Tender documents, Bid Process Managements and PMC Services. | -- N.A. | -- 4.15 Cr. | -- N.A. | -- PL/WK/8306-II/6755-A dated 06/11/2017 | -- M/s. MECON Ltd., Delhi | -- 06/11/2017 | -- 05/01/2021 | Shri Shri A.P. Trivedi, SE (PL) Shri Munib Ansari, AXEN (C) | Work Order issued to IITM |
| 36. | S/R to fenders inside Oil Jetty Area | 0.81 Cr. (-) Credit part Rs.0.016 =0.80 | 0.82 Cr. (-) Credit part Rs.0.016 =0.80 | 1.17% above the net Est. cost & PMR | PL/WK/8329/107 dated 16/01/2019 | M/s. Patel Construction Co., Gandhidham. | 01/02/2019 (Scheduled) | 18 months | Shri A.P. Trivedi, SE (PL) Shri Suresh Thacker, AE (C) | Work is in progress. |
| 37. | Strengthening of Oil Jetty No. 3 at Old Kandla | 1.70 Cr. | 2.20 Cr. | 30.03 % above. | PL/WK/8318-I/1519 dated 31/07/2019. | M/s. Patel Construction Co., Gandhidham. | 05/08/2019 | 04/08/2020 (12 months) | Shri A.P. Trivedi, SE (PL) Shri Suresh Thacker, AE (C) | Work is in progress. |
| 38. | S/R to fire fighting pipeline at Oil Jetty | 0.69 Cr. (-) Credit part Rs.0.09 Cr. =0.59 | 0.63 Cr. (-) Credit part Rs.0.11 Cr. =0.52 | 12.61% and 25.88% below the Est. cost & PMR respecti-vely. | PL/WL/8311/323 dated 26/02/2019 | M/s. Mepabhai Mandan & Co., Gandhidham. | 12/02/2019 (Scheduled) | 12 months | Shri A.P. Trivedi, SE (PL) Shri Suresh Thacker, AE (C) | Work is in progress. |
| 39. | AMC for the fire fighting pipeline and water supply lines inside Cargo Jetty at Kandla. | 0.61 Cr. (-) Credit part 0.002 =0.60 | 0.36 Cr. (-) Credit part 0.003 =0.35 | Indivi-dually 41.14% below Part-A and 20% above Part-B and overall 41.65% below. | PL/WK/8345/1233 dated 15/07/2019 | M/s. Mepabhai Mandan & Co., Gandhidham. | 02/07/2019 | 12 months | Shri A.P. Trivedi, SE (PL) Shri Suresh Thacker, AE (C) | Work is in progress. |
| 40. | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years. | 0.94 Cr. | 0.66 Cr. | 30.51% below | PL/WK/8358/1522 dated 20/11/2019. | M/s. Premji Kanji Sorathia | 20/11/2019 | 19/11/2021 (24 months) | Shri A.P. Trivedi, SE (PL) Shri Suresh Thacker, AE (C) | Work is in progress. |
| 41. | Annual Maintenance Contract for residential & Non-residential buildings at New Kandla | 0.66 Cr. | 0.60 Cr. | 9% below | RW/WK/7763-I/628 dated 27/02/2019 | M/s. Patel Construction Co., Gandhidham. | 11/03/2019 | 10/03/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work is in progress. |
| 42. | Up-gradation of existing road from bye pass junction to IFFCO Plant Gate at Old Kandla. | 4.54 Cr. | 3.93 Cr. | 13.43% below | RW/WK/7768-I/770 dated 16/07/2019 | M/s. Dhanjibhai K. Patel, Anjar | 22/07/2019 | 21/03/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work is in progress. |
| 43. | Widening of existing road from IFFCO Gate to Oil Jetty entry Gate at Old Kandla | 0.74 Cr. | 0.54 Cr. | 27.50% below | RW/WK/ 7762-I/44 dated 23/08/2019 | M/s. Premji Kanji Sorathia, Gandhidham. | 09/09/2019 | 08/03/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work in progress. |
| 44. | AMC for Roads at Kandla 2018-19. | 0.89 Cr. | 0.65 Cr. | 27.53% below | RW/WK/ 7754 -I/66 dated 16/09/2019 | M/s. Mepabhai Mandan & Co., Adipur. | 17/09/2019 | 16/09/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work in progress. |
| 45. | Construction of dust bins at New Port Colony, New Kandla. | 0.52 Cr. | 0.33 Cr. | 32.22% below | RW/WK/ 7757 -I/121 dated 17/10/2019 | M/s. Viyuha Infrabuild, Gandhidham | 01/11/2019 | 31/07/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work in progress. |
| 46. | Maintenance Contract for Cleaning of SWD along road sides for 2 years (J.N Road, Link Road, bye pass road & O/s CJA) at NPC, New Kandla (18-20) | 0.55 Cr. | 0.32 Cr. | 41.90% below | RW/WK/ 7767-I/ dated 10/10/2019 | M/s. Vihat Construction Co., Adipur. | 21/10/2019 | 22/10/2021 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work in progress. |
| 47. | Providing service road from road leading W, G-1 to W, G-2 (Road leasing to 13th to 16th cargo berth) | 3.14 Cr. | 2.27 Cr. | 33.44% below | RW/WK/ 7734-I/201 dated 27/12/2019 | M/s. MMC Projects (India) P. Ltd., Gandhidham. | 15/01/2020 | 14/07/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work Order issued. |
| 48. | Maintenance Contract for Sanitation of New Port Colony, New Kandla for the year 2019-20. | 0.98 Cr. | 0.66 Cr. | 32.40% below | RW/WK/7784-I/45 dated 26/08/2019 | M/s. Vihat Construction Co., Gandhidham. | 02/09/2019 | 01/09/2021 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work in progress. |
| 49. | Up-gradation of existing road and surrounding area at CISF complex. | 0.69 Cr. | 0.46 Cr. | 33.57% below | RW/WK/7781-I/126 dated 27/10/2019 | M/s. Mepabhai Mandan & Co., Gandhidham. | 04/11/2019 | 03/05/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work Order issued. |
| 50. | Up-gradation of road from West Gate I to road leading to West Gate-II. | 0.84 Cr. | _ | _ | _ | _ | _ | _ | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Note send to TC meeting for qualifying the bidder to open their price bid. |
| 51. | Widening and up-grading existing road from J.N. Road to CISF Complex. | 0.84 Cr. | 0.61 Cr. | 27.56% below | RW/WK/ 7755-I/163 dated 28/11/2019 | M/s. Patel Construction Co., Gandhidham. | 11/12/2019 | 10/06/2020 | Shri Srinivas Rao, SE (R) Shri M.G. Shahdadpuri AE (C) | Work in progress. |
| 52. | Providing Legal, Technical and Financial transactions for all ongoing and future proposals of DPT on PPP / Captive Mode for the period of two years and further extendable for one year. | 3.27 Cr. | 1.98 Cr. | 39.25% below | EW/WK/ 4759/TA/79 dated 10/10/2019 | M/s. Infrastructure Development (Karnataka) Corpn. Ltd. (1deck) | 14/10/2019 as per work order | 2 years and further extendable for 1 year. | Shri Rajendra Prasad, SE (D) Shri Asnani, AE (C) Shri Gohil, XEN (PIC) | Work Order issued. Work in progress. |
| 53. | Strengthening of existing Environmental Management Cell at DPT. Appointment of Experts for two year and further extendable for one year. | 1.23 Cr. | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad, SE (D) Shri Nalin Padliya, JE (C) | Technical Bids has been opened and evaluation is under process and pre-audit remarks are under compliance. |
| 54. | Preparing and monitoring of Environmental Management Plan for DPT at Kandla. | 4.08 Cr. | 2.52 Cr. | 38.17% below | EW/WK/EMC/11023/ 2011-IV dated 05/12/2019 | M/s. Detox Corporation Pvt. Ltd. | 16/12/2019 | -- | Shri Rajendra Prasad, SE (D) Shri Nalin Padliya, JE (C) | Work Order issued. |
| 55. | Third Party inspection and quality assurance for the works costing more that Rs. 1.00 Cr. of Civil Engineering Department of DPT. | 1.35 Cr. | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad, SE (D) Shri Chandru Patai JE (C) | Technical bid has been opened and comparative statement submitted on 23/09/2019 for pre-audit report. |
| 56. | Appointment of Independent Engineer for the work of "Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis. | 1.44 Cr. | 1.18 Cr. | (-) 17.89% | EW/WK/ 4823/(IE) / 109 dated 22/10/2019 | M/s. Rina Services, s.p.a., Mumbai. | 01/11/2019 | 42 months | Shri Rajendra Prasad, SE (D) Shri Asnani, JE (C) | Work Order issued on 22/10/2019. Work commenced from 01/11/2019. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6 .	MARINE DEPARTMENT							                                                                                      AS ON 31.01.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hiring of 04 Nos. of 50/60 tonn Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 308.00 Cr. | 19.89% below Estimated Cost - OSL Ltd. 20.08% below Estimated Cost - KNK Ship | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. T. Srinivas, Deputy Conservator Shri Sunilkumar, Flotilla Supdt. | Board vide Resolution No. 56 in its meeting held on 12.08.2016 have approved to award the work to contractors. W.O. has been issued on 03/10/2016 & 22/09/2016. Integrity Pact Agreement signed. |
| 2 | Hiring of 01 Nos. of 60 T Bollard Pull Tug for a period of Ten years extendable further by one year on time charter basis. | 9.00 Cr. per year | 90.03 Cr. | 23.18% below estimated cost | 31/05/2018 | M/s. Polestar Maritime Ltd. Mumbai | 30/05/2018 | 29/05/2028 | Shri Rajan K. Gurav, COM, OOT, Vadinar. Shri Nayak, M.E. Gr.I | LOA issued on 28/03/2018. Work Order issued on 11/05/2018. Integrity Pact Agreement signed. |
| 3 | Supply, installation and commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | 30.11 Cr. | -- | M/s. Electronics Corporation of India Ltd., Hyderabad | -- | 24 months of supply installation & commissioning. AMC 10 years after installation | Capt. T. Srinivas, Deputy Conservator. Shri Sunilkumar, Flotilla Supdt. | LOA issued on 06/10/2018. Work Order issued on 31/01/2019. Integrity Pact Agreement signed. |
| 4 | Conversion of Pilot Launch ML Karishma as Dumb Barge. | 1.16 | 0.85 | 27% below | Executed on 05/08/2019 | M/s. SSR Marine Services Pvt. Ltd. Mumbai. | 01/08/2019 | 8 months 31/03/2020 | Capt. T. Srinivas, Deputy Conservator. Shri Sunilkumar, Flotilla Supdt. | LOA issued on 27/05/2018. Work Order issued on 30/07/2019. Integrity Pact Agreement signed. |
| 5. | Hiring of 3 Nos. 60T Bollard Pull Tug ( 2 Nos. for Vadinar & 1 No. for Kandla) on Charter / Rate per day for the period of 10 years extendable further by one year. | 8.80 Per Tug Per Year | 352.1 Cr. | 9.17% below estimate of KNK Ship Ltd. 7.42% below estimate of OSL | Executed on 06/01/2020 Executed on 06/01/2020 | M/s. KNK Ship Management, Mumbai M/s. Ocean Sparkle Ltd., Hyderabad. |  |  | Shri Rajan K. Gurav, COM, OOT, Vadinar. | LOA issued on 28/03/2018 Work Order issued on 11/05/2018 LOA issued on 28/03/2018 Work Order issued on 11/05/2018 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 31.01.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Under process | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri T. Venugopal, Secretary Shri Arvind B. Pradhan, Labour Officer. | Issued Work Order No. LB/WK/1083 (Bus-2019)/65 dated 18/01/2020. Work commenced from 01/01/2020. |
| 2 | Hiring of brand new make and model of 2018 on "monthly hire basis" and made and model not earlier than1st January, 2017 on "as and when required basis" diesel vehicles to DPT for a period of 03 years | 8.86 Cr. | 8.23 Cr. | 7.11% Below | -- | M/s. Shree Ganesh Travels, Mumdra | 01/07/2019 | 30/06/2022 | Shri T. Venugopal, Secretary. Shri Rajender Singh, Dy. Secretary. | Work commenced from 01/07/2019. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	MEDICAL DEPARTMENT										                                            AS ON 31.01.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 7.80 Cr. | Party offered 20% discount on the monthly bill amount. | 20% discount on the monthly bill amount. | MH/SP/11/ 2016-17 dated 03/10/2017 | M/s. Mars Remedies, Jamnagar | 25/10/2017 | 3 years extendable for six months on mutual consent on same discount terms and conditions. | Dr. (Mrs.) K. Gandhi Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	TRAFFIC DEPARTMENT											                	AS ON 31.01.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N I L |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

9.	FINANCE DEPARTMENT										                                     AS ON 31.02.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |

*****