DEENDAYAL PORT TRUST

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 30.09.2021

| Sr. No. | Name of work and location | Estimated cost (Rs.) in lakh | Tendered Cost (Rs.) in lakh | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 8181.98 | 6359.61 | 18.91 Below | EL/WK/2472/ 480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Commenced on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri Susil Chandra Nahak, Dy. CME | Comprehensive A.M.C. work in progress. |
| 2. | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 15570.46 | 14446.38 9685.90 towards capital cost &4760.48 towards O&M Charges. | 7.22% Below | EL/WK/2491/ 1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri D.K. Hazra, XEN(E) | Comprehensive AMC work in progress. |
| 3. | Maintenance Contract of 3 Nos. ELL Wharf Cranes of 25T capacity 4 Rope of M/s. TIL make alongwith Grab inside Cargo Jetty Area for a period of 2 years. | 360.00 | 394.20 | 9.5% above | EL/WK/2594/ 4050 dated 19/11/2020 LOI No. EL/AC/2594(a)/ 4157 Dt.05/11/2020 | M/s. R.S. Electricals, Gandhidham | 05/11/2020 | 04/11/2022 | Shri Dana Manohar, XEN(M) | Work in progress. |
| 4 | Design, Manufacture, Supply Erection, Testing, Commissioning & Operation of 02 Nos. of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 9181.77 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit (LC) | 08 months from the date of opening of letter of credit (LC) | Shri Dana Manohar, XEN(M) | CAMC work in progress. |
| 5. | Repairs to 30 Mtr High Mast Towers & AMC of Area Lighting at inside Cargo Jetty Area for a period of Two Years. | 350.44 | 312.60 | 10.80% Below | EL/AC/2538/138 dated 01/01/2020 | M/s. C.K. Electricals, Surat | 01/01/2020 | 31/12/2021 | Shri D.K. Hazra, XEN(E) | Work is in progress. |
| 6. | Maintenance Contract of 03 Nos. 25T and 02 Nos. 16T capacity MBE make wharf cranes, along with Grabs for a period of two years at inside Cargo Jetty Area. | 632.40 | 630.00 | 0.38% below | EL/WK/2549(b)/ /516 dated 16/08/2019 | M/s. R. S. Electricals, Gandhidham | 16/08/2019 | 15/08/2021 | Shri Dana Manohar, XEN(M) | Work is in progress. |
| 7 | Annual maintenance Contract of Liebherr make HMC :- LHM 550- S/N:- 141143 & LHM 550-S/N :- 141169 for the period of two year at birth No. 13 inside Cargo jetty area. | 484.16 | 312.00 | 35.56 % below | EL/WK/2553/671 dated 20/07/2020 | M/s. R.S. Electricals, gandhidham | 20/07/2020 | 19/07/2022 | Shri Dana Manohar, XEN (M) | AMC is progress |
| 8. | Restoration of power supply & Re-Conditioning of Electrical installation at Berth No 13th & 15th at inside Cargo jetty Area. | 259.76 | 186.36 | 28.26% below | EL/WK/2539/268 dated 23/01/2020 | M/s. C.K. Electricals, Surat | 23/01/2020 | 22/09/2020 | Shri D.K. Hazra, XEN(E) | Work in progress. Proposal for extension is in process. |
| 9. | Maintenance Contract for HT & LT Electrical Installations including substations, overhead Lines, Residential, Non-Residential, Hospital and School Buildings outside Cargo Jetty Area. | 398.48 | 357.89 | 10.18% below | EL/WK/2557/383 dated 10/02/2020 | M/s. Sterling & Wilson Ltd | 10/02/2020 | 09/02/2023 | Shri D.K. Hazra, XEN(E) | AMC is in progress. |
| 10. | Operation and Maintenance of 66/11kV and 11/0.433kV Substation inside Cargo Jetty area at DPT, Kandla for a period of two years. | 312.46 | 252.00 | 19.35% below | EL/WK/2626/562 dated 01/07/2020 | M/s. Ascent Electrical Engineers, Jamnagar | 01/07/2020 | 30/06/2022 | Shri D.K. Hazra, XEN(E) | AMC is in progress. |
| 11. | Annual Rate contract for supply & laying of HT/LT underground cables at inside and outside cargo jetty area. | 261.18 | 232.43 | 11.00% below | EL/WK/2608/1295 dated 05/04/2021 | M/s. Onix Structure Pvt. Ltd, Rajkot | 05/04/2021 | 04/04/2021 | Shri D.K.Hazra, XEN(E) | ARC is in progress. |
| 12. | Design, Supply, Installation, Erection, Testing and Commissioning of DC Over Head/UG 11KV line for providing Power Supply to SIPC of DPT at Kandla. | 533.38 | 429.39 | 19.50% | EL/WK/2613/4 dated 05/02/2021 | M/s. Technisys Eng.Pvt. Ahmedabad | 05/02/2021 | 04/08/2021 | Shri D.K. Hazra, XEN(E) | Termination proposal has Been approved. Letter under issuance. |
| 13. | Replacement of existing feeder pillar of High Mast & Lattice Towers with FRP Feeder Pillar | 109.59 | 107.97 | 44.99% below | EL/WK/1948/ 1253 dated 26/03/21 | M/s. Rajdeep Electricals Pvt. Ltd, G’dham | 31/03/2021 | 28/07/2021 | Shri Chitrang Vyas, AXEN(E) | Work is in progress. |
| 14. | Supply, Installation, Testing & Commissioning of five numbers 100 M.T. Capacity, Pit-less Type, fully electronic, Road Weighbridges with Five Years Comprehensive Maintenance contract after expiry of two years guarantee Period. | 91.15 | 74.85 | 17.88% below | ML/WK/3942/ 596 dated 16/12/2019 | M/s. Techno Scale Industries, Ahmedabad | 16/12/2019 | 120 days i.e. 13/04/2020 | Shri Mani Pushpak, SE(M) | Board has approved the proposal for outsourcing of weigh bridges and accordingly, the work is not required to be executed. |
| 15. | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weigh bridges (15Kmph speed) of 140Mt capacities including comprehensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 150.79 | 147.67 | (-)2.07% Below | No.ML/WK/3916-II/738 dated 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., E-1, TVK Industrial Estate, Guindy, Chennai - 600032 | 05/01/2019 | 120 days, i.e. 04/05/2019 Further extension granted from 05/05/2019 to 31/01/2021 or 120 days after clearance from upgradation of existing Rail Network inside Cargo Jetty area, whichever is later as per recomm-endations of variation Committee. | Shri Rajesh Road (EIC) | Materials have been received at site. 2 Nos. of Weigh Bridges have been installed and commissioned. |
| 16. | Comprehensive Annual Maintenance Contract for Port owned five nos. of Pilot Launches, one no. Survey Launch & two nos. of Mooring Launches for a period of two years. | 435.70 | 349.40 | 19.81% below | ML/WK/3992/97 dated 28/03/2021 | M/s. SSR Marine Services Pvt. Ltd., Thane. | -- | 24 Months | Shri Rajdeep, Marine Engineer Gr.I | Work in progress. |
| 17. | Supply, installation, commissioning, operation and maintenance of 10 Nos. of T RCC Composite Weighbridges on Revenue sharing basis inside custom bound area of DPT for a period of 10years & buy-back of 15Nos. Road Weighbridges. | 1392.74 | -- | -- | -- | -- | -- | 10 years | Shri Mani Pushpak, SE(M) | The online Technical bid has been opened on 23/03/2021. The technical bids are under scrutiny. File sent to finance for further scrutiny. |
| 18. | Supply, Installation, Testing and Commissioning of remote operated water curtain system, fire alarm, hooter & its accessories at Oil Jetty No. 1, Kandla | 204.77 | -- | -- | -- | -- | -- | 120 days | Shri Mani Pushpak, SE(M) | The online technical bids has been opened on 09/04/2021. Shortfalls have been called for. Pre-audit report on technical bid & shortfall approved by AAO (W/A) on 24/08/2021. Note to TC to be submitted. The scheme is proposed to be dropped in budget. |
| 19 | Supply, installation, Testing & Commissioning of 01 no. kirloskar Make vertical Turbine Fire Fighting pump – Diesel engine driven located at cargo jetty area No- 01 ‘’ through Authorized dealer of kirloskar Brothers Ltd. Or OEm | 157.08 | - | - | - | - | - | 180 days | Shri Mani Pushpak, SE(M) | Tender published on 04/09/2021 with date of opening on 28/09/2021. Date extended upto 05/11/2021. |
| 20 | Major Repair Work of Heave Up Barge Bhimsen. | 166.77 | - | - | - | - | - | 120 days | Shri Rajdeep, Marine Engineer Gr.I | Tender published on 30/09/2021 with date of opening on 30/10/2021. Date extended upto 05/10/2021. |
| 21 | Development, Operation and Maintenance of Container Terminal at Berth Nos. 11 and 12 at Kandla Port on PPP Mode | 15981.00 | 15981.00 | N.A. | MS/WK/4003-V/357 dated.19/2/2016 | M/s. Kandla International Container Terminal | 29/02/2016 | 15/02/2018 | Shri Susil Chandra Nahak, Dy. CME | LOI issued. Concession Agreement signed on 29/02/2016. Project fully commissioned on 15/02/2018. |
| 22 | Appointment of Consultant for the work of Mechanization of handling of Fertilizers at Kandla Port | 166.67 | N.A | N.A | N.A | N.A | N.A | N.A | Shri Susil Chandra Nahak, Dy. CME | Project mode transferred from EPC to PPP mode. So, the services of existing Transaction Advisor appointed for PPP projects has been rendered. |
| 23 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 12094.14 | 12232.53 | 0.9% above the estimated cost | LoA issued vide MS/WK/4025-II/GIM-265 dated 31/03/2017 | M/s. Rishi Shipping, Gandhidham | 31/03/2017 | 31/03/2018 | Shri Rajesh Roat, (EIC) | LoA issued on 31/03/2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect. |
| 24 | Mechanization of fertilizer handling facility at Berth No. 14, Deendayal Port | 30028.00 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME | As per direction of Ministry, RFQ was invited on 31/07/2021. As per schedule pre-bid conference held on 01/09/2021 in which four prospective bidders participated & submitted their queries. The last date of submission of Applications was on 14/09/2021. Applicants have submitted the RFQ fees and RFQ documents in hard copies. Evaluation of submitted RFQ documents is under process. |
| 25 | Appointment of Consultant for carrying out environmental impact assessment and environmental management plan studies for development of another ship-repairing facility at Vadinar, to obtain statutory clearances from State authorities & MoEF&CC. | 52.02 | 35.10 | 32.53% Below | LOA No. DD/WK/3050/ EC/598 dated 08/12/2020. | M/s. Envision Enviro Technologies Pvt. Ltd., Surat | 08/12/2020 | 07/12/2021 12 Months | Shri Shiva Mudaliyar EIC (DD) | The work has been commenced on 08/12/2020 and inspection report hs been submitted. |
| 26 | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhidham Area for period of three years. | 154.92 | 139.22 | 19.14% below | DD/WK/4309/338 dated 04/08/2021 | M/s. Inspection & Engineering Services, Ahmedabad | 04/08/2021 | 03/08/2024 | Shri Shiva Mudaliyar EIC (DD | Work Order issued on 04-08-2021. |
| 27 | Comprehensive AMC of Mech works and equipment | 431.40 | -- | -- | -- | -- | -- | 5 years | EIC (M) | Technical bid opened & submitted for approval |
| 28 | Supply, installation, testing & commissioning of Sprinkling System for coal dust suppression in 34-hectare coal yard with five Years Operation & Comprehensive Main-tenance Contract | 2811.33 | -- | -- | -- | -- | -- | 1 years supply & installation, and, 5 years O&M | Dy. CME | Technical submission under process. |
| 29 | Outsourcing of 02 Nos. each Truck Mounted Mist Cannon system, and, Truck Mounted Road Sweeper system, along with comprehensive operation & maintenance, for the period of three years at DPT | 892.73 | 1018.80 | 14.12 % below | -- | M/s sambhav corporation | -- | 3 years | Dy. CME | Price bid open & Submittes for approval. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 30.09.2021

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | -- | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 2 | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | -- | M/s. Aeromarine Pvt. Ltd., Mumbai |  | 3 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/RM/8009/1947 dated 03/03/2020. |
| 3. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | 49.32 Cr. | 6.62% below | -- | M/s. Parsh Construction and Foundations Pvt. Ltd., Mumbai | -- | 18 months | Shri Vikash A.C. XEN (Civil), | Work Order issued vide No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. |
| 4 | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 | 5.01 % above | -- | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri Vikash A.C. XEN (Civil), | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. |
| 5. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | 1.06 Cr. | 2.98% above | -- | M/s. Abhay Intelligence & Security Services, Vadodara. | 14/03/2020 | 2 years | Shri Vikash A.C. XEN (Civil), | Work Order issued vide No. OOT/C-WK/RM/4002/2001 dated 12/03/2020 |
| 6. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 | 6.01 % below | -- | M/s. Safari Travels, Balasinor | 07/03/2020 | 3 years | Shri Rajesh Roat, XEN (E&M), | Work Order issued vide No. OOT/ME/WK/6008/1795 dated 06/02/2020. |
| 7. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | -- | M/s. Pariya Electricals, Vadinar. | 01/04/2021 | 3 years | Shri Rajesh Roat, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2021. |
| 8. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.44 Cr. | 2.83% above | -- | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years | Shri Rajesh Roat, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. |
| 9. | Painting work for residential and Non-residential buildings Port Colony at Vadinar | 2.58 | 1.61 | 37.66% Below | -- | M/s. Shreeji Enterprise Gondal | ----- | 18 Months | Shri Vikash A.C. XEN (Civil), | LOA issued vide OOT/C-WK/RM/4049/548, Dated 19/07/2021 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 30.09.2021

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agree ment No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Two years maintenance contract for cleaning and sweeping of office building & surrounding outside at New Kandla. | 1.67 Cr. | 0.99 Cr. | 41.11% Below | HW/WK/ 2408 dated 30/07/2019 | M/s. Dhanjibhai K. Patel. | 30/07/2019 | 29/07/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress |
| 2. | Annual Maintenance contract of Fender inside cargo jetty area (HD-01/19) | 1.28 Cr. | 1.51 Cr. | 18.35% above | HW/WK/2375 dated 13/12/2019 | M/s. Patel Construction Co. | 13/12/2019 | 12 Months (ext. granted Upto 17/12/2021) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 3. | Annual Maintenance contract for Godown inside cargo jetty area for two years(HD-03/19) | 1.96 Cr. | 1.28 Cr. | 34.44% below | HW/WK/2405/ 338 dated 13/12/2019 | M/s. Mepabhai Mandan & Co. | 13/12/2019 | 12/12/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. Anticipated variation 28% approved by the competent authority.. |
| 4. | Maintenance contract for quay and transit area inside cargo jetty area for two years (05/19) | 1.14 Cr. | 0.99 Cr. | 13.00% below | HW/WK/2402 -II/236 dated 19/09/2019 | M/s. Mahesh Construction, Adipur. | 18/09/2019 | 17/09/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work completed on 17/09/2021. |
| 5. | Tree plantation near offices other buildings along roads etc. including two years maintenance contract at New Kandla (HD-06/19) | 0.96 Cr. | 0.72 Cr. | 25.06% | HW/WK/ 2380-I/99 dated 13/04/2020 | M/s. Dhanji K Patel, Anjar | 24/04/2020 | 23/04/2022 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 6. | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla (HD-07/19). | 1.12 Cr. | 1.20 Cr. | 7.21% above | HW/WK/2379-III /332 dated 05/12/2019 | M/s. Patel Construction Co. | 18/12/2019 | 12 months (Ext. of work Granted upto 17/12/2021) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 7. | Housekeeping and cleaning of office building inside Cargo Jetty Area for 2 years (HD-10/19). | 0.54 Cr. | 0.4128 Cr. | 23.43% below | HW/WK/ 2422-I/367 dated 20/02/2021 | M/s. Shree Ganesh Construction, Anjar. | 06/03/2021 | 05/03/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 8. | Two years maintenance contract for office building outside Port area (Civil Work) HD-02/19 | 0.89 Cr. | 0.64 Cr. | 27.27% below | HW/WK/ 2336-I/339 dated 13/12/2019 | M/s. Mohit Construction | 13/12/2019 | 12/12/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 9. | Improving the fendering arrangement inside cargo jetty area HD-14/19. | 2.85 Cr. | 3.54 Cr. | 24.39% above | HW/WK/ 2392/137 dated 02/06/2020 | M/s. Patel Construction Co., Gandhidham. | 15/06/2020 | 12 months Extension granted upto 14/12/2021. | Shri Srinivas Rao, SE (H) | Work in progress. |
| 10. | Development of equipment to remove cargo / solid waste periodically from road to maintain high standard of hygienic and to avoid pollution and contamination of cargo in Port area HD-15/19. | 1.34 Cr. | 0.64 Cr. | 52.31% below | HW/WK/ 2413-I/167 dated 23/07/2020 | M/s. Patel Construction Co., Gandhidham. | 28/07/2020 | 12 months (Ext granted upto 27/10/2021) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 11. | Development of equipment for cleaning of all toilet block inside Orit area to maintain high standard of hygienic and to avoid pollution . (HD-20/19) | 1.88 Cr. | 1.16 Cr. | 38.04% below | HW/WK/ 2428/104 dated 21/04/2020 | M/s. Patel Construction Co., Gandhidham. | 04/05/2020 | 03/05/2022 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 12. | Providing toilet block and drinking water facility in 66,40, 34 H area and on Berth No.13 & 15 in CJA under Swachh Bharat Abhiyan. | 2.03 Cr. | 1.55 Cr. | 23.38% below | HW/WK/ 2447/268 dated 28/10/2020 | M/s. Quality Constructions, Gandhidham. | 01/11/2020 | 9 months (ext granted upto 31/10/2021) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 13. | AMC of Custom fencing wall and gates of Cargo Jetty and Bunder area. | 0.74 Cr. | 0.48 Cr. | 35.20% above | HW/WK/ 2420/320 dated 25/01/2021 | M/s. Sanjay K. Sorathiya & Co. | 05/02/2021 | 04/02/2022 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 14. | Upgrading the road network of 66 hectare. | 17.42 Cr. | 12.72 Cr. | 26.95% Below | HW/WK/ 2476/239 dated 09/09/2020 | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd., Gandhidham. | 23/09/2020 | 12 months | Shri Srinivas Rao, SE (H) | Work completed on 22.09.2021 |
| 15. | Maintenance contract for roads and RCC culverts inside CJA at New Kandla for 2 years. | 1.75 Cr. | 1.84 Cr. | 5.74% above | HW/WK/ 2443/401 dated 31/03/2021 | M/s. Shree Ganesh Construction | 16/04/2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 16. | Two years contract for cleaning of storm water drain inside Cargo Jetty area. | 0.80 Cr. | 0.42 Cr. | 47.81% below | HW/WK/ 2441/180(A)dated 10/07/2020 | M/s. Narayan Construction | 29/07/2020 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 17. | Development of plots, roads & SWD in 34 Ha area inside Cargo Jetty Area. | 57.08 Cr. | 36.60 Cr. | 35.89% below | HW/WK/ 2486/363 dated 20/02/2021 | M/s. Bhimji Velji Soratia Construction P. Ltd. | 06/03/2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 18. | Providing Screen wall surrounding the coal stacking yard inside Cargo Jetty Area of DPT | 18.63 Cr. | 14.97 Cr. | 19.63% below | HW/WK/2486 363 dated 20/02/2021 | M/s. Mohandas V. Rajani. | 15/08/2021 | 12 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 19. | Construction of 3 Nos. Toilet Blocks on Central Road inside cargo jetty area at New Kandla (HD-12/20) | 1.40 Cr. | 1.18 Cr. | 14.39% below | HW/WK/2477/299 dated 15/12/2020 | M/s. Dharam Construction Co. | 28/12/2020 | 27/11/2021 11 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 20. | Development of Parking yards for trucks/vehicles for pre checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 Cr. | 14.59 Cr. | 12.87% below | HW/WK/2446/436 dated 26/06/2021 | M/s. Indian Construction Co., | 08/07/2021 | 07/07/2023 & 24 months Maintenance | Shri Srinivas Rao, SE (H) | Work in progress. |
| 21. | Upgradation of Plots, Roads &SWD behind Berth No. 7 to 10 inside Cargo Jetty area. | 8.20 Cr. | 5.56 Cr. | 32.08% below | HW/WK/2490/496 dated 29/07/2021 | M/s. Krishna Construction | 29/07/2021 | 11 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 22. | Construction of Dome Shaped Storage Sheds inside cargo jetty area – Phase-I | 46.53 Cr. | 35.93 Cr. | 22.78% below | HW/WK/2475/456 dated 16/06/2021 | M/s. Patel Construction Co., Gandhidham. | 30/06/2021 | 29/06/2021 12 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 23. | Development of Land in the West of Existing 66 hectare area for storage of cargo (Extension of custom bonded area) | 42.81 Cr. | 33.38 Cr. | 22.02% below | HW/WK/ 2457/355 dated 17/02/2021 | M/s. Kalthia Engineering Construction Ltd. | 02/03/2021 | 01/03/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 24. | Construction of watch tower inside cargo jetty area | 3.04 Cr. | 2.84 Cr. | 6.22% below | HW/WK/ 2470/407 dated 09/04/2021. | M/s. Viyuha Infrabuild | 23/04/2021 | 8 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 25. | Two years contract for supply and maintenance of railway tracks inside and outside Cargo Jetty Area for 2 years | 2.59 Cr. | 2.03 Cr. | 21.40% below | HW/WK/ 2487/359 dated 20/02/2021. | M/s. Laxyo Entergy Ltd. | 06/03/2021 | 05/03/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 26. | R/M of Maintenance Jetty - Repairs and Maintenance of Pontoons and Walkways of SNA Jetty and Flotila Jetty | 2.77 Cr. | 3.37 Cr. | 10.51% above | HW/WK/ 2949/462 dated 25/06/2021. | M/s. Patel Construction, Gandhidham | 08/07/2021 | 07/07/2021 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 27. | Two years maintenance contract for railway track leading to Tuna from 0 to 11 Km KPT line (Take off point at 2.573 Km at GIM Yard to 13.54 Km) including LC-1, LC-2 | 1.19 Cr. | 0.908 Cr. | 23.77% below | HW/WK/2515/432 dated 31/05/2021 | M/s. Patel Construction, Gandhidham. | 14/06/2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 28. | Maintenance contract for quay and transit area inside cargo jetty area for two years | 1.04 Cr. | 0.86 Cr. | 16.77% | HW/WK/2617/12 dated 24/09/2021 | M/s. Sanjay Soratia, Anjar. | 10/10/2021 | 24 months | Shri Srinivas Rao, SE (H) | Work order issued on 24.09.2021 |
| 29. | Providing Labour Amenities Centre at various location inside Cargo Jetty Area. | 1.53 Cr. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Technical bid under scrutiny. |
| 30. | Improving / Upgradation of Custom Fencing Wall of Cargo Jetty and Bunder Area | 7.68 Cr. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Tender committee meeting held on 29/09/2021. |
| 31. | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 Cr. | 2.43 Cr. | 35.73% Below | HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd., Gurgaon - 122015 Haryana- India | 11/02/2021 | 36 months | Shri Srinivas Rao, SE (H&D) | Work in progress. |
| 32 | AMC of RO plants at Kandla for years 2021-23 | 0.22 | NA | NA | NA | NA | NA | NA | Shri Srinivas Rao, SE (H&D) | Scrutiny report sent to SA (circle office) and AAO (W/A) |
| 33. | Dismantling of existing godown no.10 to 14 and 25 inside cargo jetty area. | 0.36 | NA | NA | NA | NA | NA | NA | Shri Srinivas Rao, SE (H&D) | Technical bid under scrutiny |
| 34. | Appointment of Project Management Consultant (PMC) for capital & maintenance dredging work of DPT from firms / consortiums empanelled consultants from dredging work (Class-A, Category-A) by Indian Ports Association, New Delhi. | 6.36 Cr. | 5.33 Cr. | 15.32% below | LOA No. EG/WK/6112 /333 dated 15/11/2019 | M/s. AECOM India Pvt. Ltd., Gurgaon | 25/11/2019 | 36 months | Shri Srinivas Rao, SE (H&D) | Work in progress. |
| 35. | Dredging in the Navigational Channel and alongside Cargo Berth / Oil Jetties at Deendayal Port Trust for the year 2020-23. Location at Kandla. | 393.80 Cr | 310.04 Cr. | 21.27% below | LOA No. EG/WK/6116/ 182 dated 10/03/2021 | M/s. Adani Port and Special Economic Zone Ltd., Ahmedabad. | 09/04/2021 | 36 months | Shri Srinivas Rao, SE (H&D) | Work in progress. |
| 36. | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years. | 0.94 Cr. | 0.65 Cr. | 30.506% below | PL/WK/8358/1522 dated 20/11/2019. | M/s. Premji Kanji Sorathia | 20/11/2019 | 19/11/2021 (24 months) | Shri Rajendra Prasad SE (PL) | Work in progress. |
| 37. | Strengthening of RCC custom fencing wall of Oil Jetty and Providing CCTV lighting arrangement at Old Kandla - Strengthening of RCC Custom Fencing Wall. | 1.12 Cr. Credit part 0.21 Cr. | Part-A 0.76 Cr. Part-B 0.01 Cr. | 31.29% below | PL/WK/8420-I/2652 dated 14/10/2019. | M/s. Rajput Infrastructure Company, Gandhidham. | 28/10/2020 | 06 months (ext upto 27/10/2021) | Shri Rajendra Prasad SE (PL) | Work in progress. 2nd RA Bill Paid. |
| 38. | Annual Maintenance Contract for the Buildings, Walkway, trestles, Fire Fighting, Pipelines, Garden inside and outside Oil Jetty area at Old Kandla | 1.29 Cr. Credit part 0.50 Cr. | Part-A 1.26 Cr. Part-B 0.04 Cr | 9.48% above | PL/WK/8316-II/125/A dated 12/02/2020 | M/s. Mahesh Construction, Adipur | 15/02/2021 | 12 months | Shri Rajendra Prasad SE (PL) | Work in progress. 1st RA Bill Paid. |
| 39. | Improving Storm Water drainage system at Old Kandla. | 2.31 Cr. | 1.67 Cr. | 27.54% below | --- | M/s Shree Ganesh Construction, Adipur | -- | 11 months | Shri Rajendra Prasad SE (PL) | Pre-acceptance letter issued to M/s Shree Ganesh Construction. |
| 40. | Providing RCC drinking water tank. | 1.52 Cr. | -- | -- | --- | -- | -- | -- | Shri Rajendra Prasad SE (PL) | Re-Revised Pre-Audit Report being Prepared |
| 41. | Improving existing Oil Jetty structures at Oil Jetty No. 1, 2, 4 | 8.20 Cr. | 8.08 Cr. | 1.55% below | Pl/WK/8421-I/2238 dated 10/06/2020 | M/s. Sarjan Construction Pvt. Ltd. | 20/06/2020 | 18 months | Shri Rajendra Prasad SE (PL) | Work in progress. |
| 42. | Construction of Fire Bridge Station at Old Kandla | 1.65 Cr. | Part-A 1.34 Cr. And Part-B 776621.00 | 13.95% Below | - | M/s Ankita Construction, Adipur | - | 12 months | Shri Rajendra Prasad SE (PL) | Pre-acceptance letter issued to M/s Ankita Construction. |
| 43. | Improving of Oil Jetty Gate and Canteen at Old Kandla | 0.71 | 0.62 | 13.29% Below | PL/WK/8148-I/641 dated 08/08/2021 | M/s Mepabhai Mandan & co | - | 12 months | Shri Rajendra Prasad SE (PL) | Work In progress. |
| 44. | Maintenance Contract for cleaning of SWD along road sides for 2 years (J.N. road, link road, bye pass road & O/s CJA) at New Port Colony New Kandla (18-20) | 0.55 Cr. | 0.32 Cr. | 41.90% Below | RW/WK/7767-I/ dated 10/10/2019 | M/s. Vihat Const. Co., Adipur | 21/10/2019 | 20/10/2021 | Shri Hemant Kumar Bhaskar, XEN (R) | Work in progress. |
| 45. | Maintenance Contract for Sanitation of New Port Colony New Kandla for year 19-20. | 0.98 Cr. | 0.66 Cr. | 32.40% below | RW/WK/7784-I/45 dated 26/08/2019 | M/s. Vihat Const. Co., G'dham | 02/09/2019 | 01/09/2021 | Shri Hemant Kumar Bhaskar, XEN (R) | Work in progress. Extension applied for 04 months. |
| 46. | Resurfacing of existing road from NH Junction to Bye pass - KK Road Junction. | 8.19 Cr. | 5.91 Cr. | 27.78% below | RW/WK/7777-I/616 dated 18/12/2020 | M/s. Mepabhai Mandan & Co., Adipur | 28/12/2020 | 27/09/2021 | Shri Hemant Kumar Bhaskar, XEN (R) | Work in progress. Applied for extension for 2 months. |
| 47. | Maintenance Contract for Residential & Non-Residential Building at Port Colony, New Kandla for 2 years. | 1.59 Cr. | 1.06 Cr. | 33.30% below | RW/WK/7790-I/509 dated 01/09/2020 | M/s. Rajput Infrastructure Co., Gandhidham. | 02/09/2020 | 01/09/2022 | Shri Hemant Kumar Bhaskar, XEN (R) | Work in progress |
| 48. | R/M of CISF Complex at New Kandla - Repairs to Toilet block at CISF Complex, New Kandla. | 0.50 Cr. | 0.45 Cr. | 11.01% below | RW/WK/7782-I/81 dated 16/02/2021 | M/s. Pars Enterprise, Gandhidham | 21/02/2021 | 20/08/2021 | Shri Srinivas Rao, SE (R) | Work in progress. Extension applied for 02 months |
| 49. | Up-gradation of service road leading to west gate-I from zero point at Kandla | 3.83 Cr. | 2.68 Cr. | 30.16% below | RW/WK/ 7800-I/178 dated 01/06/2021 | M/s. Mepabhal Mandan & Co., Adipur | 01/06/2021 | 30/11/2021 | Shri Hemant Kumar Bhaskar, XEN (R) | Work in progress. |
| 50. | Dismantling of Residential and Non - Residential buildings at New Kandla | 0.96 Cr. | 1.58 Cr. | 64.42% above | - | M/s. Symcom Exim (P) Ltd. Mumbai | - | - | Shri Hemant Kumar Bhaskar, XEN (R) | Submitted for acceptance of L-1 offer. |
| 51 | Annual maintenance Contract For Sanitation of New Port Colony, New Kandla | 0.64 Cr. | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(Road) | Technical Bid Opened On 28/09/2021. |
| 52 | Construction of Dr. Babsheb Ambedker Convention Centre, Gandhidham. | 33.08 Cr. | 28.83 Cr. | 12.84% below | TW/WK/ 7715-I/410 dated 07/02/2019 | M/s. Dipesh Construction Co., Anjar | 15/02/2019 | 14/02/2021 (ext upto 14/11/2021) | Shri M.T. Gohel, XEN (TD) | Work in progress. Applied for extension |
| 53 | Annual Maintenance Contract for Gardens at Shaktinagar & A.O Building for the period of 2 years | 0.61 Cr. | 0.41 Cr. | 34.51% below | TW/WK/ 7734-/174 dated 02/11/2019 | M/s. Praful A. Parmar | 01/08/2019 | 31/07/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. Applied for extension |
| 54 | Modernization of AO Building at Gandhidham Stage -II | 1.26 Cr. | 0.89 Cr. | 29.76% below | TW/WK 7717-I/345 dated 20/05/2020 | M/s. Pars Enterprise, Gandhidham. | 03/06/2020 | 02/06/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 55. | Annual Maintenance Contract for Sport Complex at Gopalpuri for the period of 2 years. | 0.65 Cr. | 0.42 Cr. | 35.35% | TW/WK 7764-I/371 dated 14/04/2020 | M/s. Patel Construction Co. | 16/04/2020 | 15/04/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 56. | Annual Maintenance Contract for Residential Building of Port Colony, Gopalpuri and AO Building at Gandhidham. | 1.15 Cr. | 0.68 Cr. | 40.95% below | TW/WK 7773/342 dated 13/03/2020 | M/s. Rajput Infrastructure, Gandhidham. | 13/03/2020 | 12/03/2021 | Shri M.T. Gohel, XEN (TD) | Work completed. |
| 57. | AMC for Whitewashing, Distempering & Painting to Resi. & NRB at Gopalpuri. KDLB, Gandhidham & Adipur for the year 2020-21. | 1.98 Cr. | 0.93 Cr. | 52.80% below | TW/WK 7760-I/88 dated 11/02/2021 | M/s. Mepabhai Mandan & Co. | 11/02/2021 | 10/02/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 58. | Maintenance of Public Health & Underground drainage at Gopalpuri Port Colony & KDLB Colony for the period of 2 years. | 2.52 Cr. | 1.33 Cr. | 47.12% below | TW/WK 7757-I/229 dated 05/12/2019 | M/s. Patel Cons. Co., Gandhidham. | 09/12/2019 | 08/12/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 59. | Modernization of Staff Club / Officer's Club at Gopalpuri | 2.15 Cr. | 1.82 Cr. | 15.57% below | TW/WK/7781-I/621 dated 14/10/2020 | M/s. Dhanjibhai K. Patel, Anjar. | 14/10/2020 | 13/10/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 60. | R/M of Arboriculture / Horticulture work in public building at Gopalpuri and KDLB Colony for the year 2020-22. | 2.19 Cr. | 1.15 Cr. | 47.36% below | TW/WK/7781-I/621 dated 14/10/2020 | M/s. Rajut Infrastructure, Gandhidham | 15/10/2020 | 14/10/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress |
| 61. | Strengthening of Sewage, Drainage, SWD, Culvert network at Gopalpuri, KDLB Colony | 2.98 Cr. | 1.45 Cr. | 51.18% below | TW/WK/7787-I/248 dated 21/04/2021 | M/s. Sterling Infrastructure Co. | 22/04/2021 | 21/04/2022 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 62. | AMC for cleaning & House Keeping works of DTP Hospital and Isolation Ward at Gopalpuri and Kandla (For Two Years). | 1.62 Cr. | 0.85 Cr. | 47.70% below | TW/WK/7798 dated 30/01/2021 | M/s. Patel Construction Co., Gandhidham. | 10/02/2021 | 09/02/2023 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 63. | Strengthening of Multi storey building with micro concreting, plinth protection at Gopalpuri | 6.61 cr. | 4.26 Cr. | 35.41% below | TW/WK/7794-I/ dated 26/03/2021 | M/s. Mohandas V. Rajani, Adipur | 01/04/2021 | 30/09/2022 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 64. | AMC for AO building at Gandhidham | 0.71 Cr. | 0.45 Cr. | 36.36% below | TW/WK/7799-I/110 dated 01/03/2021 | M/s. Rajput Infrastructure Co., Gandhidham. | 02/03/2021 | 01/03/2022 | Shri M.T. Gohil XEN(TD ) | Work in progress. |
| 65. | Providing power supply arrangement for air conditioner units installed at AO Building, Gandhidham. | 0.62 Cr. | 0.61 Cr. | 21.21% below | TW/WK/7796-I/247 dated 21/04/2021 | M/s. Mepabhai Manda & Co. | 22/04/2021 | 21/03/2022 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 66. | S/R to Quarters to Gopalpuri-Replacement of slabs, water proofing chajjas, walls etc. | 6.56 Cr. | 4.78 Cr. & 4.66 Cr. (Credit) | 27.26% below | TW/WK/7783/274 dated 24/05/2021 | M/s. Dhanjibhai K. Patel, Anjar | 24/05/2021 | 23/05/2022 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 67. | Construction of A,B, C and D type quarters at Gopalpuri. | 18.94 Cr. | 13.78 Cr. | 27.18% below | TW/WK/7785/299 dated 02/06/2021 | M/s. VC Project & Infra Pvt. Ltd. | 05/06/2021 | 04/06/2023 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 68. | Improving & up-gradation of gardens and land scalping at Gopalpuri (Renovation of Nehru park and rain water harvesting by strengthening of SWD network near recharging pond at Gopalpuri. | 4.79 Cr. | 2.40 Cr. | 49.81% below | TW/WK/7802-I/404 dated 16/07/2021 | M/s. Rainbow Infrastructure, Rajkot. | 03/07/2021 | 02/07/2021 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 69. | Construction of compound wall on vacant plots of Gandhidham Township - Removal / Prevention of Encroachment - Stage-II | 4.06 Cr. | 2.29 Cr. | 43.54% Below | TW/WK/7802-I/404 Dt 16/07/2021 | M/s Ankita Construction, Adipur | 26/08/2021 | 25/08/2022 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 70. | S/R to Non-Residential Building - Providing water proofing to terrace and interior wall of AO Building. | 0.67 Cr. | 0.41 Cr. | 39.11% Below | - | M/s Rajput Infrastructure Co., Gandhidham | - | - | Shri M.T. Gohil XEN(TD) | Price Bid Opened on 25/08/2021 |
| 71. | Construction of 14th & 16th Berth for Multi Purpose Cargo - Additional Piled Platform. | 83.05 Cr. | 64.03 Cr. | 22.89% below | CN/WK/ 2243 & 44-III/95(G) dated 06/06/2020 | M/s. Vijay Mistry Construction Pvt. Ltd., Ahmedabad. | 22/06/2020 | 21/05/2021 and extended upto 21/11/21 | Shri M.T. Gohel, XEN (C-I) | Work in progress. Extension granted upto 21/11/2021. |
| 72. | Retrofitting of existing Cargo Berth No. 7 (Panel 51 to 59) | 65.05 Cr. | 49.57 Cr. | 23.79% below | CN/WK/ 2273-IV/ Works/108 (G) dated 31/07/2020 | M/s. BMS-Marymatha JV., Surat. | 14/08/2020 | 13/07/2021 and extended upto 13/11/2021 | Shri M.T. Gohel, XEN (C-I) | Work in progress |
| 73. | Upgradation and strengthening of existing road from WG 2 to 16th Cargo Berth - Phase -I. | 69.18 Cr. | 41.50 Cr. | 40.02% below | CN-I/WK/2259/Works/92 dated 01/03/2021 | M/s. M.K.C. Infrastructure, Anjar. | 09/03/2021 | 11 months | Shri M.T. Gohel, XEN (C-I) | Work in progress. |
| 74. | Construction of SWD and Cable Trench at backup of Beth No 11 & 12 | 4.70 Cr. | 3.15 Cr. | 33.05% below | EG/WK/8112/225 dated 21/04/2021 | M/s. Dharti Construction Pvt. Ltd., Mumbai | 12/05/2021 | 10 months | Shri M.T. Gohel, XEN (C-I) | Work in progress. |
| 75. | Retrofitting cargo berth No 8 | 70.00 Cr. | - | - | - | - | - | - | Shri M. T. Gohil XEN(C-I) | Tender Opened on 28/09/2021 |
| 76. | Retrofitting cargo berth No 9 | 70.00 Cr. | - | - | - | - | - | - | Shri M. T. Gohil XEN(C-I) | Tender Opened on 28/09/2021 |
| 77. | Extension of custom bounded area in backup of 13th & 16th berth | 40.00 Cr. | - | - | - | - | - | - | Shri M. T. Gohil XEN(C-I) | NIT invited With date of opening on 25/10/2021 |
| 78. | Retrofitting of the Bunder Basin Structures | 10.00 Cr. | - | - | - | - | - | - | Shri M. T. Gohil XEN(C-I) | NIT invited With date of opening on 26/10/2021 |
| 79. | Construction of Oil Jetty No.7 at Kandla | 44.59 Cr. | 42.40 Cr. | 4.93% below | CN-I/WK/ 1553/81 dated 26/10/2015 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | 26/02/2020 | 25/08/2022 18 months | Shri Rajendra Prasad SE (P) | Work in progress. Extension under Process |
| 80. | Construction of Oil Jetty No.8 at Old Kandla | 105.51 Cr. | 99.08 Cr. | 6.09% Below | CN-I/WK/ 15571/work/243 dated 03/02/2021 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | 17/02/2021 | 18 months | Shri Rajendra Prasad SE (P) | Work in progress. |
| 81. | Augmentation of Liquid Cargo handling capacity by revamping of existing pipeline network at Oil Jetty area, DPT, Kandla. | 130.49 Cr. | 126.49 Cr. | 3.05% Below | -- | M/s Patel Corrrtech JV, Gandhidham | -- | 24 months | Shri Rajendra Prasad SE (P) | Work order issued. |
| 82. | Providing Legal, Technical and Financial transactions for all ongoing and future proposals of DPT on PPP / Captive Mode for the period of two years and further extendable for one year. | 3.27 Cr. | 1.98 Cr. | 39.25% below | EG/WK/ 4759/TA/79 dated 10/10/2019 | M/s. Infrastructure Development (Karnataka) Corpn. Ltd. (1deck) | 14/10/2019 as per work order | 2 years and further extendable for 1 year. | Shri K.J. Todarmal, SE (D) | Work is in Progress. |
| 83. | Strengthening of existing Environmental Management Cell at DPT. Appointment of Experts for two year and further extendable for one year. | 1.23 Cr. | 1.20 Cr. | 2.60% below | EG/WK/ 4783/V/131dated 05/02/2021 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15/02/2021 | 24 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in Progress. |
| 84. | Preparing and monitoring of Environmental Management Plan for DPT at Kandla. | 4.08 Cr. | 2.52 Cr. | 38.17% below | EG/WK/EMC/11023/ 2011-IV dated 05/12/2019 | M/s. Detox Corporation Pvt. Ltd. | 16/12/2019 | 15/12/2022 36 months. | Shri B.Rajendra, SE(PL) & EMC (I/C) | Work in progress. |
| 85. | Third Party inspection and quality assurance for the works costing more that Rs. 1.00 Cr. of Civil Engineering Department of DPT. | 1.35 Cr. | -- | -- | -- | -- | -- | -- | Shri Sunil Soren, XEN (D) | LOA issued to M/s VCS quality services Pvt. Ltd. Work order will be issued after BG confirmation |
| 86. | Appointment of Independent Engineer for the work of "Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis. | 1.44 Cr. | 1.18 Cr. | 17.89% below | EG/WK/ 4823/(IE) / 109 dated 22/10/2019 | M/s. Rina Services, s.p.A., Mumbai. | 11/1/2019 | 42 months | Shri K.J. Todarmal, SE (D) | Work Order issued dated 22/10/2019 As Concessionaire has not started the construction activity, the work order issued to M/s. RINA has been kept in abeyance. |
| 87. | Const. of road at SIPC location 2 stage-I (Kandla) for development of SIPC at Kandla - Gandhidham - Adipur complex | 8.09 Cr. | 5.62 Cr. | 30.51%below | CN-I/WK/ 5545/Road location-2/I/05 dated 23/02/2021 | M/s. Dharti Construction, Anjar | 05/04/2021 | 6 months | Shri K.J. Todarmal, SE(C), SIPC | Work in progress. |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No | Name of work & location | Reserve price Per sq. mtr./year | Premium received over and above reserve price during e-auction (per sq. mtr. / per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | e-tender cum e-auction for allotment of Plot No. 8, admeasuring 11,695 sq. m. (including structures) situated to the West of Link Road connecting Old Kandla for the purpose of Construction of Liquid Chemical Storage Installation on 30 years lease basis. | Rs. 1,039.76 per sq. m./ per year | -- | -- | -- | -- | ShriI S.K. Rao, SE (KL) | Pre-Bid meeting is fixed 27/09/2021. Opening of the Price bid is 16/10/2021. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6 .	MARINE DEPARTMENT							                                                                                      AS ON 30.09.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hiring of 04 Nos. of 50/60 tonn Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below Estimated Cost - OSL Ltd. 20.08% below Estimated Cost - KNK Ship | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator | Board vide Resolution No. 56 in its meeting held on 12.08.2016 have approved to award the work to contractors. W.O. has been issued on 03/10/2016 & 22/09/2016. Integrity Pact Agreement signed. |
| 2. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | - |  | M/s.Electronics Corporation of India Ltd., Hyderabad | - | 24 months for supply, installation and commissioning AMC 10 years after installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Integrity Pact Agreement signed. |
| 3. | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | -- | 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 14/12/2020. . Integrity Pact Agreement signed. |
| 4. | Design, Consultation and supply of 2 Nos. of Steel Hull Mooring Launches. | 2.42 Cr. | 1.95 Cr. | 19.25% below | Executed on 28/12/2020 | M/s. A.H. Wadia Boar Builders, Bilimora | -- | 1st Launch in 12 months 2nd Launch in 15 months. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 14/12/2020. Work Order issued on 05/01/2021. Integrity Pact Agreement signed. |
| 5. | Renewal of Steal Plates & painting of various crafts / Tugs of DPT | 2.09 Cr. | 1.80 Cr. | 14.19% below | Executed on 16/06/2021 | M/s. Patel Engineering Works, Gandhidham. | -- | 2 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 21/05/2021. Work Order issued on 13/07/2021. Integrity Pact Agreement signed. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 30.09.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of brand new make and model of 2018 on "monthly hire basis" and made and model not earlier than1st January, 2017 on "as and when required basis" diesel vehicles to DPT for a period of 03 years | 8.86 Cr. | 8.23 Cr. | 4.34% Below | Executed. | M/s. Shree Ganesh Travels, Mumdra | 01/01/2019 | 30/06/2022 | Shri Piyush Parag, Law Officer.. | Work in progress. |
| 2. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	MEDICAL DEPARTMENT										                                            AS ON 30.09.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. | Dr. (Mrs.) K. Gandhi Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	TRAFFIC DEPARTMENT											                	AS ON 30.09.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Engagement of manpower service provider for providing various categories of outsourced staff to carry out railway operation inside Cargo Jetty area for a period of 3 years. | 3.88 Cr. | 2.87 Cr. | 26.00% below | Executed on dated 26/07/2021 | M/s. Dhanjibhai K. Patel, Anjar. | 01/05/2021 | 30/04/2024 | Shri T.D. Maheshwari, ATM (Railway), | Work in progress. |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

9.	FINANCE DEPARTMENT										                                     AS ON 30.09.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |

*****