DEENDAYAL PORT TRUST

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 30.06.2021

| Sr. No. | Name of work and location | Estimated cost (Rs.) in lakh | Tendered Cost (Rs.) in lakh | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 8181.98 | 6359.61 | 18.91 Below | EL/WK/2472/ 480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Commenced on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri Susil Chandra Nahak, Dy. CME | Comprehensive A.M.C. work in progress. |
| 2. | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 15570.46 | 14446.38 9685.90 towards capital cost &4760.48 towards O&M Charges. | 7.22% Below | EL/WK/2491/ 1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri D.K. Hazra, XEN(E) | Work completed on 30/03/2019, Free maintenance period of two years is in progress. |
| 3. | Maintenance Contract of 3 Nos. ELL Wharf Cranes of 25T capacity 4 Rope of M/s. TIL make alongwith Grab inside Cargo Jetty Area for a period of 2 years. | 360.00 | 394.20 | 9.5% above | EL/WK/2594/ 4050 dated 19/11/2020 LOI No. EL/AC/2594(a)/ 4157 | M/s. R.S. Electricals, Gandhidham | 05/11/2020 | 04/11/2022 | Shri Dana Manohar, XEN(M) | Work in progress. |
| 4 | Design, Manufacture, Supply Erection, Testing, Commissioning & Operation of 02 Nos .of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 9181.77 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit (LC) | 08 months from the date of opening of letter of credit (LC) | Shri Dana Manohar, XEN(M) | CAMC work in progress. |
| 5. | Repairs to 30 Mtr High Mast Towers & AMC of Area Lighting at inside Cargo Jetty Area for a period of Two Years. | 350.44 | 312.60 | 10.80% Below | EL/AC/2538/138 dated 01/01/2020 | M/s. C.K. Electricals, Surat | 01/01/2020 | 31/12/2021 | Shri D.K. Hazra, XEN(E) | Work is in progress. |
| 6. | Maintenance Contract of 03 Nos. 25T and 02 Nos. 16T capacity MBE make wharf cranes, along with Grabs for a period of two years at inside Cargo Jetty Area. | 632.40 | 630.00 | 0.38% below | EL/WK/2549(b)/ /516 dated 16/08/2019 | M/s. R. S. Electricals, Gandhidham | 16/08/2019 | 15/08/2021 | Shri Dana Manohar, XEN(M) | Work is in progress. |
| 7. | Annual maintenance Contract of Liebherr make HMC:- LHM 550- S/N:- 141143 & LHM 550-S/N:- 141169 for the period of two year at Berth No. 13 inside Cargo Jetty area. | 484.16 | 312.00 | 35.56% below | EL/WK/2508/671 dated 20/07/2020 | M/s. R. S. Electricals, Gandhidham | 20/07/2020 | 19/07/2022 | Shri Dana Manohar, XEN(M) | Work in Progress. |
| 8. | Improving and reconditioning of 66/11KV Switchyard and 66/11KV Substation – Strengthening of 66/11KV Switchyard & Substation at inside Cargo Jetty Area thereof. | 239.46 | 224.41 | 6.28% Below | EL/WK/2543/412 dated 18/11/2019 | M/s. Onix Structure Pvt. Ltd, Rajkot | 18/11/2019 | 17/07/2020 | Shri D.K. Hazra, XEN(E) | Work is in progress. Proposal for Extension is in process. |
| 9. | Restoration of power supply & Re-Conditioning of Electrical installation at Berth No 13th & 15th at inside Cargo jetty Area. | 259.76 | 186.36 | 28.26% below | EL/WK/2539/268 dated 23/01/2020 | M/s. C.K. Electricals, Surat | 23/01/2020 | 22/09/2020 | Shri D.K. Hazra, XEN(E) | Work in progress. Proposal for extension is in process. |
| 10. | Maintenance Contract for HT & LT Electrical Installations including substations, overhead Lines, Residential, Non-Residential, Hospital and School Buildings outside Cargo Jetty Area. | 398.48 | 357.89 | 10.18% below | EL/WK/2557/383 dated 10/02/2020 | M/s. Sterling & Wilson Ltd | 10/02/2020 | 09/02/2023 | Shri D.K. Hazra, XEN(E) | AMC is in progress. |
| 11. | Operation and Maintenance of 66/11kV and 11/0.433kV Substation inside Cargo Jetty area at DPT, Kandla for a period of two years. | 312.46 | 252.00 | 19.35% below | EL/WK/2626/562 dated 01/07/2020 | M/s. Ascent Electrical Engineers, Jamnagar | 01/07/2020 | 30/06/2022 | Shri D.K. Hazra, XEN(E) | AMC is in progress. |
| 12. | Design, Supply, Installation, Erection, Testing and Commi-ssioning of DC Over Head/UG 11KV line for providing Power Supply to SIPC of DPT at Kandla. | 533.38 | 429.39 | 19.50% | EL/WK/2613/4 dated 05/02/2021 | M/s. Technisis Faridabad | 05/02/2021 | 04/08/2021 | Shri D.K. Hazra, XEN(E) | Work in progress. |
| 13. | Replacement of existing feeder pillar of High Mast & Lattice Towers with FRP Feeder Pillar | 109.59 | 107.97 | 44.99% below | EL/WK/1948/ 1253 dated 26/03/21 | M/s.Rajdeep Electricals Pvt. Ltd, G’dham | 31/03/2021 | 28/07/2021 | Shri Chitrang Vyas, AXEN(E) | Work is in progress. |
| 14. | Supply, Installation, Testing & Commissioning of five numbers 100 M.T. Capacity, Pit-less Type, fully electronic, Road Weighbridges with Five Years Comprehensive Maintenance contract after expiry of two years guarantee Period. | 91.15 | 74.85 | 17.88% below | ML/WK/3942/ 596 dated 16/12/2019 | M/s. Techno Scale Industries, Ahmedabad | 16/12/2019 | 120 days i.e. 13/04/2020 | SE(M) | Board has approved the proposal for outsourcing of weigh bridges and accordingly, the work is not required to be executed. |
| 15. | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weigh bridges (15Kmph speed) of 140Mt capacities including comprehensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 150.79 | 147.67 | (-)2.07% Below | No.ML/WK/3916-II/738 dated 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., E-1, TVK Industrial Estate, Guindy, Chennai - 600032 | 05/01/2019 | 120 days, i.e. 04/05/2019 Further extension granted upto 31/01/2021 | Shri Rajesh Road (EIC) | Materials have been received at site. 2 Nos. of Weigh Bridges have been installed and commissioned. |
| 16. | Comprehensive Annual Maintenance Contract for Port owned five nos. of Pilot Launches, one no. Survey Launch & two nos. of Mooring Launches for a period of two years. | 435.70 | 349.40 | 19.81% below | ML/WK/3992/ 97 dated 28/03/2021 | M/s. SSR Marine Services Pvt. Ltd., Thane. | -- | 24 Months | Shri Rajdev Kumar ME Gr.I | Work order has been issued. |
| 17. | Supply, installation, commissioning, operation and maintenance of 10 Nos. of T RCC Composite Weighbridges on Revenue sharing basis inside custom bound area of DPT for a period of 10 years and buy-back of 15 Nos. Road Weighbridges. | 1392.74 | -- | -- | -- | -- | -- | 10 years | SE(M) | The online Technical bid has been opened on 23/03/2021. The Technical bids are under scrutiny. File sent to Finance for further scrutiny. |
| 18 | Supply, Installation, Testing and Commissioning of remote operated water curtain system, fire alarm, hooter & its accessories at Oil Jetty No. 1, Kandla | 204.77 | -- | -- | -- | -- | -- | 120 days | Shri Dana Manohar, SE(M) | The online technical bids has been opened on 09/04/2021 and the same is under scrutiny. |
| 19. | Development, Operation and Maintenance of Container Terminal at Berth Nos. 11 and 12 at Kandla Port on PPP Mode | 15981.00 | 15981.00 | N.A. | MS/WK/4003-V/357 dated.19/2/2016 | M/s. Kandla International Container Terminal | 29/02/2016 | 15/02/2018 | Shri Susil Chandra Nahak, Dy. CME | LOI issued. Concession Agreement signed on 29/02/2016. Project fully commissioned on 15/02/2018. |
| 20. | Appointment of Consultant for the work of Mechanization of handling of Fertilizers at Kandla Port | 166.67 | N.A | N.A | N.A | N.A | N.A | N.A | Shri Susil Chandra Nahak, Dy. CME | Project mode transferred from EPC to PPP mode. So, the services of existing Transaction Advisor appointed for PPP projects has been rendered. |
| 21. | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commission- ing of the project. | 12094.14 | 12232.53 | 0.9% above | LoA issued vide MS/WK/4025-II/GIM-265 dated 31/03/2017 | M/s. Rishi Shipping, Gandhidham | 31/03/2017 | 31/03/2018 | Shri Rajesh Road, (EIC) | LoA issued on 31/03/2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect. |
| 22. | Mechanization of fertilizer handling facility at Berth No. 14, Deendayal Port | 27709.94 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME | SFC Meeting held on 01/02/2021. Minutes are awaited. |
| 23. | Appointment of Consultant for carrying out environmental impact assessment and environmental management plan studies for development of another ship-repairing facility at Vadinar, to obtain statutory clearances from State authorities & MoEF&CC. | 52.02 | 35.10 | 32.53% Below | LOA No. DD/WK/3050/EC/598 dated 08/12/2020. | M/s. Envision Enviro Technologies Pvt. Ltd., Surat | 08/12/2020 | 07/12/2021 12 Months | Shri Shiva Mudliyar, EIC (DD) | The work has been commenced on 08/12/2020 and inspection report hs been submitted. |
| 24. | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhidham Area for period of three years. | 154.92 | -- | -- | -- | -- | -- | 3 years | E.I.C. (DD) | The online technical bid has been opened on 23/03/2021 and same is under scrutiny. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 30.06.2021

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | -- | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), OOT, Vadinar. | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 2 | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | -- | M/s. Aeromarine Pvt. Ltd., Mumbai | 09/03/2020 | 3 years | Shri Narendra Naik, ME (Gr. I), OOT, Vadinar. | Work Order issued vide No. OOT/ME/WK/RM/8009/1947 dated 03/03/2020. |
| 3. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | 49.32 Cr. | 6.62% below | -- | M/s. Parsh Construction and Foundations Pvt. Ltd., Mumbai | -- | 18 months | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri M.A. Jadav, AXEN(C) | Work Order issued vide No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. |
| 4 | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 | 5.01 % above | -- | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri S.C. Vishwas AE (C) | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. |
| 5. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | 1.06 Cr. | 2.98% above | -- | M/s. Abhay Intelligence & Security Services, Vadodara. | 14/03/2020 | 2 years | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri S.C. Vishwas AE (C) | Work Order issued vide No. OOT/C-WK/RM/4002/2001 dated 12/03/2020 |
| 6. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 | 6.01 % below | -- | M/s. Safari Travels, Balasinor | 07/03/2020 | 3 years | Shri Rajesh Roat, XEN (E&M), OOT, Vadinar Shri Gopal Matha, JE (M) | Work Order issued vide No. OOT/ME/WK/6008/1795 dated 06/02/2020. |
| 7. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | -- | M/s. Pariya Electricals, Vadinar. | -- | 3 years | Shri Rajesh Roat XEN (E&M) OOT, Vadinar | Letter of Acceptance issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2020. |
| 8. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.45 Cr. | 2.83% above | -- | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years | Shri Rajesh Roat XEN (E&M) OOT, Vadinar | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 30.06.2021

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agree ment No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Two years maintenance contract for Non-Residential Building inside Cargo Jetty area (Civil Work). (HD-09/19) | 0.88 Cr. | Part-A 0.58 Part-B 0.01 Neet 0.57 Cr. | 33.33% below | HW/WK/2384/100 dated 13/04/2020 | M/s. Shree Ganesh Construction, Anjar | 24/04/2020 | 24/04/2021 (12 months) | Shri Srinivas Rao, SE (H) | Work completed on 01/06/2021. |
| 2. | Two years maintenance contract for cleaning and sweeping of office building & surrounding outside at New Kandla. | 1.67 Cr. | 0.99 Cr. | 41.11% Below | HW/WK/ 2408 dated 30/07/2019 | M/s. Dhanjibhai K. Patel. | 30/07/2019 | 29/07/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 3. | Annual Maintenance contract of Fender inside cargo jetty area (HD-01/19) | 1.28 Cr. | 1.51 Cr. | 18.35% above | HW/WK/2375 dated 13/12/2019 | M/s. Patel Construction Co. | 13/12/2019 | 12/12/2020 (12 months) | Shri Srinivas Rao, SE (H) | Work in progress. Extension granted upto 23/06/2021. |
| 4. | Annual Maintenance contract for Godown inside cargo jetty area for two years(HD-03/19) | 1.96 Cr. | 1.28 Cr. | 34.44% below | HW/WK/2405/ 338 dated 13/12/2019 | M/s. Mepabhai Mandan & Co. | 13/12/2019 | 12/12/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. Anticipated variation 28% approved by the competent authority.. |
| 5. | Maintenance contract for quay and transit area inside cargo jetty area for two years (05/19) | 1.14 Cr. | 0.99 Cr. | 13.00% below | HW/WK/2402 -II/236 dated 19/09/2019 | M/s. Mahesh Construction, Adipur. | 18/09/2019 | 17/09/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 6. | Tree plantation near offices other buildings along roads etc. including two years maintenance contract at New Kandla (HD-06/19) | 0.96 Cr. | 0.72 Cr. | 25.06% | HW/WK/ 2380-I/99 dated 13/04/2020 | M/s. Dhanji K Patel, Anjar | 24/04/2020 | 23/04/2022 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 7. | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla (HD-07/19). | 1.12 Cr. | 1.20 Cr. | 7.21% above | HW/WK/2379-III /332 dated 05/12/2019 | M/s. Patel Construction Co. | 18/12/2019 | 17/12/2020 (12 months) | Shri Srinivas Rao, SE (H) | Work in progress. Extension granted upto 17/12/2021. |
| 8. | Housekeeping and cleaning of office building inside Cargo Jetty Area for 2 years (HD-10/19). | 0.54 Cr. | 0.41 Cr. | 23.43% below | HW/WK/ 2422-I/367 dated 20/02/2021 | M/s. Shree Ganesh Construction, Anjar. | 06/03/2021 | 05/03/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 9. | Two years maintenance contract for office building outside Port area (Civil Work) HD-02/19 | 0.89 Cr. | 0.64 Cr. | 27.27% below | HW/WK/ 2336-I/339 dated 13/12/2019 | M/s. Mohit Construction | 13/12/2019 | 12/12/2021 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 10. | Improving the fendering arrangement inside cargo jetty area HD-14/19. | 2.85 Cr. | 3.54 Cr. | 24.39% above | HW/WK/ 2392/137 dated 02/06/2020 | M/s. Patel Construction Co., Gandhidham. | 15/06/2020 | 14/06/2021 12 months | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 14/12/2021 is processed for approval. |
| 11. | Development of equipment to remove cargo / solid waste periodically from road to maintain high standard of hygienic and to avoid pollution and contamination of cargo in Port area HD-15/19. | 1.34 Cr. | 0.64 Cr. | 52.31% below | HW/WK/ 2413-I/167 dated 23/07/2020 | M/s. Patel Construction Co., Gandhidham. | 28/07/2020 | 27/07/2021 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 12. | Improving the road network inside cargo jetty area. Providing Asphalt paving (Stage-II) HD-16/19 | 7.34 Cr. | 5.78Cr. | 21.20% Below | HW/WK/ 2308-I/142 dated 04/06/2020 | M/s. Ravji Manji Soratia & Co. | 19/06/2020 | 18/06/2021 (12 months) | Shri Srinivas Rao, SE (H) | Work completed on 18/06/2021. |
| 13. | Development of equipment for cleaning of all toilet block inside Orit area to maintain high standard of hygienic and to avoid pollution . (HD-20/19) | 1.88 Cr. | 1.16 Cr. | 38.04% below | HW/WK/ 2428/104 dated 21/04/2020 | M/s. Patel Construction Co., Gandhidham. | 04/05/2020 | 03/05/2022 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 14. | Providing toilet block and drinking water facility in 66,40, 34 H area and on Berth No.13 & 15 in CJA under Swachh Bharat Abhiyan. | 2.03 Cr. | 1.55 Cr. | 23.38% below | HW/WK/ 2447/268 dated 28/10/2020 | M/s. Quality Constructions, Gandhidham. | 01/11/2020 | 9 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 15. | AMC of Custom fencing wall and gates of Cargo Jetty and Bunder area. | 0.74 Cr. | 0.48 Cr. | 35.20% below | HW/WK/ 2420/320 dated 25/01/2021 | M/s. Sanjay K. Sorathiya & Co. | 05/02/2021 | 04/02/2022 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 16. | Upgrading the road network of 66 hectare. | 17.42 Cr. | 12.73 Cr. | 28.95% Below | HW/WK/ 2476/239 dated 09/09/2020 | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd., Gandhidham. | 23/09/2020 | 22/09/2021 (12 months) | Shri Srinivas Rao, SE (H) | Work in progress. Anticipated variation 7.40% approved by competent authority. |
| 17. | Maintenance contract for roads and RCC culverts inside CJA at New Kandla for 2 years. | 1.75 Cr. | 1.84 Cr. | 5.74% above | HW/WK/ 2443/401 dated 31/03/2021 | M/s. Shree Ganesh Construction | 16/04/2021 | 15/04/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 18. | Two years contract for cleaning of storm water drain inside Cargo Jetty area. | 0.80 Cr. | 0.42 Cr. | 47.81% below | HW/WK/ 2441/180(A)dated 10/07/2020 | M/s. Narayan Construction | 29/07/2020 | 28/07/2022 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 19. | Development of plots, roads & SWD in 34 Ha area inside Cargo Jetty Area. | 57.08 Cr. | 36.60 Cr. | 35.89% below | HW/WK/ 2486/363 dated 20/02/2021 | M/s. Bhimji Velji Soratia Construction P. Ltd. | 06/03/2021 | 05/03/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 20. | Providing Screen wall surrounding the coal stacking yard inside Cargo Jetty Area of DPT | 18.63 Cr. | 14.97 Cr. | 19.63% below | HW/WK/2486 363 dated 20/02/2021 | M/s. Mohandas V. Rajani. | NA | NA | Shri Srinivas Rao, SE (H) | Commencement of work on or before 15/08/2021 with the approval of competent authority. |
| 21. | Construction of 3 Nos. Toilet Blocks on Central Road inside cargo jetty area at New Kandla (HD-12/20) | 1.40 Cr. | 1.18 Cr. | 14.39% below | HW/WK/2477/299 dated 15/12/2020 | M/s. Dharam Construction Co. | 28/12/2020 | 27/11/2021 11 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 22. | Development of Parking yards for trucks/vehicles for pre checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 Cr. | 14.59 Cr. | 12.87% below | HW/WK/2446/436 dated 25/06/2021 | M/s. Indian Construction Co., | 08/07/2021 | 07/07/2023 24 months | Shri Srinivas Rao, SE (H) | Work Order issued. |
| 23. | Upgradation of Plots, Roads &SWD behind Berth No. 7 to 10 inside Cargo Jetty area. | 8.20 Cr. | 5.56 Cr. | 32.08% below | N.A. | M/s. Krishna Construction | N.A. | N.A. | Shri Srinivas Rao, SE (H) | LOA issued on 15/02/2021. |
| 24. | Construction of Dome Shaped Storage Sheds inside cargo jetty area – Phase-I | 46.53 Cr. | 35.93 Cr. | 22.78% below | HW/WK/2475/456 dated 16/06/2021 | M/s. Patel Construction Co., Gandhidham. | 30/06/2021 | 29/06/2021 12 months | Shri Srinivas Rao, SE (H) | Work Order issued. |
| 25. | Development of Land in the West of Existing 66 hectare area for storage of cargo (Extension of custom bonded area) | 42.81 Cr. | 33.38 Cr. | 22.02% below | HW/WK/ 2457/355 dated 17/02/2021 | M/s. Kalthia Engineering Construction Ltd. | 02/03/2021 | 01/03/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 26. | Construction of watch tower inside cargo jetty area | 3.04 Cr. | 2.84 Cr. | 6.22% below | HW/WK/ 2470/407 dated 09/04/2021. | M/s. Viyuha Infrabuild | 23/04/2021 | 8 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 27. | Two years contract for supply and maintenance of railway tracks inside and outside Cargo Jetty Area for 2 years | 2.59 Cr. | 2.03 Cr. | 21.40% below | HW/WK/ 2487/359 dated 20/02/2021. | M/s. Laxyo Entergy Ltd. | 06/03/2021 | 05/03/2023 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 28. | R/M of Maintenance Jetty - Repairs and Maintenance of Pontoons and Walkways of SNA Jetty and Flotila Jetty | 2.77 Cr. | 3.37 Cr. | 10.57% above | HW/WK/ 2949/462 dated 25/06/2021. | M/s. Patel Construction, Gandhidham | 08/07/2021 | 07/07/2021 24 months | Shri Srinivas Rao, SE (H) | Work Order issued on 25/06/2021 |
| 29. | Two years maintenance contract for railway track leading to Tuna from 0 to 11 Km KPT line (Take off point at 2.573 Km at GIM Yard to 13.54 Km) including LC-1, LC-2 | 1.19 Cr. | 0.908 Cr. | 23.77% below | HW/WK/2515/432 dated 31/05/2021 | M/s. Patel Construction, Gandhidham. | 14/06/2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 30. | Maintenance contract for quay and transit area inside cargo jetty area for two years | 1.04 Cr. | 0.86 Cr. | 16.17% Below | N.A. | M/s. Sanjay Soratia, Anjar. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Price Bid opened on 30/06/2021. |
| 31. | Providing Labour Amenities Centre at various location inside Cargo Jetty Area. | 1.53 Cr. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Tender discharged. |
| 32. | Improving / Upgradation of Custom Fencing Wall of Cargo Jetty and Bunder Area | 7.68 Cr. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Preliminary and Technical bid opened on 29/06/2021. |
| 33. | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 Cr. | 2.43 Cr. | 35.73% Below | HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd., Gurgaon - 122015 Haryana- India |  | 36 months | Shri Srinivas Rao, SE (H&D) | Work in progress. |
| 34. | Appointment of Project Management Consultant (PMC) for capital & maintenance dredging work of DPT from firms / consortiums empanelled consultants from dredging work (Class-A, Category-A) by Indian Ports Association, New Delhi. | 6.36 Cr. | 5.33 Cr. | 15.32% below | LOA No. EG/WK/6112 /333 dated 15/11/2019 | M/s. AECOM India Pvt. Ltd., Gurgaon | 25/11/2019 | 36 months | M/s. AECOM India Pvt. Ltd., Haryana. Shri Srinivas Rao, SE (H&D) | Work in progress. |
| 35. | Dredging in the Navigational Channel and alongside Cargo Berth / Oil Jetties at Deendayal Port Trust for the year 2020-23. Location at Kandla. | 393.00 Cr | 310.04 Cr. | 21.27% below | LOA No. EG/WK/6116/ 182 dated 10/03/2021 | M/s. Adani Port and Special Economic Zone Ltd., Ahmedabad. | -- | 36 months | M/s. AECOM India Pvt. Ltd., Haryana. Shri Srinivas Rao, SE (H&D) | Work in progress. |
| 36. | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years. | 0.94 Cr. | 0.66 Cr. | 30.51% below | PL/WK/8358/1522 dated 20/11/2019. | M/s. Premji Kanji Sorathia | 20/11/2019 | 19/11/2021 (24 months) | Shri Rajendra Prasad SE (PL) | Work in progress. |
| 37. | Strengthening of RCC custom fencing wall of Oil Jetty and Providing CCTV lighting arrangement at Old Kandla - Strengthening of RCC Custom Fencing Wall. | 1.12 Cr. Credit part 0.21 Cr. | Part-A 0.76 Cr. Part-B 0.01 Cr. | 31.29% below | PL/WK/8420-I/2652 dated 14/10/2019. | M/s. Rajput Infrastructure Company, Gandhidham. | 27/06/2021 | 8 months | Shri Rajendra Prasad SE (PL) | Work in progress. |
| 38. | Annual Maintenance Contract for the Buildings, Walkway, trestles, Fire Fighting, Pipelines, Garden inside and outside Oil Jetty area at Old Kandla | 1.29 Cr. Credit part 0.50 Cr. | Part-A 1.26 Cr. Part-B 0.04 Cr | 9.48% above | PL/WK/8316-II/125/A dated 12/02/2020 | M/s. Mahesh Construction, Adipur | 14/02/2022 | 12 months | Shri Rajendra Prasad SE (PL) | Work in progress. |
| 39. | Improving Storm Water drainage system at Old Kandla. | 2.32 Cr. | -- | -- | --- | -- | -- | -- | Shri Rajendra Prasad SE (PL) | TCM prepared after Price bid opening. |
| 40. | Providing RCC drinking water tank. | 1.52 Cr. | -- | -- | --- | -- | -- | -- | Shri Rajendra Prasad SE (PL) | Re-Revised Pre-Audit is being submitted. |
| 41. | Improving existing Oil Jetty structures at Oil Jetty No. 1, 2, 4 | 8.20 Cr. | 8.08 Cr. | 1.55% below | Pl/WK/8421-I/2238 dated 10/06/2020 | M/s. Sarjan Construction Pvt. Ltd. | 20/06/2020 | 18 months | Shri Rajendra Prasad SE (PL) | Work in progress. |
| 42. | Maintenance Contract for cleaning of SWD along road sides for 2 years (J.N. road, link road, bye pass road & O/s CJA) at New Port Colony New Kandla (18-20) | 0.55 Cr. | 0.32 Cr. | 41.90% Below | RW/WK/7767-I/ dated 10/10/2019 | M/s. Vihat Const. Co., Adipur | 21/10/2019 | 20/10/2021 | Shri Srinivas Rao, SE (R) | Work in progress. |
| 43. | Maintenance Contract for Sanitation of New Port Colony New Kandla for year 19-20. | 0.98 Cr. | 0.66 Cr. | 32.40% below | RW/WK/7784-I/45 dated 26/08/2019 | M/s. Vihat Const. Co., G'dham | 02/09/2019 | 01/09/2021 | Shri Srinivas Rao, SE (R) | Work in progress |
| 44. | Resurfacing of existing road from NH Junction to Bye pass - KK Road Junction. | 8.19 Cr. | 5.91 Cr. | 27.78% below | RW/WK/7777-I/616 dated 18/12/2020 | M/s. Mepabhai Mandan & Co., Adipur | 28/12/2020 | 27/09/2021 | Shri Srinivas Rao, SE (R) | Work in progress. |
| 45. | Maintenance Contract for Residential & Non-Residential Building at Port Colony, New Kandla for 2 years. | 1.59 Cr. | 1.06 Cr. | 33.30% below | RW/WK/7790-I/509 dated 01/09/2020 | M/s. Rajput Infrastructure Co., Gandhidham. | 02/09/2020 | 01/09/2022 | Shri Srinivas Rao, SE (R) | Work in progress |
| 46. | Resurfacing of roads from WG-II to WG-III | 4.90 Cr. | 3.12 Cr. | 36.30% below | RW/WK/7793-I/47 dated 19/01/2021 | M/s. Krishna Construction | 20/01/2021 | 19/07/2021 | Shri Srinivas Rao, SE (R) | Work in progress. |
| 47. | R/M of CISF Complex at New Kandla - Repairs to Toilet block at CISF Complex, New Kandla. | 0.50 Cr. | 0.45 Cr. | 11.01% below | RW/WK/7782-I/81 dated 16/02/2021 | M/s. Pars Enterprise, Gandhidham | 21/02/2021 | 20/08/2021 | Shri Srinivas Rao, SE (R) | Work in progress. |
| 48. | Resurfacing over roads inside New Port colony at Kandla | 1.57 Cr. | 0.999 Cr. | 36.15% below | RW/WK/ 7791-I/119 dated 17/03/2021 | M/s. Krishna Construction | 17/03/2021 | 16/09/2021 | Shri Srinivas Rao, SE (R) | Work in progress. |
| 49. | Resurfacing of Tuna Road | 3.90 Cr. | 2.63 Cr. | 32.56% below | RW/WK/ 7762-I/198 dated 23/03/2021 | M/s. Mepabhal Mandan & Co., Adipur | 01/04/2021 | 30/09/2021 | Shri Srinivas Rao, SE (R) | Work in progress. |
| 50. | Up-gradation of service road leading to west gate-I from zero point at Kandla | 3.83 Cr. | 2.68 Cr. | 30.16% below | RW/WK/ 7800-I/178 dated 01/06/2021 | M/s. Mepabhal Mandan & Co., Adipur | 01/06/2021 | 30/11/2021 | Shri Srinivas Rao, SE (R) | Pre-Acceptance issued. |
| 51. | Dismantling of Residential and Non - Residential buildings at New Kandla | 0.96 Cr. | - | - | - | - | - | - | Shri Srinivas Rao, SE (R) | TC Note for Technical Bid submitted. |
| 52. | Construction of Dr. Babsheb Ambedker Convention Centre, Gandhidham. | 33.08 Cr. | 28.83 Cr. | 12.84% below | TW/WK/ 7715-I/410 dated 07/02/2019 | M/s. Dipesh Construction Co., Anjar | 15/02/2019 | 14/02/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. Applied for extension. |
| 53. | Annual Maintenance Contract for Gardens at Shaktinagar & A.O Building for the period of 2 years | 0.61 Cr. | 0.41 Cr. | 34.51% below | TW/WK/ 7734-/174 dated 02/11/2019 | M/s. Praful A. Parmar | 01/08/2019 | 31/07/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 54. | Modernization of AO Building at Gandhidham Stage -II | 1.26 Cr. | 0.89 Cr. | 29.60% below | TW/WK 7717-I/345 dated 20/05/2020 | M/s. Pars Enterprise, Gandhidham. | 06/03/2020 | 06/02/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 55. | Annual Maintenance Contract for Sport Complex at Gopalpuri for the period of 2 years. | 0.65 Cr. | 0.42 Cr. | 35.35% | TW/WK 7764-I/371 dated 14/04/2020 | M/s. Patel Construction Co. | 16/04/2020 | 15/04/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 56. | Annual Maintenance Contract for Residential Building of Port Colony, Gopalpuri and AO Building at Gandhidham. | 1.15 Cr. | 0.68 Cr. | 40.95% below | TW/WK 7773/342 dated 13/03/2020 | M/s. Rajput Infrastructure, Gandhidham. | 13/03/2020 | 12/03/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 57. | AMC for Whitewashing, Distempering & Painting to Resi. & NRB at Gopalpuri. KDLB, Gandhidham & Adipur for the year 2019-20. (Re-invited) | 1.98 Cr. | 0.93 Cr. | 52.80% below | TW/WK 7760-I/88 dated 11/02/2021 | M/s. Mepabhai Mandan & Co. | 11/02/2021 | 10/02/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 58. | Maintenance of Public Health & Underground drainage at Gopalpuri Port Colony & KDLB Colony for the period of 2 years. | 2.52 Cr. | 1.33 Cr. | 47.12% below | TW/WK 7757-I/229 dated 05/12/2019 | M/s. Patel Cons. Co., Gandhidham. | 09/12/2019 | 08/12/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 59. | Providing interlocking paving on both sides shoulders of roads of Gopalpuri | 1.45 Cr. | 0.76 Cr. | 48.19% below | TW/WK 7754-I/64 dated 01/02/2021 | M/s. Narayan Construction Co. | 03/02/2021 | 02/08/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 60. | Providing safely measures - providing compound wall and SWD in Gopalpuri Colony, Gandhidham. | 2.19 Cr. | 1.30 Cr. | 38.73% below | TW/WK/7779-I/654 dated 02/11/2020 | M/s. Ankita Const. | 03/11/2020 | 02/11/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 61. | Modernization of Staff Club / Officer's Club at Gopalpuri | 2.15 Cr. | 1.82 Cr. | 15.57% below | TW/WK/7781-I/621 dated 14/10/2020 | M/s. Dhanjibhai K. Patel, Anjar. | 14/10/2020 | 13/10/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 62. | R/M of Arboriculture / Horticulture work in public building at Gopalpuri and KDLB Colony for the year 2020-22. | 2.19 Cr. | 1.15 Cr. | 47.36% below | TW/WK/7781-I/621 dated 14/10/2020 | M/s. Rajut Infrastructure, Gandhidham | 15/10/2020 | 14/10/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress |
| 63. | Strengthening of Sewage, Drainage, SWD, Culvert network at Gopalpuri, KDLB Colony | 2.98 Cr. | 1.45 Cr. | 51.18% below | TW/WK/7787-I/248 dated 21/04/2021 | M/s. Sterling Infrastructure Co. | 22/04/2021 | 21/04/2022 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 64. | AMC for cleaning & House Keeping works of DTP Hospital and Isolation Ward at Gopalpuri and Kandla (For Two Years). | 1.62 Cr. | 0.85 Cr. | 47.70% below | TW/WK/7798 dated 30/01/2021 | M/s. Patel Construction Co., Gandhidham. | 10/02/2021 | 09/02/2023 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 65. | Strengthening of Multi storey building with micro concreting, plinth protection at Gopalpuri | 6.61 cr. | 4.26 Cr. | 35.41% below | TW/WK/7794-I/ dated 26/03/2021 | M/s. Mohandas V. Rajani, Adipur | 01/04/2021 | 30/09/2022 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 66. | AMC for AO building at Gandhidham | 0.71 Cr. | 0.45 Cr. | 36.36% below | TW/WK/7799-I/110 dated 01/03/2021 | M/s. Rajput Infrastructure Co., Gandhidham. | 02/03/2021 | 01/03/2022 | Shri K. J. Todermal, SE(C ) | Work in progress. |
| 67. | Providing power supply arrangement for air conditioner units installed at AO Building, Gandhidham. | 0.62 Cr. | 0.61 Cr. | 21.21% below | TW/WK/7796-I/247 dated 21/04/2021 | M/s. Mepabhai Manda & Co. | 22/04/2021 | 21/03/2022 | Shri K. J. Todermal, SE(C ) | Work in progress. |
| 68. | S/R to Quarters to Gopalpuri-Replacement of slabs, water proofing chajjas, walls etc. | 6.56 Cr. | 4.78 Cr. & 4.66 Cr. (Credit) | 27.26% below | TW/WK/7783/274 dated 24/05/2021 | M/s. Dhanjibhai K. Patel, Anjar | 24/05/2021 | 23/05/2022 | Shri M.T. Gohil XEN(TD) | Work in progress. |
| 69. | Construction of A,B, C and D type quarters at Gopalpuri. | 18.94 Cr. | 13.78 Cr. | 27.18% below | TW/WK/7785/299 dated 02/06/2021 | M/s. VC Project & Infra Pvt. Ltd. | 05/06/2021 | 04/06/2023 | Shri M.T. Gohil XEN(TD) | Work Order issued. |
| 70. | Improving & up-gradation of gardens and land scalping at Gopalpuri (Renovation of Nehru park and rain water harvesting by strengthening of SWD network near recharging pond at Gopalpuri. | 4.79 Cr. | - | - | - | - | - | - | Shri M.T. Gohil XEN(TD) | Technical Bid opened on 25/03/2021 |
| 71. | Construction of compound wall on vacant plots of Gandhidham Township - Removal / Prevention of Encroachment - Stage-II | 4.06 Cr. | - | - | - | - | - | - | Shri M.T. Gohil XEN(TD) | Technical Bid opened on 11/05/2021. |
| 72. | S/R to NOn-Residential Building - Providing water proofing to terrace and interior wall of AO Building. | 0.67 Cr. | - | - | - | - | - | - | Shri M.T. Gohil XEN(TD) | Technical Bid opened on 23/06/2021. |
| 73. | Construction of 14th & 16th Berth for Multi Purpose Cargo - Additional Piled Platform. | 83.05 Cr. | 64.03 Cr. | 22.89% below | CN/WK/ 2243 & 44-III/95(G) dated 06/06/2020 | M/s. Vijay Mistry Construction Pvt. Ltd., Ahmedabad. | 22/06/2020 | 11 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 74. | Retrofitting of existing Cargo Berth No. 7 (Panel 51 to 59) | 65.05 Cr. | 49.57 Cr. | 23.79% below | CN/WK/ 2273-IV/ Works/108 (G) dated 31/07/2020 | M/s. BMS-Marymatha JV., Surat. | 14/08/2020 | 11 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 75. | Upgradation and strengthening of existing road from WG 2 to 16th Cargo Berth - Phase -I. | 69.18 Cr. | 41.50 Cr. | 40.02% below | CN-I/WK/2259/Works/92 dated 01/03/2021 | M/s. M.K.C. Infrastructure, Anjar. | 09/03/2021 | 11 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 76. | Construction of SWD and Cable Trench at backup of Beth No 11 & 12 | 4.70 Cr. | 3.15 Cr. | 33.05% below | EG/WK/8112/225 dated 21/04/2021 | M/s. Dharti Construction Pvt. Ltd., Mumbai | 12/05/2021 | 10 months | Shri K. Srinivasa Rao, S.E. (C-I) | Work in progress. |
| 77. | Construction of Oil Jetty No.7 at Kandla | 44.59 Cr. | 42.40 Cr. | 4.93% below | CN-I/WK/ 1553/81 dated 26/10/2015 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | 26/02/2020 | 25/08/2022 18 months | Shri Rajendra Prasad SE (P) | Work in progress. |
| 78. | Construction of Oil Jetty No.8 at Old Kandla | 105.51 Cr. | 99.08 Cr. | 6.09% Below | CN-I/WK/ 15571/work/243 dated 03/02/2021 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | 04/02/2021 | 18 months | Shri Rajendra Prasad SE (P) | Work in progress. |
| 79. | Augmentation of Liquid Cargo handling capacity by revamping of existing pipeline network at Oil Jetty area, DPT, Kandla. | 130.49 Cr. | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad SE (P) | The preliminary bid opened and under scrutiny. |
| 80. | Providing Legal, Technical and Financial transactions for all ongoing and future proposals of DPT on PPP / Captive Mode for the period of two years and further extendable for one year. | 3.27 Cr. | 1.98 Cr. | 39.25% below | EG/WK/ 4759/TA/79 dated 10/10/2019 | M/s. Infrastructure Development (Karnataka) Corpn. Ltd. (1deck) | 14/10/2019 as per work order | 2 years and further extendable for 1 year. | Shri Srinivas Rao, SE (D) | Work in progress. |
| 81. | Strengthening of existing Environmental Management Cell at DPT. Appointment of Experts for two year and further extendable for one year. | 1.23 Cr. | 1.20 Cr. | 2.60% below | EG/WK/ 4783/V/131dated 05/02/2021 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15/02/2021 | 24 months | Shri Srinivas Rao, SE (D) | Work in progress. |
| 82. | Preparing and monitoring of Environmental Management Plan for DPT at Kandla. | 4.08 Cr. | 2.52 Cr. | 38.17% below | EG/WK/EMC/11023/ 2011-IV dated 05/12/2019 | M/s. Detox Corporation Pvt. Ltd. | 16/12/2019 | 15/12/2022 36 months. | Shri Srinivas Rao, SE (D) | Work in progress. |
| 83. | Third Party inspection and quality assurance for the works costing more that Rs. 1.00 Cr. of Civil Engineering Department of DPT. | 1.35 Cr. | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad, SE (D) | After approval of Pre-Audit Report, Tender Committee meeting was held on 16/06/2021 and approval of pre-qualification of bidders is under process. |
| 84. | Appointment of Independent Engineer for the work of "Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis. | 1.44 Cr. | 1.18 Cr. | 17.89% below | EG/WK/ 4823/(IE) / 109 dated 22/10/2019 | M/s. Rina Services, s.p.A., Mumbai. | 01/11/2019 | 42 months | Shri Srinivas Rao, SE (D) | Work in progress. |
| 85. | Const. of road at SIPC location 2 stage-I (Kandla) for development of SIPC at Kandla - Gandhidham - Adipur complex | 8.09 Cr. | 5.62 Cr. | 30.51%below | CN-I/WK/ 5545/Road location-2/I/05 dated 23/02/2021 | M/s. Dharti Construction, Anjar | 05/04/2021 | 6 months | Shri K.J. Todarmal, SE(C), SIPC | Work in progress. |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No | Name of work & location | Reserve price Per sq. mtr./year | Premium received over and above reserve price during e-auction (per sq. mtr. / per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | e-tender cum e-auction for allotment of Plot No. 8, admeasuring 11,695 sq. m. (including structures) situated to the West of Link Road connecting Old Kandla for the purpose of Construction of Liquid Chemical Storage Installation on 30 years lease basis. | Rs. 1,039.76 per sq. m./ per year | -- | -- | -- | -- | ShriI S.K. Rao, SE (KL) | Technical bids opened on 25/05/2021. Legal opinion is sought from the Law Officer for common directorship / shareholders. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6 .	MARINE DEPARTMENT							                                                                                      AS ON 30.06.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hiring of 04 Nos. of 50/60 tonn Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below Estimated Cost - OSL Ltd. 20.08% below Estimated Cost - KNK Ship | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator Shri Sunilkumar, Flotilla Supdt. | Board vide Resolution No. 56 in its meeting held on 12.08.2016 have approved to award the work to contractors. W.O. has been issued on 03/10/2016 & 22/09/2016. Integrity Pact Agreement signed. |
| 2. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | -- | Executed on 07/01/2021 | M/s.Electronics Corporation of India Ltd., Hyderabad | 20/02/2020 | 24 months for supply & installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Integrity Pact Agreement signed. |
| 3. | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | -- | 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 14/12/2020. Work Order issued on 05/01/2021. Integrity Pact Agreement signed. |
| 4. | Design, Consultation and supply of 2 Nos. of Steel Hull Mooring Launches. | 2.42 Cr. | 1.95 Cr. | 19.25% below | Executed on 28/12/2020 | M/s. A.H. Wadia Boar Builders, Bilimora | -- | 1st Launch in 12 months 2nd Launch in 15 months. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 14/12/2020. Work Order issued on 05/01/2021. Integrity Pact Agreement signed. |
| 5. | Renewal of Steal Plates & painting of various crafts / Tugs of DPT | 2.08 Cr. | 1.80 Cr. | 14.19% below | Executed on 16/06/2021 | M/s. Patel Engineering Works, Gandhidham. | -- | 2 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 21/05/2021. Integrity Pact Agreement signed. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 30.06.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of brand new make and model of 2018 on "monthly hire basis" and made and model not earlier than1st January, 2017 on "as and when required basis" diesel vehicles to DPT for a period of 03 years | 8.86 Cr. | 8.23 Cr. | 4.34% Below | Executed. | M/s. Shree Ganesh Travels, Mumdra | 01/01/2019 | 30/06/2022 | Shri Piyush Parag, Law Officer.. | Work in progress. |
| 2. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	MEDICAL DEPARTMENT										                                            AS ON 30.06.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. | Dr. (Mrs.) K. Gandhi Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	TRAFFIC DEPARTMENT											                	AS ON 30.06.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N I L |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

9.	FINANCE DEPARTMENT										                                     AS ON 30.06.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |

*****