## Sep-22
HARBOUR DIVISION
Statement showing the details of Bills of various parties and its payment status for the month of September - 2022
Sr. No. | Nature of Work | Name of firm | GSTIN | Address with Pin | Phone / Mobile No. & Email | Amount (Rs.) | Bill No. & Date | Date of Receipt | Date of forward | Time taken by Division (Days) | Date of payment | Time taken by Accounts (Days) | Total Time (Days) | Reasons for delay, if any
1 | Providing Aluminium partition at 66 Kv Electric Substation inside cargo jetty area. | M/s. Shiv Infracon, Plot No. S.A.X. - 125, Adipur - Kutch | 24ABNFM8895M1Z7 | M/s. Shiv Infracon, Plot No. S.A.X. - 125, Adipur - Kutch | shivinfracom@gmail.com | 419232 | 1st & Final Bill | 01.09.2022 | 01.09.2022 | 1 day
2 | Development of Land in the West of Existing 66 hectare area for storage of cargo (Extension of custom bonded area) | M/s. Kalthia Engineering & Construction Limited, Ahmedabad | 24AAACK8944N1Z2 | Kalthia Group, Shivdham Farm, 744, Makraba Gam, S.G. Highway, B/h Karnavati Club, Ahmedabad | piyush@kalthiagroup.com | 17213874 | 16th RA Bill | 01.09.2022 | 01.09.2022 | 1 day
3 | Development of Plots, Roads & SWD in 34 hectare area inside C J area. | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd, Plot No.112-113, Arbuda Nagar, Survey No.10/2 & 10/3, Village Antarjal, Adipur (Kutch) 370205 | 24AAFCB4960Q1Z8 | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd, Plot No.112-113, Arbuda Nagar, Survey No.10/2 & 10/3, Village Antarjal, Adipur (Kutch) 370205 | ravji@bvscpl.in | 27138428 | 16th RA Bill | 04.09.2022 | 05.09.2022 | 2 days
4 | Construction of Dome Shaped Storage Sheds Inside Cargo Jetty Area (Phase-I) | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | 24ADEPK3468M1ZA | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | pcc@neelkanth.co.in | 42169544 | 8th RA Bill | 04.09.2022 | 07.09.2022 | 3 days
5 | Deployment of equipment for cleaning of all toilet block inside port area to maintain high standard of hygienic and to avoid pollution. | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | 24ADEPK3468M1ZA | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | pcc@neelkanth.co.in | 1627370 | 12th RA Bill | 07.09.2022 | 08.09.2022 | 2 days
6 | Construction of RCC Floor on surface of dismentled Godown no 3 & 4 inside cargo jetty area. | M/s. Ankita Construction, Office No.01, 3rd Floor, Vraj Arcade, Near Vraj Residency, Adipur | 24ABAFA5529R1Z5 | M/s. Ankita Construction, Office No.01, 3rd Floor, Vraj Arcade, Near Vraj Residency, Adipur | ankitacostruction75@gmail.com | 5327670 | 1st RA Bill | 12.09.2022 | 12.09.2022 | 1 day
7 | House Keeping & Cleaning of office building inside cargo jetty area. (For 2 Years) | M/s. Shree Ganesh Construction, 11, Ganshyam Nagar, Near Sawasar Gate, Anjar | 24ACVFS6459E2ZJ | M/s. Shree Ganesh Construction, 11, Ganshyam Nagar, Near Sawasar Gate, Anjar | sgc.anjar05@gmail.com | 1409000 | 3rd RA Bill | 16.09.2022 | 20.09.2022 | 4 days
8 | Two Years Contract for supply and maintenance of railway tracks inside and outside cargo jetty area (For Years 2020-22). | M/s. Laxyo Energy Ltd., Laxyo Tower,46/1, T.I.T. Road, Ratlam (M.P) | 23AABCL3031E1Z9 | M/s. Laxyo Energy Ltd., Laxyo Tower,46/1, T.I.T. Road, Ratlam (M.P) | info@laxyo.com | 4561377 | 3rd RA Bill | 23.09.2022 | 23.09.2022 | 1 day