DEENDAYAL PORT TRUST

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 31.12.2021

| Sr. No. | Name of work and location | Estimated cost (Rs.) in lakh | Tendered Cost (Rs.) in lakh | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Mechanization of fertilizer handling facility at Berth No. 14, Deendayal Port | 30028.00 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME, | As per direction of Ministry, New MCA is to incorporated in the project under beading stage also. Accordingly, previously unproved DCA changed as per MCA. The revise DCA is approved by competent authority. RFP issued on dated 24.12.2021. Due date of submission of bid 08/02/2022& Security clearance of applicants has been send to ministry for approval please. |
| 2 | Development, Operation and Maintenance of Container Terminal at Berth Nos. 11 and 12 at Kandla Port on PPP Mode | 15981.00 | 15981.00 | N.A. | MS/WK/4003-V/357 dtd.19/2/2016 | M/s. Kandla International Container Terminal | 29-02-2016 | 15-02-2018 | Shri Susil Chandra Nahak, Dy. CME, | LOI issued. Concession Agreement signed on 29/02/2016. Project fully commissioned on 15.02.2018. |
| 3 | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 15570.46 | 14446.38 9685.90 towards capital cost &4760.48 towards O&M Charges. | 7.22% Below | EL/WK/2491/1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30.03.2019 CAMC work commenced on 30.03.2019 Scheduled date of Completion is 29.03.2039 | Shri D.K.Hazra, XEN (E) | Comprehensive A.M.C. work in progress. |
| 4 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 12094.14 | 12232.53 | 0.9% above the estimated cost | LoA issued vide MS/WK/4025-II/GIM-265 dtd. 31.03.2017 | M/s. RISHI Shipping, Gandhidham | 31/03/2017 | 31-03-2018 | Shri Rajesh Roat, (EIC) | LoA issued on 31.03.2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect. |
| 5 | Design, Manufacture, Supply Erection, Testing, Commissioning &Operation of 02 Nos .of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 9181.77 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 Cr. (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit(LC) | 08 months from the date of opening of letter of credit (LC) | Shri Dana Manohar, XEN(M),DPT | CAMC work in progress. |
| 6 | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 8181.98 | 6359.61 | 18.91 Below | EL/WK/2472/480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Comm’ned on 29.03.2017 CAMC work commenced on 27.05.2017 Scheduled date of Completion is 26.05.2037 | Shri D.K. Hazra, XEN(E) | Comprehensive A.M.C. work in progress. |
| 7 | Revamping and upgradation of Fire fighting system and associated facilities at Oil jetty area-Supply, Installation, Testing and commissioning of Water Pump Set/Water Pumping System including AMC for a period of 5 Years thereof at Oil Jetty Area of Deendayal Port-Kandla. (Phase-I work) | 3701.80 with credit item of Rs. 324.80 | -- | -- | -- | -- | -- | 12 months for EPC Contract & % years of CAMC | Shri Mani Pushpak Sethi Superintending Engineer (M) | Tender hoisted on websites on 28/12/2021. Pre-bid meeting on 12/01/2022. Scheduled date of opening of tender on 28/01/2022. |
| 8 | Supply, installation, testing & commissioning of Sprinkling System for coal dust suppression in 34-hectare coal yard with five Years Operation & Comprehensive Maintenance contract | 2811.33 | 2447.98 | 12.92% | -- | M/s Omkar Enterprise, Ahmedabad | -- | 1 year supply & installation, and, 5 years O&M | Shri Susil Chandra Nahak, Dy. CME, | Price Bid Opened |
| 9 | Outsourcing of 02 Nos. each Truck Mounted Mist Cannon system, and, Truck Mounted Road Sweeper system, along with comprehensive operation & maintenance, for the period of three years at DPT` | 892.73 | 1018.80 | 14.12% above | MS/WK/4047/GIM-542 Dated 21/12/2021 | M/s Sambhav Corporation, Ahmedabad | -- | 3 years | Shri Mani Pushpak Sethi Superintending Engineer (M) | Work Order issued on 21.12.2021 |
| 10 | Maintenance Contract of 03 Nos. 25T and 02 Nos. 16T capacity MBE make wharf cranes, along with Grabs for a period of two years at inside Cargo Jetty Area. | 632.40 | 630.00 | 0.38% below | EL/AC/2549(b)/516 dated 16/08/2019 | M/s. R. S. Electricals, Gandhidham | 16/08/2019 | 15/08/2021 (extended for further six months of date of issue of work order for new contract, which ever is earlier) | Shri Dana Manohar, XEN(M), | AMC in progress. |
| 11 | Design, Supply, Installation, Erection, Testing and Commissioning of DC Over Head/UG 11KV line for providing Power Supply to SIPC of DPT at Kandla | 533.38 | 429.39 | 19.50% below | EL/WK/2613/ 4497 dated 05.02.21 | M/s. Technisys Eng. Pvt. Ltd, Ahmedabad | 05.02.2021 | 04.08.2021 | Shri D.K.Hazra, XEN(E) | Work in Progress |
| 12 | Annual maintenance Contract of Liebherr make HMC:- LHM 550- S/N:- 141143 & LHM 550-S/N:- 141169 for the period of two year at Berth No. 13 inside Cargo Jetty area. | 484.16 | 312.00 | 35.56% below | EL/WK/2553/671 dated 20.07.2020 | M/s. R.S. Electricals, Gandhidham | 20.07.2020 | 19.07.2022 | Shri Dana Manohar, XEN(M), | AMC in progress |
| 13 | Comprehensive Annual Maintenance Contract for Port owned five nos. of Pilot Launches, one no. Survey Launch & two nos. of Mooring Launches for a period of two years. | 435.70 | 349.40 | 19.81% below | W.O.No. ML/WK/3992 dated 18.03.2021 | M/s. SSR Marine Services Pvt. Ltd., Thane | 18.03.2021 | 24 Months | Shri Rajdeep Marine Engineer Gr.I | Work in Progress. |
| 14 | Special Repairs to SFDD Phase-VI self docking to Pontoon 5 & 6 | 434.99 | -- | -- | -- | -- | -- | -- | Shri Rajesh Roat, E.I.C.(DD) | Online tenders opened on 16/12/2021 and the technical bids are under scrutiny. |
| 15 | Comprehensive AMC of Mech works and equipment | 431.40 | 411.60 | 4.59% Below | MS/WK/4048 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | -- | 5 years | Shri Mani Pushpak Sethi Superintending Engineer (M) | LOI issued in 03/11/20211 |
| 16 | Supply, Installation, Testing and Commissioning of High Mast Lighting Tower at Berth No. 14. | 401.08 | 277.75 | 30.75% | -- | M/s. Vishal Electricals, B-4, Hans Plaza, Ambedkar Road, Ghaziabad 201001 | - | - | Shri Chitrang Vyas, AXEN(E) | LOI issued |
| 17 | Maintenance Contract for HT & LT Electrical, installation including substations, overhead Lines, Residential, Non-Residential, Hospital and School Buildings outside Cargo Jetty Area. | 398.48 | 357.89 | 10.18% below | EL/WK/2557/ 383 Dated 10.02.2020 | M/s. Sterling & Wilson Ltd | 10.02.2020 | 09.02.2023 | Shri D.K.Hazra, XEN(E) | AMC is in progress. |
| 18 | Maintenance Contract of 3 Nos. ELL Wharf Cranes of 25T capacity 4 Rope of M/s. TIL make alongwith Grab inside Cargo Jetty Area for a period of 2 years. | 360.00 | 394.20 | 9.5% above | EL/WK/2594/ 4050 dated 19.11.2020 LOI No. EL/AC/2594(a)/4157 dt. 05.11.2020 | M/s. R.S. Electricals, Gandhidham | 05/11/2020 | 04/11/2022 | Shri Dana Manohar, XEN(M), | AMC in progress. |
| 19 | Repairs to 30 Mtr High Mast Towers & AMC of Area Lighting at inside Cargo Jetty Area for a period of Two Years. | 350.44 | 312.60 | 10.80% Below | EL/AC/2538/ 138 dated 01.01.20 | M/s. C.K. Electricals, Surat | w.e.f. date of issue of work order | 31.03.2022 (Provisional extension) | Shri D.K. Hazra, XEN ( E) | AMC in progress. |
| 20 | Operation and Maintenance of 66/11kV and 11/0.433kV Substation inside Cargo Jetty area at DPT, Kandla for a period of two yrs. | 312.46 | 252.00 | 19.35% below | EL/WK/2626/ 562 dated 1.7.2020 | M/s. Ascent Electric. Engineers, Jamnagar | 01/07/2020 | 30/06/2022 | Shri D.K.Hazra, XEN(E) | AMC is in progress. |
| 21 | Annual Rate contract for supply & laying of HT/LT underground cables at inside and outside cargo jetty area. | 261.18 | 232.43 | 11.00% below | EL/WK/2608/ 1295 dated 05-04-21 | M/s. Onix Structure Pvt. Ltd, Rajkot | 05-04-2021 | 04-04-2021 | Shri D.K.Hazra, XEN(E) | ARC is in progress. |
| 22 | Major Repair Work of Heave Up Barge Bhimsen. | 166.77 | -- | -- | -- | -- | -- | 120 days | Shri Rajdeep Marine Engineer Gr.I | Tender opened on on17/11/2021 &clarifications called form the bidders on technical bids which are received and the same are under scrutiny. |
| 23 | Appointment of Consultant for the work of Mechanization of handling of Fertilizers at Kandla Port | 166.67 | N.A | N.A | N.A | N.A | N.A | N.A | Shri Susil Chandra Nahak, Dy. CME, | Project mode transferred from EPC to PPP mode. So, the services of existing Transaction Advisor (TA) appointed for PPP projects has been rendered. |
| 24 | Supply, Installation, Testing & Commissioning of 01 no. Kirloskar Make Vertical Turbine Fire Fighting pump - Diesel engine driven located at cargo jetty area No- 01” through Authorized dealer of Kirloskar Brothers Ltd. or OEM | 157.08 | 160.16 | 1.96% above | W.O, No. ML/WK/4037/ 350 Dtd. 21/11/2021 | M/s. Jay Project, Vadodara | 21.11.2021 | 180 days | Shri Mani Pushpak Sethi Superintending Engineer (M) | Work commenced from 21.11.2021 Work in progress. |
| 25 | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhidham Area for period of three years. | 154.92 | 139.22 | 10.14% below | No. DD/WK/4309/ 338 dated 04.08.2021 | M/s. Inspection & Engineering Services, Ahmedabad | 04.08.2021 | 3 years | Shri Rajesh Roat, E.I.C.(DD) | Work in Progress. |
| 26 | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weighbridges (15Kmph speed) of 140Mt capacities including comprehensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 150.79 | 147.67 | 2.07% below | W.O. No.ML/WK/ 3916-II/738 dtd. 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., E-1, TVK Industrial Estate, Guindy, Chennai - 600032 | 05/01/2019 | 120 days, i.e. 04/05/2019. Further, extension has been granted from 5.05.2019 to31.01.2021 or 120 days after site clearance from upgradation of existing Rail Network inside Cargo Jetty area, whichever is later as per recommendations of the variation committee. | Shri Rajesh Roat, E.I.C. (Railway In-motion weigh Bridge) | 2 nos. of weigh bridges have been installed and commissioned. Remaining two weighbridges are also installed. Commissioning to be done after inspection by test wagons provided by Railway Authority. Stamping certificate also issued. WIP by EDP section. |
| 27 | Replacement of existing feeder pillar of High Mast & Lattice Towers with FRP Feeder Pillar | 109.59 | 107.97 | 44.99% below | EL/WK/1948/ 1253 dtd. 26.03.21 | M/s.Rajdeep Electricals Pvt. Ltd, G’dham | 31.03.2021 | 28.07.2021 | Shri Chitrang Vyas, AXEN(E) | Work is in progress. |
| 28 | Supply, Installation, Testing & Commissioning of five numbers 100 M.T. Capacity, Pit-less Type, fully electronic, Road Weighbridges with Five Years Comprehensive Maintenance contract after expiry of two years guarantee Period. | 91.15 | 74.85 | NA. | ML/WK/3942/ 596 dated 16.12.2019 | M/s. Techno Scale Industries, Ahmedabad | 16.12.2019 | 120 days i.e. 13.04.2020 | Shri Mani Pushpak Sethi Superintending Engineer (M) | Board has approved the proposal for outsourcing of weigh bridges and accordingly, the work is not required to be executed. Proposal for cancellation of work order submitted to competent authority. |
| 29 | Appointment of Consultant for the study & preparation of Techno-Economical Feasibility report for the mechanized handling of bulk cargo at Deendayal Port | 56.00 | - | - | - | - | - | - | Shri Mani Pushpak Sethi Superintending Engineer (M) | Tender Uploaded |
| 30 | Appointment of Consultant for carrying out environmental impact assessment and environmental management plan studies for development of another ship-repairing facility at Vadinar, to obtain statutory clearances from State authorities & MoEF&CC. | 52.02 | 35.10 | 32.53% below | LOA No. DD/WK/3050/EC/598 dated 8.12.2020. | M/s. Envision Enviro Technologies Pvt. Ltd., Surat | 08/12/2020 | 12 Months | Shri Rajesh Roat, E.I.C.(DD) | The Work has commenced on 8.12.2020 and the inception report has been submitted. NOC from Marine National Part & Sanctuary and CRZ meeting held on 23/11/2021 in which Virtual Clearance Received. |
| 31 | Sand blasting and painting work of various structure of steel Floating Dry Cock. | 48.53 | 43.19 | 8.33% below | No. DD/WK/3061/ 123 dated 10.03.2021 | M/s. Marine Services, Thane | 10.03.2021 | 180 days | Shri Rajesh Roat, E.I.C.(DD) | Work in Progress |
| 32 | Sell of renewable power generated from DPT’s 14.7 MW wind power plant on Medium Term Open Acces basis through tariff based competitive bidding through auction | Rs. 4.26 per unit | Rs. 4.27 | - | LOI No. EL/C/2688/ 1158, dated 10.11.2021 | M/s. UPL Ltd. GIDC Jhagadia- Bharuch | - | - | Shri D.K. Hazra, XEN(E) | LOI Issued |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 31.12.2021

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | 49.32 Cr. | 6.62% below | No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. | M/s. Parsh Construction and Foundations Pvt. Ltd., Mumbai | 26/03/2021 | 18 months | Shri Vikash A.C. XEN (Civil), | Work Order issued vide No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. |
| 2. | Hiring of 2 Nos. Steel Hull Mooring Launches with Crew and Mooring Gang at OOT, Vadinar for the period of Five (05) years. Estimate: Rs. 12,53,49,780/- | 12.53 Cr. | 9.12 Cr. | 27.21 % below | OOT/ME/WK/8017/484 dated 21/05/2021. | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | -- | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. OOT/ME/WK/8017/484 dated 21/05/2021.. |
| 3. | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | No. OOT/ME/WK/3009-I/576 dated 26/12/2018. | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 4. | Painting work for residential and Non-residential buildings Port Colony at Vadinar | 2.58 Cr, | 1.61 Cr. | 37.66% Below | OOT/C-WK/ RM/4049/ 656 dated 06/09/2021 | M/s. Shreeji Enterprise Gondal | 19/07/2021 | 18 Months | Shri Vikash A.C. XEN (Civil), | Work Order issued vide OOT/C-WK/RM/4049/656 dated 06/09/2021 |
| 5. | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 Cr. | 5.01 % above | OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri Vikash A.C. XEN (Civil), | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. |
| 6. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.44 Cr. | 2.83% above | OOT/ME-WK/RM/6004/239 dated 04/03/2021. | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. |
| 7. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | 1.06 Cr. | 2.98% above | OOT/C-WK/RM/4002/2001 dated 12/03/2020 | M/s. Abhay Intelligence & Security Services, Vadodara. | 14/03/2020 | 2 years | Shri Vikash A.C. XEN (Civil), | Work Order issued vide No. OOT/C-WK/RM/4002/2001 dated 12/03/2020 |
| 8. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | OOT/ME-WK/RM/ 6018/329 dated 26/03/2021. | M/s. Pariya Electricals, Vadinar. | 01/04/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2021. |
| 9. | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | OOT/ME/WK/RM/8009/1947 dated 03/03/2020. | M/s. Aeromarine Pvt. Ltd., Mumbai | 03/03/2020. | 3 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/RM/8009/1947 dated 03/03/2020. |
| 10. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 | 6.01 % below | OOT/ME/WK/6008/1795 dated 06/02/2020. | M/s. Safari Travels, Balasinor | 07/03/2020 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME/WK/6008/1795 dated 06/02/2020. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 31.12.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dredging in the Navigational Channel & Alongside Cargo Berths/Oil Jetties at Deendayal Port Trust for year Year 2020-23”. Location At Kandla | 393.80 | 310.04 | 21.27 % Below | LOA No. EG/WK/6116/182 dated 10.03.2021 | M/s Adani Ports and Special Economic Zone Ltd., Ahmedabad | 09.04.2021 | 18/04/2024 36 months | Shri K. Srinivasa Rao, SE (H&D) | Work is in progress |
| 2 | Augmentation of liquid cargo handling capacity by revamping of existing pipeline network at Oil Jetty are, Deendayal Port Trust, Kandla | 130.49 | 126.49 | 3.05% below | CN/WK/ 2174/Work/ 322 dated 16/09/2021 | M/s Patel Corrrtech JV, Gandhidham | 30/09/2021 | 29/09/2023 24 months | Shri Rajendra Prasad SE (P) | Work in Progress |
| 3 | Construction of Oil Jetty No.8 at old kandla. | 105.51 | 99.08 | 6.09 below | CN/WK/1571/work/243 dtd.03.02.21 | M/s Kargwal KM Joint Venture, Mumbai | 17.02.2021 | 18 months | Shri B. Rajendra Prasad, SE (P) | Work in Progress |
| 4 | Upgradation and strengthening of existing road from WG 2 to 16th Cargo Berth - Phase-I | 69.18 | 41.5 | 40.02% | CN-I/WK/ 2259/ Works/ 92 dated 01/03/2021 | M/s MKC Infrastrucutre Ltd., Anjar | 03-09-2021 | 11 months | Shri M.T. Gohil XEN(C-I) | Work in Progress |
| 5 | Retrofitting cargo berth No.8 & Retrofitting cargo berth No.9 | 64.86 | 47.27 | 27.13 % Below | - | M/s. BMS Project & Marymatha JV. | - | 16 Months | Shri M.T. Gohil XEN(C-I) | Price Bid opened on 31.12.2021, M/s. BMS Project - Marymatha JV, Kerala Stands L-1 |
| 7 | Development of plots, Roads & SWD in 34 hectare area inside CJA | 57.08 | 36.6 | 35.89% below | HW/WK/2486/363 dated 20/02/2021 | M/s. Bhimji Velji Soratia Construction P Ltd., | 06-03-2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 8 | Construction of Dome Shaped Storage Sheds inside cargo jetty area – Phase-I | 46.53 | 35.93 | 22.78% below | HW/WK/2475/456 dated 16.06.2021 | M/s Patel Construction. Gandhidham | 30.06.2021 | 12 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 9 | Construction of Oil Jetty No.7 at old kandla. | 44.59 | 42.4 | 4.93 % below | No.CN/WK/ 1553/81 dated 26.10.2015 | M/s Kargwal Construction Pvt. Ltd., Mumbai | 26/02/2020 | 18 months, Ext. granted upto 23.07.2022 | Shri B. Rajendra Prasad, SE (P) | WIP (extension granted upto 23.07.2022) |
| 10 | Development of Land in the West of Existing 66 hectare area for storage of cargo (Extension of custom bonded area) | 42.81 | 33.38 | 22.02% below | HW/WK/2457/355 dated 17/02/2021 | M/s. Kalthia Engineering Construction Ltd. | 02-03-2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 11 | Extension of Custom Bounded area in Backup of 13th & 16th Berth | 40.00 | - | - | - | - | - | - | Shri M.T. Gohil XEN(C-I) | Technical bid processed |
| 12 | Construction of A,B, C and D type quarters at Gopalpuri | 18.94 | 13.78 | 27.16% below | TW/WK/7775/299 dtd. 07.06.2021 | M/s. VC Project & Infra Pvt. Ltd. | 05.06.2021 | 04.06.2023 | Shri M.T. Gohil XEN(TD) | work in progress |
| 13 | Providing screen wall surrounding the coal stacking yard inside CJA of DPT | 18.63 | 14.9716 | 19.6307% below | HW/WK/2423/468 dated 29.06.2021 | M/s. Mohandas V Rajani, | 15.08.2021 | 12 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 14 | Development of Parking yards for trucks/vehicles for pre checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 | 14.59 | 12.87% below | HW/WK/2446/463 dated 26.06.2021 | M/s. Indian Construction Co., | 08.07.2021 | 12 months work and 24 months maintenance | Shri Srinivas Rao, SE (H) | Work in progress |
| 15 | Retrofitting of the Bunder Basin Structures | 10.00 | - | - | - | - | - | - | Shri M.T. Gohil XEN(C-I) | Technical bid processed |
| 16 | Improving existing oil jetty structures at oil jetty No.1, 2, 4 | 8.20 | 8,08,15,600/- | 1.5515% below | PL/WK/8421-I/2238 dated 10/06/2020 | M/s. Sarjan Construction Pvt. Ltd. | 20/06/2020 | 18 Months | Shri Rajendra Prasad B., SE(PL) | Work in Progress |
| 17 | Upgradation of Plots, Roads &SWD behind Berth No. 7 to 10 inside Cargo Jetty area. | 8.20 | 5.56 | 32.08% below | HW/WK/2490/496 dated 29/07/2021 | M/s Krishna Construction | 29.07.2021 | 11 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 18 | Improving / Upgradation of Custom Fencing Wall of Cargo jetty and Bunder Area | 7.68 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | TCN sent for discharge and reinvite the bid. |
| 19 | S/R to Road along side Godown no 18, 24, 32 & 33 inside cargo jetty area | 7.68 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | TCN for technical bid is under submission. |
| 20 | Strengthening of multi storey Building with micro concreting, plinth protection at Gopalpuri | 6.61 | 4.26 | 35.41% below | TW/WK/7794-I/ dtd. 26.03.2021 | M/s. Mohandas V. Rajani, Adipur | 01.04.2021 | 30.09.2022 | Shri M.T. Gohil XEN(TD) | work in progress |
| 21 | S/R to Quarters to Gopalpuri-Replacement of slabs, water proofing chajjas, walls etc. | 6.56 | 4.78 & 4.66 (credit item) | 27.26% below | TW/WK/7783/274 dtd. 24.05.2021 | M/s. Dhanjibhai K Patel, Anjar | 24.05.2021 | 23.05.2022 | Shri M.T. Gohil XEN(TD) | work in progress |
| 22 | Appointment of Project Management Consultant (PMC) for Capital and Maintenance Dredging works of Deendayal Port Trust from firms/consortiums Empanelled Consultants for dredging works (Class-A, Category-A) by Indian Port Association, New Delhi. | 6.36 | Rs. 5.33 | 15.32 % Below | LOA No. EG/WK/6112/333 dated 15.11.2019 | M/s AECOM INDIA PVT LTD, GURGAON | Work commenced from 25.11.2019 | 36 months | Shri K. Srinivasa Rao, SE (H&D) | Work is in progress |
| 23 | Improving & up-gradation of gardens and land scrapping at Gopalpuri (Renovation of Nehru park and rain water harvesting by strengthening of SWD network near recharging pond at Gopalpuri. | 4.79 | 2.4 | 49.81% below | TW/WK/7802-I/404 dtd. 16.07.2021 | M/s.Rainbow Infrastructure, Rajkot | 03.07.2021 | 02.07.2022 | Shri M.T. Gohil XEN(TD) | work in progress |
| 24 | Construction of SWD and Cable Trench at backup Of Beth No 11 & 12 | 4.70 | 3.15 | 33.05 % Below | LOA No. EG/WK/8112/225 dated 21/04/2021 | M/s Dharti Construction, Anjar | 05-12-2021 | 10 months | Shri M.T. Gohil XEN(C-I) | work in progress |
| 25 | Preparing and monitoring of environmental management plan for DPT at Kandla. | 4.076 | 2.52 | 38.17 % below | EG/WK/EMC/11023/2011/ IV dtd. 05.12.19 | M/s Detox Corporation Pvt. Ltd. | 16.12.2019 | 36 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 26 | Construction of compound wall on vacant plots of Gandhidham Township-Removal/Prevention of Encroachment –Stage-II | 4.06 | 2.29 | 43.54% below | TW/WK/7767-I/ dated 26.08.2021 | M/s. Ankita Construction, Adipur | 26.08.2021 | 25.08.2022 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 27 | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 | Rs. 2.43 | 35.73% Below | HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd.,Gurgaon - 122015 Haryana- India | 11.02.2021 | 36 months | Shri K. Srinivasa Rao, SE (H&D) | Work is in progress |
| 28 | Providing Legal, Technical and Financial transactions for all ongoing and future proposals of DPT on PPP / Captive Mode for the period of two years and further extendable for one year. | 3.26 | 1.985 | 39.25% below Estimated Cost | EG/WK/4759/TA/79 dated 10.10.19 | Infrastructure Development (Karnataka) Corporation Ltd (Ideck) | 14.10.2019 (as per Work Order) | 2 years and further extendable for 1 year | Shri K.J. Todarmal, SE(D) | Work in progress. |
| 29 | Construction of watch tower inside cargo jetty area | 3.04 | 2.84 | 6.22 % below | HW/WK/2470/407 dated 09.04.2021 | M/s. Viyuha Infrabuild | 24-05-2021 | 8 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 30 | Strengthening of Sewage, Drainage, SWD, Culvert network at Gopalpuri, KDLB colony | 2.98 | 1.45 | 51.18% below | TW/WK/7787-I/248 dtd. 21/04/2021 | M/s. Sterling Infrastructure co. | 22.04.2021 | 21.04.2022 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 31 | Improving the fendering arrangement inside cargo jetty area HD-14/19 | 2.85 | 3.54 | 24.39% above | HW/WK/2392/137 dated 02/06/2020 | M/s. Patel Construciton Co., Gandhidham | 15-06-2020 | 12 months (Extension of work granted upto 14.12.2021) Proposal submitted for 2nd extension upto 14/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 32 | R/m of Maintenance Jetty - Repairs and Maintenance of Pontoons and Walkways of SNA Jetty and Flotilla Jetty | 2.77 | 3.37 | 10.51% above | HW/WK/2494/462 dated 25.06.2021 | M/s Patel Construction. Gandhidham | 08.07.2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 33 | Two years contract for supply and maintenance of railway tracks inside and outside cargo jetty area (for 02 years | 2.59 | 2.03 | 21.40 % below | HW/WK/2487/359 dated 20/02/2021 | M/s. Laxyo Entergy Ltd. | 06-03-2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 34 | Improving Storm Water drainage system at old Kandla. | 2.31 | 1,67,88,037/- | 27.54% below | PL/WK/8408/944 dated 06/10/2021 | M/s. Shree Ganesh Cosntruction. | 30/11/2021 | 11 Months | Shri Rajendra Prasad B., SE(PL) | Work in Progress |
| 35 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2020-22 | 2.19 | 1.15 | 47.36% below | TW/WK/7781-I/ 621 dt.14/10/2020 | M/s. Rajput Infrastructure, G’dham | 15/10/2020 | 14/10/2022 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 36 | AMC for White washing, Distempering & painting to Resi. & NRB at Gopalpuri, KDLB, G’dham & Adipur for the year 2020-21. | 1.98 | 0.93 | 52.80% below | TW/WK/7760-I/88 dtd. 11/02/2021 | M/s. Mepabhai Mandan & Co. | 02-11-2021 | 02-10-2022 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 37 | House Keeping & Cleaning of office building and surrouding outside Cargo Jetty aea for year 2021-23. | 1.97 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Revised scrutiny report sent for approval. |
| 38 | Annual Maintenance contract for Godown inside cargo jetty area for two years (HD-03/19) | 1.96 | 1.28 | 34.44% below | HW/WK/2405/338 dated 13/12/2019 | M/s. Mepabhai Mandan & Co. | 13-Dec-19 | 24 months (Proposal submitted for extension upto 12/03/2022) | Shri Srinivas Rao, SE (H) | Work in progress. Anticipated variation 28% approved by competent authority |
| 39 | Deployment of equipment for cleaning of all toilet block inside Port area to maintain high standard of hygienic and to avoid pollution (HD-20/19) | 1.88 | 1.16 | 38.04% below | HW/WK/2428/104 dated 21/04/20 | M/s. Patel Construction | 04-05-2020 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 40 | Maintenance contract for roads and RCC culverts inside CJA at New Kandla for 02 years | 1.75 | 1.84 | 5.74 % above | HW/WK/2443/401dated 31.03.2021 | M/s Shree Ganesh Construction | 16-04-2021 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 41 | Two years maintenance contract for cleaning and sweeping of office building & surrounding outside at New Kandla | 1.67 | 0.99 | 41.11% below | HW/WK/ dated 30/07/19 | M/s. Dhanji K Patel | 30-Jul-19 | 24th months (Extension granted upto 31/10/2021) | Shri Srinivas Rao, SE (H) | Work in progress - proposal for extension upto 31/01/2022 is submitted to competent authority |
| 42 | Construction of Fire Brigade Station at Old Kandla. | 1.65 | Part - A 1,34,34,770/- Part - B 7,75,621/- | 13.9597% below | PL/WK/8446/919 dated 30/09/2021 | M/s. Ankita Construction. | 30/10/2021 | 12 Months | Shri Rajendra Prasad B., SE(PL) | Work in Progress |
| 43 | Annual Maintenance Contract for cleaning & housekeeping work of DPT Hospital & Isolation Ward at Gopalpuri & Kandla (for 2years) | 1.62 | 0.85 | 47.70% below | TW/WK/7798 dtd.30.01.2021 | M/s. Patel Const. co., G’dham | 02-10-2021 | 02-09-2023 | Shri M.T. Gohil XEN(TD) | work in progress |
| 44 | Maintenance Contract for Residential & Non - Residential Building at New Port Colony at New Kandla for two years. | 1.59 | 1.06 | 33.30% below | RW/WK/7790-I/509 dtd.01.09.2020 | M/s. Rajput Infrastructure Co., Gandhidham | 02.09.2020 | 01.09.2022 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress. |
| 45 | Providing labour amenities centre at various locatios inside Cargo Jetty area. | 1.53 | 1.18 | 22.85 % below | N.A. | M/s. Rajput Infrastructure Co. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Price bid opened on 15/12/2021. L-1 offer submitted for approval. |
| 46 | Providing RCC drinking water tank. | 1.52 | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad B., SE(PL) | Price bid opened on 25/12/2021 |
| 47 | Appointment of Independent Engineer for the work of “Development of Marine Liquid Terminal Facilities consisting of SPM and Two Product Jetties in KPT waters at OOT, Vadinar for Handling Crude and Petroleum Products on Captive Use Basis”. | 1.44 | 1.18232 | 17.89% below | Work Order No.EG/WK/ 4823(IE)/109 dated 22.10.19 | M/s RINA Services s.p.A,Mumbai | 01-11-2019 | 42 months | Shri K.J. Todarmal, SE(D) | Concessionaire has not started construction activity, the work order issued to M/s. RINA has been kept in abeyance. |
| 48 | Construction of 3 Nos. Toilet blocks on central road inside cargo jetty area at New kandla | 1.40 | 1.187 | 14.39% below | HW/WK/2477/299 dated 15.12.2020 | M/s. Dharam Constrution Co., | 28.12.2020 | 11 months (Extension granted upto 27/02/2022) | Shri Srinivas Rao, SE (H) | Work in progress |
| 49 | Third party inspection and quality assurance for the works costing more than 1 Cr. of Civil Engineering Department of DPT. | 1.35 | 1.17 | 14.05% below | EG/WK/5212/53 dtd. 16.10.2021 | M/s. VCS Quality Services pvt. Ltd., Mumbai | 25.10.2021 | 2 years from 25.10.2021 | Shri Sunil Soren, XEN(D) | LOA issued to M/s. VCS Quality services pvt. Ltd. Work order on 16.10.2021. Work in Progress. |
| 50 | Maintenance Contract for non-residential building inside Habour area (Civil work) | 1.31 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Technical bid under scrutiny |
| 51 | Annual Maintenance Contract for the Buildings, Walkway, trestles, fire fighting pipelines, garden insdie and outside oil jetty area at Old Kandla. | 1.29 credit part 4,95,000/- | part A 1,17,15,386.00 Part B credit item 4,29,066.00 | 9.63% below the est. cost. | PL/WK/8316-II/125-A dated 12/02/2021 | M/s. Mahesh Construction, Adipur. | 15/02/2021 | 12 Months | Shri Rajendra Prasad B., Superintending Engineer (PL) | The work is in progress, 1st RA Bill paid. |
| 52 | Annual Maintenance contract of Fender inside cargo jetty area (HD-01/19) | 1.28 | 1.51 | 18.35% above | HW/WK/2375/ dated 13/12/2019 | M/s. Patel Construction Co. | 13-Dec-19 | 12 months (Extension granted upto 17/12/2021, proposal submitted for extension upto 17/06/2022) | Shri Srinivas Rao, SE (H) | Work in progress |
| 53 | Modernization of A.O. Building at Gandhidham Stage-II. | 1.26 | 0.89 | 29.76% below | TW/WK/7717-I/ 345 dt.20/05/20 | M/s. Pars Enterprise, G’dham | 06-03-2020 | 06-02-2022 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 54 | Strengthening of existing environmental management cell at DPT. Appointment of environment experts for two years and further extendable for one year | 1.23 | 1.2 | (-) 2.60% below | EG/WK/4783//V/100 dated 04.01.2021 & No.EG/WK/4783/V/131 dtd.05.02.21 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15.02.2021 | 24 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 55 | Two years maintenance contract for railway track leading to Tuna from 0 to 11 Km KPT line (take off point at 2.537 Km at GIM Yard to 13.54 Km) including LC-1, LC -2. | 1.19 | 0.908 | 23.77% below | HW/WK/2515/432 DATED 31/05/2021 | M/s Patel Construction. Gandhidham | 14-06-2021 | 24 Months | Shri Srinivas Rao, SE (H) | Work in progress |
| 56 | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla. -HD-07/19 | 1.12 | 1.20 | 7.21% above | HW/WK/2379-III/332 dated 05/12/2019 | M/s. Patel Construction Co. | 18-Dec-19 | 12 months Extension of work granted upto 17.12.2021. Proposal for 2nd extension submitted upto 17/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 57 | Strengthening of RCC custom fencing wall of Oil Jetty and providing CCTV lighting arrangement at Old Kandla - Strengthening of RCC custom fencing wall. | 1.11 credit part 2,12,790/- | part A 76,57,423.00 Part B credit item 1,24,560.00 | 31.4865% below the est. cost. | PL/WK/8420-I/2652 dated 14/10/2020 | M/s. Rajput Infrastructure Company Gandhidham | 28-10-2020 | 06 Months (extend upto 27/10/2021) | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in progress, |
| 58 | Maintenance contract for quay and transit area inside cargo jetty area for two years | 1.04 | N.A. | 16.77% | HW/WK/2617/12 dated 24/09/2021 | M/s. Sanjay K Sorathiya & Co. | 10-10-2021 | 24 Months | Shri Srinivas Rao, SE (H) | Work in progress |
| 59 | Maintenance Contract for Sanitation of New Port Colony New Kandla for year 19-20. | 0.98 | 0.66 | 32.04% below | RW/WK/7784-I/45 dt. 26.8.2019 | M/s. Vihat Const. Co., G'dham | 2.9.2019 | 1.9.2021 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress (Ext. applied for 04 months) |
| 60 | Dismantling of Residential and Non - Residential buildings at New Kandla | 0.96 | 1.58 | 64.42% above | RW/WK/7706-I/19 dtd. 08.12.2021 | M/s. Symcom Exim (P) Ltd., Mumbai | 16.12.2021 | 15.08.2022 | Shri Hemant Kumar Bhaskar XEN(Road), | Work order issued on 08.12.2021. |
| 61 | Tree plantation near offices other buildings along roads etc. including two years maintenance contract at New Kandla - HD-06/19 | 0.96 | 0.72 | 25.06% below | HW/WK/2380-I/99 dated 13/04/2020 | M/s. Dhanjibhai K Patel, Anjar | 24-04-2020 | 23/04/22 (24 months) | Shri Srinivas Rao, SE (H) | Work in progress. |
| 62 | Two years maintenance contract for office buildings outside Port area (civil work) - HD-2/19 | 0.89 | 0.64 | 27.27% below | HW/WK/23366-I/339 dated 13/12/2019 | M/s. Mohit Construction | 13-Dec-19 | 24 months | Shri Srinivas Rao, SE (H) | Work completed on 05/12/2021 |
| 63 | Two years contract for cleaning of storm water drain inside cargo jetty area | 0.80 | 0.42 | 47.81% below | HW/WK/2444/180(A) dated 10.07.2020 | M/s. Narayan Construction Co. | 29.07.2020 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 64 | AMC of custom fencing wall and gates of cargo jetty and bunder area | 0.74 | 0.48 | 35.2% above | HW/WK/2420/320 dated 21/25.01.2021 | M/s. Sanjay K Sorathiya & Co. | 05.02.2021 | 12 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 65 | Improving of Oil Jetty Gate & Canteen at Old Kandla. | 0.71 | 62,03,302/- | 13.29% below | PL/WK/8148-I/641 dated 08/07/2021 | M/s. Mepabhai Mandan & Co. | 08/07/2021 | 12 Months | Shri Rajendra Prasad B., SE(PL) | Work in Progress |
| 68 | Annual Maintenance Contract for A.O. Building at Gandhidham | 0.71 | 0.45 | 36.36% below | TW/WK/7799-I/110 dtd. 01.03.2021 | M/s. Rajput Infrastructure co., G’dham | 02.03.2021 | 01.03.2022 | Shri M.T. Gohil XEN(TD) | work in progress |
| 69 | S/R to Non - Residential Buildings - Providing water proofing to terrace and interior wall of A.O> Building | 0.67 | 0.41 | 39.11 below | TW/WK/7777-I/534 dated 13.10.2021 | M/s. Rajput Infrastructure Co., Gandhidham | 13.10.2021 | 12.04.2022 | Shri M.T. Gohil XEN(TD) | work in progress |
| 70 | Annual Maintenance Contract for Sports Complex at Gopalpuri for the period of 2 yrs. | 0.65 | 0.42 | 35.35% below | TW/WK/7764-I/ 371 dt.14/04/2020 | M/s. Patel Const. Co., | 16/04/2020 | 15/04/2022 | Shri M.T. Gohil XEN(TD) | Work in progress |
| 71 | Annual Maintenance Contract for Sanitation of New Port Colony, New Kandla | 0.64 | 0.34 | 46.36% above | - | M/s. Rajput Infrastructure Co., Gandhidham | - | - | Shri Hemant Kumar Bhaskar XEN(Road), | Price Bid opened on 20.11.2021 and under process |
| 72 | Providing Power supply arrangements for air conditioner units installed at A.O Building, Gandhidham | 0.62 | 0.49 | 21.21 % Below | TW/WK/7796-I/247 dtd.21.04.2021 | M/s. Mepabhai Mandan & Co., Adipur | 22.04.2021 | 21.03.2022 | Shri M.T. Gohil XEN(TD) | work in progress |
| 73 | House keeping & cleaning of office building inside cargo jetty area (for 2 years) HD-10/19 | 0.54 | 0.4128 | 23.43% below | HW/WK/2422-I/367 dated 20/02/2021 | M/s. Shree Ganesh Construction, Anjar | 6-Mar-21 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 74 | R/M of CISF Complex at New Kandla - Repairs to Toilet block at CISF Complex, New Kandla | 0.50 | 0.45 | 11.01% below | RW/WK/7782-I/81 dtd.16.02.2021 | M/s. Pars Enterprise, Gandhidham | 21.02.2021 | 20.08.2021 | Shri Hemant Kumar Bhaskar XEN(Road), | Work extended upto 20.10.2021 vide EG/WK/5836/485 dated 03.12.21 |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No | Name of work & location | Reserve price Per sq. mtr./year | Premium received over and above reserve price during e-auction (per sq. mtr. / per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | “E-tender cum e-auction is for allotment of various sizes of plot for salt manufacturing and salt related activities in between village Veera to village Jungi on 30 years lease on as is where is basis”- Phase-I | Rs. 25923.3 Per Acer / Per Annum | -- | -- | -- | -- | ShriI S.K. Rao, SE (KL) | Technical bid opened on 04.12.2021. Technical evaluation processed. Grievances received & Legal Opinion sought. |
| 2 | E-tender cum e-auction for allotment of plot admeasuring 15690 Sq. Mtrs situated adjacent to Plot No. 61 & 62 (Allotted to Vijay Tanks & Vessels(P) Limited, Vadodara) Kandla for Construction of Petrol Pump cum Service Station on 10 years lease on as is where is basis. | Rs. 212.89 Per Sq. Mtr / per year | -- | -- | -- | -- | ShriI S.K. Rao, SE (KL) | Technical bid opened on 02.12.2021. Tender proceed for discharge due to simple unqualified bidder as per TCM. |
| 3 | E-tender cum e-auction for allotment of plot admeasuring 4000 Sq. Mtrs situated opposite to VTMS towards and behind boundary of DPT (East of Dry Dock) for the purpose of barge repairing/beaching on 5 years lease on as is where is basis | Rs. 271.69 Per. Sq. Mtrs / per year | -- | -- | -- | -- | ShriI S.K. Rao, SE (KL) | Technical bid opened on 02.12.2021. Tender under discharge as per TCM. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6 .	MARINE DEPARTMENT							                                                                                      AS ON 31.12.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | - | Draft Agreement submitted. | M/s. Electronics Corporation of India Ltd., Hyderabad | 25/11/2021 | 24 months for supply, installation and commissioning AMC 10 years after installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Supply & Installation work completed on 25/11/2020. AMC work in progress. |
| 2 | Hiring of 04 Nos. of 50/60 tonn Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below Estimated Cost - OSL Ltd. 20.08% below Estimated Cost - KNK Ship | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator | Board vide Resolution No. 56 in its meeting held on 12.08.2016 have approved to award the work to contractors. W.O. has been issued on 03/10/2016 & 22/09/2016. |
| 3 | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | 26/04/2021 | 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 13/10/2020. Work Order issued on 05/01/2021. . |
| 4 | Renewal of Steal Plates & painting of various crafts / Tugs of DPT | 2.09 Cr. | 1.80 Cr. | 14.19% below | Executed on 16/06/2021 | M/s. Patel Engineering Works, Gandhidham. | 06/08/2021 | 2 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 21/05/2021. Work Order issued on 13/07/2021. |
| 5 | Design, Consultation and supply of 2 Nos. of Steel Hull Mooring Launches. | 2.42 Cr. | 1.95 Cr. | 19.25% below | Executed on 28/12/2020 | M/s. A.H. Wadia Boar Builders, Bilimora | 10/01/2021 | 1st Launch in 12 months 2nd Launch in 15 months. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 14/12/2020. Work Order issued on 07/01/2021. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 31.12.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |
| 2. | Hiring of brand new make and model of 2018 on "monthly hire basis" and made and model not earlier than1st January, 2017 on "as and when required basis" diesel vehicles to DPT for a period of 03 years | 8.86 Cr. | 8.23 Cr. | 4.34% Below | Executed. | M/s. Shree Ganesh Travels, Mumdra | 01/01/2019 | 30/06/2022 | Shri Piyush Parag, Law Officer.. | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	MEDICAL DEPARTMENT										                                            AS ON 31.12.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. | Dr. (Mrs.) K. Gandhi Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	TRAFFIC DEPARTMENT											                	AS ON 31.12.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Engagement of manpower service provider for providing various categories of outsourced staff to carry out railway operation inside Cargo Jetty area for a period of 3 years. | 3.88 Cr. | 2.87 Cr. | 26.00% below | Executed on dated 26/07/2021 | M/s. Dhanjibhai K. Patel, Anjar. | 01/05/2021 | 30/04/2024 | Shri T.D. Maheshwari, ATM (Railway), | Work in progress. |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

9.	FINANCE DEPARTMENT										                                     AS ON 31.12.2021

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |  |  |  |  |  |  |  |  |  |  |

*****