DEENDAYAL PORT TRUST

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 31.08.2020

| Sr. No. | Name of work and location | Estimated cost (Rs.) in lakh | Tendered Cost (Rs.) in lakh | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 8181.98 | 6359.61 | 18.91 Below | EL/WK/2472/ 480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Commenced on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri Susil Chandra Nahak, Dy. CME | Comprehensive A.M.C. work in progress. |
| 2. | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 15570.46 | 14446.38 9685.90 towards capital cost &4760.48 towards O&M Charges. | 7.22% Below | EL/WK/2491/ 1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri Susil Chandra Nahak, Dy. CME | Work completed on 30/03/2019, Free maintenance period of two years is in progress. |
| 3. | Maintenance Contract of 3 Nos. ELL Wharf Cranes of 25T capacity 4 Rope of M/s. TIL make alongwith Grab inside Cargo Jetty Area for a period of 2 years. | 360.00 | 468.00 | 30.00% Above | N.A. | N.A. | N.A. | N.A. | Shri Dana Manohar, XEN(M) | Minutes of the Negotiation Committee has been finalized. Proposal for acceptance of L1 bidder and work order is under process. |
| 4 | Design, Manufacture, Supply Erection, Testing, Commissioning & Operation of 02 Nos .of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 9181.77 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit (LC) | 08 months from the date of opening of letter of credit (LC) | Shri Dana Manohar, XEN(M) | CAMC work in progress. |
| 5. | Repairs to 30 Mtr High Mast Towers & AMC of Area Lighting at inside Cargo Jetty Area for a period of Two Years. | 350.44 | 312.60 | 10.80% Below | EL/AC/2538/138 dated 01/01/2020 | M/s. C.K. Electricals, Surat | w.e.f. date of issue of work order | 02 years from date of issue of work order | Shri Susil Chandra Nahak, Dy. CME | Work is in progress. |
| 6. | Maintenance Contract of 03 Nos. 25T and 02 Nos. 16T capacity MBE make wharf cranes, along with Grabs for a period of two years at inside Cargo Jetty Area. | 632.40 | 630.00 | 0.38% below | Work Order EL/WK/2549(b)/ /516 dated 16/08/2019 | M/s. R. S. Electricals, Gandhidham | 16/08/2019 | 15/08/2021 | Shri Dana Manohar, XEN(M) | Work is in progress. |
| 7. | Maintenance contract of 4Nos of MUKAND Cranes of 12T (2Nos) & 16T (2Nos.)capacities ELL Cranes, Along with Grabs for a period of 2 yrs inside C Jetty area | 474.67 | 364.80 | 23.15% below | EL/AC/2531 –(c)/410 dated 20/07/2019 | M/s. R. S. Electricals, Gandhidham | 20/07/2019 | 19/07/2021 | Shri Dana Manohar, XEN(M) | Work is in progress. |
| 8. | Electrification work at Location of 5 Nos. New Weigh Bridge at DPT. | 95.10 | 68.96 | 27.48% below | EL/WK/2536/269 dated 23/01/2020 | M/s. C.K. Electricals, | 23/01/2020 | 21/04/2020 | Shri Susil Chandra Nahak, Dy. CME | Work in progress. Proposal for extension is being processed. |
| 9. | Up-gradation of Power Supply &Electrical accessories of CISF Complex” CISF complex work | 73.85 | 58.38 | 20.34% | EL/WK/2508/270 dated 23/01/20 | M/s. C.K. Electricals, | 23/01/2020 | 22/07/2020 | Shri Susil Chandra Nahak, Dy. CME, | Work in Progress. Proposal for extension is being processed. |
| 10. | Revamping of 2 Nos. of TIL Make 25T ELL Crane No. 10 and 11 with latest version of VVVF Drives at Deendayal Port Trust. | 256.26 | 204.00 | 20.39% below | N.A. | M/s. Velox Automation Pvt. Ltd., Surat | N.A. | N.A. | Shri Dana Manohar, XEN(M), | WORK oRDER HAS BEEN ISSUED ON 14/08/2020. |
| 11. | Annual maintenance Contract of Liebherr make HMC:- LHM 550- S/N:- 141143 & LHM 550-S/N:- 141169 for the period of two year at Berth No. 13 inside Cargo Jetty area. | 484.16 | 312.00 | 35.56% below | N.A. | M/s. R. S. Electricals, Gandhidham | N.A. | N.A. | Shri Dana Manohar, XEN(M) | Work in Progress. |
| 12. | Supply, Installation, Testing & Commissioning of Power Transformer at 66KV Switchyard. | 122.96 | 127.65 | 3.82% above | LOI No. EL/AC/2537-I(e)/193 dated 07/03/2020 | M/s. Rajesh Power Services Pvt. Ltd, Ahmedabad | 07/03/2020 | 06/11/2020 | Shri Susil Chandra Nahak, Dy. CME | Work in progress. |
| 13. | Improving and reconditioning of 66/11KV Switchyard and 66/11KV Substation – Strengthening of 66/11KV Switchyard & Substation at inside Cargo Jetty Area thereof. | 239.46 | 224.41 | 6.28% Below | EL/WK/2543/412 dated 18/11/2019 | M/s. Onix Structure Pvt. Ltd, Rajkot | 18/11/2019 | 17/07/2020 | Shri Susil Chandra Nahak, Dy. CME | Work is in progress. Proposal for extension is being processed. |
| 14. | Restoration of power supply & Re-Conditioning of Electrical installation at Berth No 13th & 15th at inside Cargo jetty Area. | 259.76 | 186.36 | 28.26% below | EL/WK/2539/268 dated 23/01/2020 | M/s. C.K. Electricals, Surat | 23/01/2020 | 22/09/2020 | Shri Susil Chandra Nahak, Dy. CME | Contractor started the work and work in progress. Variation under process. |
| 15. | Refurbishing of Power Supply system & Lighting system of entire Oil Jetty area. | 252.52 | 174.44 | 30.92% below | EL/WK/2497/366 dated 04/02/2020 | M/s. C.K. Electricals, Surat | 06/02/2020 | 05/10/2020 | Shri D. K. Hazra, XEN(E) | Proposal for dropping the work has been processed. |
| 16. | Providing lighting arrangements on the stretch of 4.5 Kilometres area from Kutch Salt to West Gate – 2. | 247.81 | 134.59 | 45.68% below | EL/WK/2520/368 dated 28/05/2020 | M/s. RadadiyaParesh K, Rajkot | 28/05/2020 | 27/11/2020 | Shri D. K. Hazra, XEN(E) | Work in progress. |
| 17. | Up gradation of TS-IV, 7th Berth, Marine Un-loader, OLD NDA Area- Strengthening of down Stream 11KV Substations at Cargo Jetty Area. | 322.14 | 210.46 | 34.67% below | EL/WK/2542/368 dated 06/02/2020 | M/s. GPI Projects Pvt. Ltd, Ahmedabad | 06/02/2020 | 05/11/2020 | Shri Susil Chandra Nahak, Dy. CME | Work in progress. |
| 18. | Maintenance Contract for HT & LT Electrical Installations including substations,overhead Lines, Residential, Non-Residential, Hospital and School Buildings outside Cargo Jetty Area. | 398.48 | 357.89 | 10.18% below | EL/WK/2557/383 dated 10/02/2020 | M/s. Sterling & Wilson Ltd | 10/02/2020 | 09/02/2023 | Shri Susil Chandra Nahak, Dy. CME | Work in progress. |
| 19. | Supply, installation, Testing & Commissioning of 3 Nos. of 800 KVA, 11/0.433 KV Dry Type Resin Cast Transformers. | 60.61 | 48.51 | 19.96% below | EL/WK/2579-/401 dated 26/05/2020 | M/s. N.K. Industrial Services, G’dham | 26/05/2020 | 25/01/2021 | Shri Susil Chandra Nahak, Dy. CME | Work in progress. |
| 20. | Operation and Maintenance of 66/11kV and 11/0.433kV Substation inside Cargo Jetty area at DPT, Kandla for a period of two years. | 312.46 | 252.00 | 19.35% below | N.A. | M/s. Ascent Electri. Engineers, Jamnagar | N.A. | N.A. | Shri D. K. Hazra, XEN(E) | Work Order issued on 01/07/2020. |
| 21. | Annual Rate contract for supply & laying of HT/LT underground cables at inside and outside cargo jetty area. | 261.18 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME | Minutes regarding technical qualification of bidders finalized and proposal for opening of price bid is under process. |
| 22. | Supply, Installation, Testing & commissioning of 11 KV overhead line from new port colony to SIPC Area | 64.01 | 62.96 | 1.64% below | EL/WK/2625/544 dated 29/06/2020 | M/s. Onix Structure Pvt. Ltd, Rajkot | 29/06/2020 | 12/08/2020 | Shri Susil Chandra Nahak, Dy. CME | Work in progress. |
| 23. | Design, Supply, Installation, Erection, Testing and Commi-ssioning of DC Over Head/UG 11KV line for providing Power Supply to SIPC of DPT at Kandla | 533.38 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME | Minutes for approval of eligible bidder as per exemption certificate is under finalization. Technical evaluation under process. |
| 24. | Supply, Installation, Testing & Commissioning of five numbers 100 M.T. Capacity, Pit-less Type, fully electronic, Road Weighbridges with Five Years Comprehensive Maintenance contract after expiry of two years guarantee Period. | 91.15 | 74.85 | 17.88% below | ML/WK/3942/ 596 dated 16/12/2019 | M/s. Techno Scale Industries, Ahmedabad | 16/12/2019 | 120 days i.e. 13/04/2020 | Shri B.J. Solanki, SE(M) | Work order issued on 16/12/2019 but could not be commenced due to pending of Civil Structure work by C.E. department. |
| 25. | Supply, Installation, Testing &Commissioning of 04 Nos. Pit-less Type, Electronic in-motion RailwayWeigh bridges (15Kmph speed) of 140Mt capacities including comprehensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 150.79 | 147.67 | (-)2.07% Below | No.ML/WK/3916-II/738 dated 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., E-1, TVK Industrial Estate, Guindy, Chennai - 600032 | 05/01/2019 | 120 days, i.e. 04/05/2019 | Shri Rajesh Road (EIC) | Work delayed due to non-clearance from Civil Engg. Dept. Rail level may change. |
| 26. | Supply, Installation, Testing and Commissioning of 01 No. Kirloskar Make Vertical Turbine Fire Fighting Pump-Diesel Engine driven located at Cargo Jetty area No.01 through Authorized dealer of Kirloskar Brothers Ltd. | 140.00 | 142.80 | 2.00% above | ML/WK/3983/ 857 dated 12/02/2020 | M/s. Jay Project, Vadodara | 10/02/2020 | 180 days, i.e. 08/08/2020 | Shri B.J. Solanki, SE(M) | Work completed. |
| 27. | Comprehensive Annual Maintenance Contract for Port owned five nos. of Pilot Launches, one no. Survey Launch & two nos. of Mooring Launches for a period of two years. | 435.70 | -- | -- | -- | -- | -- | 12 Months | Shri Rajdev Kumar (EIC) | NIT uploaded on 29/07/2020. The Pre-bid Meeting scheduled on 07/08/2020 and the date of opening of online tender further scheduled on 10/09/2020. |
| 28. | Development, Operation and Maintenance of Container Terminal at Berth Nos. 11 and 12 at Kandla Port on PPP Mode | 15981.00 | 15981.00 | N.A. | MS/WK/4003-V/357 dated.19/2/2016 | M/s. Kandla International Container Terminal | 29/02/2016 | 15/02/2018 | Shri Susil Chandra Nahak, Dy. CME | LOI issued. Concession Agreement signed on 29/02/2016. Project fully commissioned on 15/02/2018. |
| 29. | Appointment of Consultant for the work of Mechanization of handling of Fertilizers at Kandla Port | 166.67 | N.A | N.A | N.A | N.A | N.A | N.A | Shri Susil Chandra Nahak, Dy. CME | Project mode transferred from EPC to PPP mode. So, the services of existing Transaction Advisor (TA) appointed for PPP projects is been rendered. |
| 30. | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 12094.14 | 12232.53 | 0.9% above | LoA issued vide MS/WK/4025-II/GIM-265 dated 31/03/2017 | M/s. RISHI Shipping, Gandhidham | 31/03/2017 | 31/03/2018 | Shri Rajesh Road, (EIC) | LoA issued on 31/03/2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect. |
| 31. | Mechanization of fertilizer handling facility at Berth No. 14, Deendayal Port | 27709.94 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME | As per the RoD held by Secretary (Shipping) at DPT on 02.01.2020, the project work for Mechanization of fertilizer handling at Berth No. 14 is to be carried out through PPP mode for which RFQ has been floated as approved by Board. |
| 32. | Appointment of Consultant for the work of Mechanization of handling of Coal (including pollution control measures) at Deendayal Port | 438.66 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Susil Chandra Nahak, Dy. CME | Tender for appointment of PMC discharged twice in Mechanical Engineering Department & the same has been taken over by the Traffic Department. |
| 33. | Procurement of Flameproof LED Light fitting for Oil Jetty, New Kandla. | 74.80 | 29.56 | 55.74% below | ST/PU/19048 (28) dated 16/09/2019 | M/s. Sherya Ex-tech Pvt Ltd, Ahmedabad &Sudhir Switchgear Pvt Ltd, Mumbai | 16/09/2019 | 90 Days | Shri Dana Manohar, XEN(M) | Material received on 18/12/2019 & 17/02/2020 |
| 34. | Procurement of Single Phase & Three Phase Digital Energy Meters and Meter Box | 53.59 | 40.93 | 23.63% below | ST/PU/19048 (49)/19/09 dated 05/03/2020 | M/s. Parishram Enterprises, Gandhinagar | 05/03/2020 | 90 Days | Shri Dana Manohar, XEN(M) | Material received. |
| 35. | Appointment of Consultant for carrying out environmental impact assessment and environmental management plan studies for development of another ship-repairing facility at Vadinar, to obtain statutory clearances from State authorities & MoEF&CC. | 52.02 | -- | -- | -- | -- | -- | 24 Months | Shri Shiva Mudliyar, EIC (DD) | The NIT uploaded on 06/07/2020. The Pre-bid Meeting was held on 17/07/2020. The online Technical Bids have been opened on 10/08/2020. Total 9 bids have been received an the same are under scrutiny. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 31.08.2020

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | -- | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), OOT, Vadinar. | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 2 | Providing, Operating and Maintaining of 1 No. 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of three years. Estimate:Rs.70,56,000/- | 0.71 Cr. | 0.699 Cr. | 0.899% below | -- | M/s. New Divya Tours & Travels, Jamnagar. | 05/01/2019 | 3 years | Shri D.K. Hazra, XEN (E&M) OOT, Vadinar. Shri Gopal Matha, JE (M) | Work Order issued vide No. OOT/ME/WK/RM/6004-I/658 dated 04/01/2019. |
| 3 | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | -- | M/s. Aeromarine Pvt. Ltd., Mumbai | 09/03/2020 | 3 years | Shri Narendra Naik, ME (Gr. I), OOT, Vadinar. | Work Order issued vide No. OOT/ME/WK/RM/8009/1947 dated 03/03/2020. |
| 4. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | -- | -- | -- | -- | -- | 18 months | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri M.A. Jadav, AXEN(C) | i) Technical Bid opened and 4 (four) parties submitted their offers and Technical Bid is under scrutiny. ii) Tender is discharged re-invited. Pre-Bid meeting held on 20/12/2019. iii) Reply to pre-bid query and corrigendum issued on 03/02/2020, Technical bid opened on 14/02/2020 and is under scrutiny. |
| 5 | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1,62 | 5.01 % above | -- | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri S.C. Vishwas AE (C) | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. |
| 6. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | 1.06 Cr. | 2.98% above | -- | M/s. Abhay Intelligence & Security Services, Vadodara. | 14/03/2020 | 2 years | Shri Vikash A.C. XEN (Civil), OOT, Vadinar Shri S.C. Vishwas AE (C) | Work Order issued vide No. OOT/C-WK/RM/4002/2001 dated 12/03/2020 |
| 7. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 | 6.01 % below | -- | M/s. Safari Travels, Balasinor | 07/03/2020 | 3 years | Shri D.K. Hara, XEN (E&M), OOT, Vadinar Shri Gopal Matha, JE (M) | Work Order issued vide No. OOT/ME/WK/6008/1795 dated 06/02/2020. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 31.08.2020

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agree ment No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Two years maintenance contract for railway track leading to Tuna from 0 to 11 Km DPT line (Take off point at 2.573 Km at GIM Yard to 13.54 Km including LC-1, LC-2. | 1.15 Cr. | 0.99 Cr. | 14% below | HW/WK/2391-I/14(A) dated 02/02/2019 | N/s. Dharti Construction | 11/02/2019 | 24 months | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 2. | Two years maintenance contract for Non-Residential Building inside Cargo Jetty area (Civil Work). (HD-09/19) | 0.88 Cr. | Part-A 0.58 Part-B 0.01 Neet 0.57 Cr. | 33.33% below | HW/WK/2384/100 dated 13/04/2020 | M/s. Shree Ganesh Construction, Anjar | 24/04/2020 | 24/04/2021 (12 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 3. | Modification, alternation and addition to Godown No. 34 inside cargo jetty area | 1.78 Cr. | 1.15 Cr. | 35.34% below | HW/WK/ 2407-I/55 dated 01/07/2019 | M/s. Mepabhai Mandan & Co. | 01/07/2019 | 29/02/2020 (8 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. 1st Extension granted from 01/03/2020 to 29/05/2020. Further extension processed for approval from 30/05/3030 to 07/08/2020. Variation No. 1 for next excess of 8.04% approved by the competent authority. |
| 4. | Two years maintenance contract for cleaning and sweeping of office building & surrounding outside at New Kandla. | 1.67 Cr. | 0.99 Cr. | 41.11% Below | HW/WK/ 2408 dated 30/07/2019 | M/s. Dhanjibhai K. Patel. | 30/07/2019 | 29/07/2021 (24 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 5. | Annual Maintenance contract of Fender inside cargo jetty area (HD-01/19) | 1.28 Cr. | 1.51 Cr. | 18.35% above | HW/WK/2375 dated 13/12/2019 | M/s. Patel Construction Co. | 13/12/2019 | 12/12/2020 (12 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 6. | Annual Maintenance contract for Godown inside cargo jetty area for two years(HD-03/19) | 1.96 Cr. | 1.28 Cr. | 34.44% below | HW/WK/2375/ 338 dated 13/12/2019 | M/s. Mepabhai Mandan & Co. | 13/12/2019 | 12/12/2021 (24 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. Anticipated variation 28% sent for approval. |
| 7. | Maintenance contract for quay and transit area inside cargo jetty area for two years (05/19) | 1.14 Cr. | 0.99 Cr. | 13.00% below | HW/WK/2402 -II/236 dated 19/09/2019 | M/s. Mahesh Construction, Adipur. | 18/09/2019 | 17/09/2021 (24 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 8. | Tree plantation near offices other buildings along roads etc. including two years maintenance contract at New Kandla (HD-06/19) | 0.96 Cr. | 0.72 Cr. | 25.06% | HW/WK/ 2380-I/99 dated 13/04/2020 | M/s. Dhanji K Patel, Anjar | 24/04/2020 | 23/04/2022 (24 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 9. | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla (HD-07/19). | 1.12 Cr. | 1.20 Cr. | 7.21% above | HW/WK/2379-III /332 dated 05/12/2019 | M/s. Patel Construction Co. | 18/12/2019 | 17/12/2019 (12 months) | Shri A.P. Trivedi, XEN(H) | Work in progress |
| 10. | Providing screen wall of M.S. Structure to protect West Gate-III office Building from dust (HD-08/19). | 0.78 Cr. | 0.75 Cr. | 5.01% below | HW/WK/ 2418/45 dated 06/02/2020 | M/. Viyuha Infrabuild, Adipur | 10/02/2020 | 09/08/2020 (6 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 11. | Housekeeping and cleaning of office building inside Cargo Jetty Area for 2 years (HD-10/19). | 0.54 Cr. | -- | -- | -- | -- | -- | -- | Shri A.P. Trivedi, XEN(H) | Tender discharged. |
| 12. | Two years maintenance contract for office building outside Port area (Civil Work) HD-02/19 | 0.89 Cr. | 0.64 Cr. | 27.27% below | HW/WK/ 2336-I/339 dated 13/12/2019 | M/s. Mohit Construction | 13/12/2019 | 12/12/2021 (24 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 13. | Improving the road network inside cargo jetty area. Providing RCC paving HD-12/19 | 8.01 Cr. | 5.05 Cr. | 39.02% | HW/WK/ 2401-I/62 dated 24/02/2020 | M/s. Patel Construction Co., Gandhidham. | 11/03/2020 | 10/03/2021 (12 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 14. | Improving the fendering arrangement inside cargo jetty area HD-14/19. | 2.85 Cr. | 3.54 Cr. | 24.39% above | EG/WK/ 11140/822 dated 06/04/2020 | M/s. Patel Construction Co., Gandhidham. | 15/06/2020 | 14/06/2021 12 months | Shri A.P. Trivedi, XEN(H) | Worker Order issued on 02/06/2020. |
| 15. | Development of equipment to remove cargo / solid waste periodically from road to maintain high standard of hygienic and to avoid pollution and contamination of cargo in Port area HD-15/19. | 1.34 Cr. | 0.64 Cr. | 52.31% below | EG/WK/1145/851 dated 16/07/2020 | M/s. Patel Construction Co., Gandhidham. | 05/08/2020 | 04/08/2020 | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 16. | Improving the road network inside cargo jetty area. Providing Asphalt paving (Stage-II) HD-16/19 | 7.34 Cr. | 5.78Cr. | 21.20% Below | EG/WK/ 11148/851 dated 29/04/2020 | M/s. Ravji Manji Soratia & Co. | 19/06/2020 | 18/06/2020 (12 months) | Shri A.P. Trivedi, XEN(H) | Work in progress |
| 17. | Up-gradation of open plot at Bunder Basin. HD-17/19 | 7.97 Cr. | 6.35 Cr. | 20.31% below | EG/WK/1143/828 dated 21/04/2020 | M/s. Krishna Construction. | 11/06/2020 | 10/02/2021 | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 18. | Development of equipment for cleaning of all toilet block inside Orit area to maintain high standard of hygienic and to avoid pollution . (HD-20/19) | 1.88 Cr. | 1.16 Cr. | 38.04% below | HW/WK/ 2428/104 dated 21/04/2020 | M/s. Patel Construction Co., Gandhidham. | 04/05/2020 | 03/05/2022 (24 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 19. | Improving the existing entry gates of cargo jetty construction of RCC fencing and RCC road for WG-II (Phase-VII) | 4.72 Cr. | 2.85 Cr. | 39.69% below | HW/WK/ 2419-I/68 dated 27/02/2020 | M/s. Patel Construction Co., Gandhidham. | 11/03/2020 | 10/03/2021 (12 months) | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 20. | AMC for weigh bridges (Civil Work) inside Cargo Jetty Area | 0.71 Cr. | NA | NA | NA | NA | NA | NA | Shri A.P. Trivedi, XEN(H) | Tender opened on 02/01/2020 and under process of Technical bid scrutiny. |
| 21. | Providing toilet block and drinking water facility in 66,40, 34 H area and on Berth No.13 & 15 in CJA under Swachh Bharat Abhiyan | 2.03 Cr. | 1.55 Cr. | 23.38% below | NA | M/s. Quality Constructions, Gandhidham. | NA | NA | Shri A.P. Trivedi, XEN(H) | Price Bid opened on 29/08/2020. |
| 22. | Providing portable container office at Berth No. 13 to 16 inside Cargo Jetty area. | 0.61 Cr. | 0.64 Cr. | 4.56% Above | NA | M/s. Sanjay K. Sorathiya & Co. | 24/07/2020 | 23/10/2020 | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 23. | AMC of Custom fencing wall and gates of Cargo Jetty and Bunder area. | 0.74 Cr. | NA | NA | NA | NA | NA | NA | Shri A.P. Trivedi, XEN(H) | TCN processed for prequalification of bidders. TCM under approval. |
| 24. | Upgrading the road network of 66 hectare. | 17.42 Cr. | 12.73 Cr. | 28.95% Below | NA | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd., Gandhidham. | NA | NA | Shri A.P. Trivedi, XEN(H) | Pre-Acceptance letter issued. |
| 25. | Maintenance contract for roads and RCC culverts inside CJA at New Kandla for 2 years. | 1.75 Cr. | NA | NA | NA | NA | NA | NA | Shri A.P. Trivedi, XEN(H) | Tender opened on 07/04/2020. Scrutiny completed and TCN processed. |
| 26. | Two years contract for cleaning of storm water drain inside Cargo Jetty area. | 0.80 Cr. | 0.42 | 47.81% below | EG/WK/1151/938 dated 09/07/2020 | M/s. Narayan Construction | 24/07/2020 | 23/07/2020 | Shri A.P. Trivedi, XEN(H) | Work in progress. |
| 27. | Development of plots, roads & SWD in 34 Ha area inside Cargo Jetty Area. | 57.08 Cr. | NA | NA | NA | NA | NA | NA | Shri A.P. Trivedi, XEN(H) | Technical bid opened on 02/06/2020. Bid scrutiny completed. TCN will be sent shortly. |
| 28. | Providing Screen wall surrounding the coal stacking yard inside Cargo Jetty Area of DPT | 18.63 Cr. | NA | NA | NA | NA | NA | NA | Shri A.P. Trivedi, XEN(H) | Technical bid opened on 09/06/2020. Bid scrutiny is under process. |
| 29 | Construction OF 3 NOS. Toilet Blocks on Central Road inside cargo jetty area at New Kandla (HD-12/20) | 1.40 Cr. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri A.P. Trivedi, XEN(H) | Technical bid opened on 24/07/2020. Bid Scrutiny under process. |
| 30. | Dredging in the Navigational Channel and alongside Cargo Berth / Oil Jetties at Kandla Port Trust (year 2017-20) Location at Kandla | 514.00 Cr. | 338.01 Cr. | 34.20% below | LOA No. EG/ WK/ 5226/ 257 dated 04/07/2017 WO No. MW/ WK/ 8274-V/5195A dated 24/07/2017 | M/s. Van Oord India Pvt. Ltd., Mumbai | 03/07/2017 | 36 months | M/s. AECOM India Pvt. Ltd., Haryana. Shri A.P. Trivedi, XEN(H&D) | Dredging Work is in progress by M/s. Van Oord India Pvt. Ltd., Mumbai. Extension of 3 months given vide letter No. HD/WK/2020/1069/828 dated 23/07/2020. |
| 31. | RFP for Service of Third Party Government Survey Agency for the Dredging at Kandla Port (2017-2020) | 3.63 Cr. | 2.33 Cr. | 35.73% Below | LOA No. EG/WK/ 5335/579 dated 24/11/2017 | M/s. Wapcos Ltd., Gurgaon-122015 Haryana | 29/11/2017 | 36 months | Shri A.P. Trivedi, XEN(H&D) | Work in progress. |
| 32. | Appointment of Project Management Consultant (PMC) for capital & maintenance dredging work of DPT from firms / consortiums empanelled consultants from dredging work (Class-A, Category-A) by Indian Ports Association, New Delhi. | 6.36 Cr. | 5.38 Cr. | 15.32% below | LOA No. EG/WK/6112 /333 dated 15/11/2019 | M/s. AECOM India Pvt. Ltd., Gurgaon | 25/11/2019 | 36 months | Shri A.P. Trivedi, XEN(H&D) | Work in progress. |
| 33. | Dredging in the Navigational Channel and alongside Cargo Berth / Oil Jetties at Deendayal Port Trust for the year 2020-23. Location at Kandla | 393.00 Cr | -- | -- | -- | -- | -- | -- | M/s. AECOM India Pvt. Ltd., Haryana. Shri A.P. Trivedi, XEN(H&D) | Shortfall documents called for from the bidders. |
| 34. | Replacement and revamping of pipeline network at Oil Jetty area, Kandla (i) Appointment of Technical Advisor for the preparation of Tender documents, Bid Process Managements and PMC Services. | -- N.A. | -- 4.15 Cr. | -- N.A. | -- PL/WK/8306Part-II/ Amendment/1626 dated 16/08/2019 | -- M/s. IIITM, Chennai. | -- 16/08/2019 | -- 24 months | Shri Rajendra Prasad SE (PL) | Work determined & Work Order issued to IITM. |
| 35. | S/R to fenders inside Oil Jetty Area | 0.81 Cr. (-) Credit part Rs.0.016 =0.80 | 0.82 Cr. (-) Credit part Rs.0.016 =0.80 | 1.17% above the net Est. cost & PMR | PL/WK/8329/107 dated 16/01/2019 | M/s. Patel Construction Co., Gandhidham. | 01/02/2019 (Scheduled) | 18 months | Shri Rajendra Prasad SE (PL) | Work is in progress. |
| 36. | Strengthening of Oil Jetty No. 3 at Old Kandla | 1.70 Cr. | 2.21 Cr. | 30.04 % above. | PL/WK/ 8318-II/519 dated 31/07/2019. | M/s. Patel Construction Co., Gandhidham. | 05/08/2019 | 04/08/2020 (12 months) | Shri Rajendra Prasad SE (PL) | Work is in progress. |
| 37. | S/R to fire fighting pipeline at Oil Jetty | 0.69 Cr. (-) Credit part Rs.0.09 Cr. =0.59 | 0.63 Cr. (-) Credit part Rs.0.11 Cr. =0.52 | 12.61% and 25.88% below the Est. cost & PMR respecti-vely. | PL/WL/8311/323 dated 26/02/2019 | M/s. Mepabhai Mandan & Co., Gandhidham. | 12/02/2019 (Scheduled) | 12 months | Shri Rajendra Prasad SE (PL) | Work is in progress. |
| 38. | AMC for the fire fighting pipeline and water supply lines inside Cargo Jetty at Kandla. | 0.61 Cr. (-) Credit part 0.002 =0.60 | 0.36 Cr. (-) Credit part 0.003 =0.35 | Indivi-dually 41.14% below Part-A and 20% above Part-B and overall 41.65% below. | PL/WK/8345/1233 dated 15/07/2019 | M/s. Mepabhai Mandan & Co., Gandhidham. | 02/07/2019 | 12 months | Shri Rajendra Prasad SE (PL) | Work is in progress. |
| 39. | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years. | 0.94 Cr. | 0.66 Cr. | 30.51% below | PL/WK/8358/1522 dated 20/11/2019. | M/s. Premji Kanji Sorathia | 20/11/2019 | 19/11/2021 (24 months) | Shri Rajendra Prasad SE (PL) | Work is in progress. |
| 40. | Strengthening of RCC custom fencing wall of Oil Jetty and Providing CCTV lighting arrangement at Old Kandla - Strengthening of RCC Custom Fencing Wall. | 1.12 Cr. Credit part 0.21 Cr. | Part-A 0.76 Cr. Part-B 0.01 Cr. | -- | --- | M/s. Rajput Infrastructure Company, Gandhidham. | -- | -- | Shri Rajendra Prasad SE (PL) | LOA issued on 26/08/2020. |
| 41. | Annual Maintenance Contract for the Buildings, Walkway, trestles, Fire Fighting, Pipelines, Garden inside and outside Oil Jetty area at Old Kandla | 1.29 Cr. Credit part 0.50 Cr. | -- | -- | --- | -- | -- | -- | Shri Rajendra Prasad SE (PL) | Tender Committee meeting is to be conducted. |
| 42. | Improving Storm Water drainage system at Old Kandla | 2.32 Cr. | -- | -- | --- | -- | -- | -- | Shri Rajendra Prasad SE (PL) | Technical evaluation under process. |
| 43. | Providing RCC drinking water tank | 1.52 Cr. | -- | -- | --- | -- | -- | -- | Shri Rajendra Prasad SE (PL) | Technical evaluation under process. |
| 44. | Improving existing Oil Jetty structures at Oil Jetty No. 1, 2, 4 | 8.20 Cr. | 8.08 Cr. | 1.55% below | Pl/WK/8421-I/2238 dated 10/06/2020 | M/s. Sarjan Construction Pvt. Ltd. | 20/06/2020 | 18 months | Shri Rajendra Prasad SE (PL) | Work commenced from 20/06/2020. |
| 45. | Annual Maintenance Contract for residential & Non-residential buildings at New Kandla | 0.66 Cr. | 0.60 Cr. | 9.00% below | RW/WK/7763-I/628 dated 27/02/2019 | M/s. Patel Construction Co., Gandhidham. | 11/03/2019 | 10/03/2020 | Shri Srinivas Rao, SE (R) | Work is in progress. Extension & Variation sent for approval. |
| 46. | AMC for Roads at Kandla 2018-19 | 0.89 Cr. | 0.64 Cr. | 27.53%below | RW/WK/7754-I/66 dated 16.9.2019 | M/s. Mepabhai Mandan & Co., Adipur | 17/09/2019 | 16/09/2020 | Shri Srinivas Rao, SE (R) | Work in progress |
| 47. | Construction of dust bins at New Port Colony, N.K. | 0.52 Cr. | 0.33 Cr. | 32.21% below | RW/WK/7757-I/121 dated 17.10.2019 | M/s. Viyuha Infrabuild, Gim | 01/11/2019 | 31/07/2020 | Shri Srinivas Rao, SE (R) | Work in progress. Extension & Variation sent for approval. |
| 48. | Maintenance Contract for cleaning of SWD along road sides for 2 years (J.N. road, link road, bye pass road & O/s CJA) at New Port Colony New Kandla (18-20) | 0.55 Cr. | 0.32 Cr. | 41.90% Below | RW/WK/7767-I/ dated 10/10/2019 | M/s. Vihat Const. Co., Adipur | 21/10/2019 | 22/10/2021 | Shri Srinivas Rao, SE (R) | Work in progress. |
| 49. | Providing service road from road leading W.G-1 to W.G-2 (Road leading to 13th to 16th cargo berth) | 3.41 Cr. | 2.27 Cr. | 33.44% below | RW/WK/7734-I/201 dated 27/12/2019 | M/s. MMC Projects (India) Pvt. Ltd., G'dham | 15/01/2020 | 14/07/2020 | Shri Srinivas Rao, SE (R) | Work in progress, Applied for extension |
| 50. | Maintenance Contract for Sanitation of New Port Colony New Kandla for year 19-20. | 0.98 Cr. | 0.66 Cr. | 32.40% below | RW/WK/7784-I/45 dated 26.8.2019 | M/s. Vihat Const. Co., G'dham | 02/09/2019 | 01/09/2021 | Shri Srinivas Rao, SE (R) | Work in progress |
| 51. | Up-gradation of existing road & surrounding area at CISF complex. | 0.69 Cr. | 0.46 Cr. | 33.57% below | RW/WK/7781-I/126 dated 27.10.2019 | M/s. Mepabhai Mandan & Co., Adipur | 04/11/2019 | 03/05/2020 | Shri Srinivas Rao, SE (R) | Work in progress. Applied for extension |
| 52 | Upgradation of road from West Gate-I to road leading to West Gate-II | 0.84 Cr. | 0.52 Cr. | 38.10% below | RW/WK/7753-I/410 dated 18.05.2020 | M/s. Shree Ganesh Construction | 01/06/2020 | 31/01/2021 | Shri Srinivas Rao, SE (R) | Work in progress |
| 53. | Widening of existing road from IFFCO Gate to Oil Jetty entry Gate at Old Kandla | 0.84 Cr. | 0.61 Cr. | 27.56% below | RW/WK/ 7755-I/163 dated 28/11/2019 | M/s. Patel Construction Co., Gandhidham. | 11/12/2019 | 10/06/2020 | Shri Srinivas Rao, SE (R) | Final bill passed in August, 2020. |
| 54. | Resurfacing of existing road from NH Junction to Bye pass - KK Road Junction. | 8.19 Cr. | _ | _ | _ | _ | _ | _ | Shri Srinivas Rao, SE (R) | Price Bid opened on 27/08/2020. |
| 55. | Maintenance Contract for Residential & Non-Residential Building at Port Colony, New Kandla for 2 years. | 1.59 Cr. | 1.06 Cr. | 33.30% below | _ | M/s. Rajput Infrastructure Co., Gandhidham. | _ | _ | Shri Srinivas Rao, SE (R) | Letter of Acceptance issued on 27/08/2020. |
| 56. | AMC for cleaning & house keeping works of DPT Hospital and isolation ward at Gopalpuri and Kandla (For two years) | 0.65 Cr. | 0.46 Cr. | 29.01% Below | TW/WK/ 7735-I/192 dated 25/10/2018 | M/s. Praful A. Parmar | 10/11/2018 | 09/11/2020 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 57. | Construction of Dr. Babsheb Ambedker Convention Centre, Gandhidham. | 33.08 Cr. | 28.83 Cr. | 12.84% below | TW/WK/ 7715-I/410 dated 07/02/2019 | M/s. Dipesh Construction Co., Anjar | 15/02/2019 | 14/02/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 58. | R/M of Arboriculture / Horticulture work in public building at Gopalpuri Port Colony for year 2018-19 | 0.60 Cr. | 0.40 Cr. | 33.30% below | TW/WK/ 7721-II/640 dated 12/06/2019 | M/s. Mahesh Construction | 12/06/2019 | 11/06/2020 | Shri M.T. Gohel, XEN (TD) | Processed for extension of time limit. |
| 59. | AMC for Gardens at Shaktinagar & A.O Building for the period of 2 years | 0.61 Cr. | 0.41 Cr. | 34.51% below | TW/WK/ 7734-/174 dated 02/11/2019 | M/s. Praful A. Parmar | 01/08/2019 | 31/07/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 60. | Modernization of AO Building at Gandhidham Stage -II | 1.26 Cr. | 0.89 | 29.60% below | TW/WK 77717-I/345 dated 20/05/2020 | M/s. Pars Enterprise, Gandhidham. | 03/06/2020 | 02/06/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 61. | AMC for Sport Complex at Gopalpuri for the period of 2 years. | 0.65 Cr. | 0.42 Cr. | 35.35% | TW/WK 7764-I/371 dated 14/04/2020 | M/s. Patel Construction Co. | 16/04/2020 | 15/04/2022 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 62. | AMC for Residential Building of Port Colony, Gopalpuri and AO Building at Gandhidham. | 1.15 Cr. | 0.68 Cr. | 40.95% below | TW/WK 7773/342 dated 13/03/2020 | M/s. Rajput Infrastructure, Gandhidham. | 13/03/2020 | 12/03/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 63. | AMC for Whitewashing, Distempering & Painting to Resi. & NRB at Gopalpuri. KDLB, Gandhidham & Adipur for the year 2019-20. | 0.92 Cr. | 0.48 Cr. | 48.00% below | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) | Tender discharged. Revised estimates and DTP are under process. |
| 64. | Maintenance of Public Health & Underground drainage at Gopalpuri Port Colony & KDLB Colony for the period of 2 years. | 2.52 Cr. | 1.33 Cr. | 47.12% below | TW/WK 7757-I/229 dated 05/12/2019 | M/s. Patel Cons. Co., Gandhidham. | 09/12/2019 | 08/12/2021 | Shri M.T. Gohel, XEN (TD) | Work in progress. |
| 65. | Re-surfacing of Internal Road of Port Colony, Gopalpuri | 1.95 Cr. | 1.46 Cr. | 25.15% below | -- | M/s. Premji Kanji Sorathiya, Gandhidham. | -- | -- | Shri M.T. Gohel, XEN (TD) | Pre-Acceptance issued. Work order will be issued after monsoon |
| 66. | Strengthening of Canteen, Sub-station and Store at AO Building at Gandhidham. | 0.61 Cr. | 0.52 Cr. | 15.30% below | TW/WK/ 7769-I/319 dated 02/05/2020 | M/s. Santhoshi Builders. | 12/05/2020 | 03/02/2021 | Shri K.J. Todermal SE (C) | Work in progress. |
| 67. | Providing interlocking paving on both sides shoulders of roads of Gopalpuri | 1.45 Cr. | -- | -- | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) | Called for shortfall documents. |
| 68. | Providing safely measures - providing compound wall and SWD in Gopalpuri Colony, Gandhidham. | 2.19 Cr. | -- | -- | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) | Revised pre-scrutiny submitted. |
| 69. | Modernization of Staff Club / Officer's Club at Gopalpuri | 2.15 Cr. | 1.82 Cr. | 15.57% below | -- | M/s. Dhanjibhai K. Patel, Anjar. | -- | -- | Shri M.T. Gohel, XEN (TD) | Price Bid opened on 25/08/2020 & submitted for TCM. |
| 70. | R/M of Arboriculture / Horticulture work in public building at Gopalpuri and KDLB Colony for the year 2020-22. | 2.15 Cr. | -- | -- | -- | -- | -- | -- | Shri M.T. Gohel, XEN (TD) | Technical bid opened on 10/07/2020 & called for shortfall documents. |
| 71. | Improvement of OSG Berth No. 11 | 8.70 Cr. | 6.82 Cr. | 21.53% below | CN-1/WK/ 2262-II/75(G) dated 19/02/2020 | M/s. Patel Construction Co., Gandhidham | 24/02/2020 | 23/12/2020 10 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 72. | Development of backup of Berth No. 12 | 7.68 Cr. | 5.82 Cr. | 24.29% below | CN/WK/ 2266-II dated 03/03/2020 | M/s. Patel Construction Co., Gandhidham | 15/03/2020 | 14/01/2021 10 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 73. | Construction of 14th & 16th Berth for Multi Purpose Cargo - Additional Piled Platform. | 83.05 Cr. | 64.03 Cr. | 22.89% below | CN/WK/ 2243 & 44-III/95(G) dated 06/06/2020 | M/s. Vijay Mistry Construction Pvt. Ltd., Ahmedabad. | 22/06/2020 | 11 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 74. | Retrofitting of existing Cargo Berth No. 7 (Panel 51 to 59) | 65.05 Cr. | 49.57 Cr. | 23.79% below | CN/WK/ 2273-IV/ Works/108 (G) dated 31/07/2020 | M/s. BMS-Marymatha JV., Surat. | 14/08/2020 | 11 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 75. | Construction of 16th Berth for Multi-purpose Cargo at Kandla (Other than Liquid - Improvement to Access Road for Serving to 15th and 16th Berths | 3.91 Cr. | 3.94 Cr. | 0.65% above | CN-I/WK/2244/Work dated 30/06/2020 | M/s. Dhanjibhai K. Patel, Anjar | -- | 6 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 76. | Mechanization of Fertilizer handling facility at Berth No. 14 - Development of additional Back-up area | 8.15 Cr. | 5.46 Cr. | 33.05% below | CN-I/WK/2252-IV/Works/ 106(G) dated 22/07/2020 | M/s. M.G. Bhawnani, Gandhidham. | 23/07/2020 | 8 months | Shri Srinivas Rao, SE (C-I) | Work in progress. |
| 77. | Upgradation and strengthening of existing road from WG 2 to 16th Cargo Berth - Phase -I | 69.18 | -- | -- | -- | -- | -- | -- | Shri Srinivas Rao, SE (C-I) | Tender opened on 18/08/2020. TCM for preliminary bid will be held on 01/09/2020. |
| 78. | Construction of Oil Jetty No.7 at Kandla | 44.59 Cr. | 42.40 Cr. | (-) 4.93% below | CN-I/WK/ 1553/72 dated 26/02/2020 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | 26/02/2020 | 18 months 25/08/2022 | Shri Rajendra Prasad SE (P) | The order for commencement of work order issued vide No. CN/WK/1553/72 dated 26/02/2020 to M/s. Kargwal Constructions Pvt. Ltd., Mumbai. |
| 79. | Construction of Oil Jetty No:8 at Old Kandla | 110.84 Cr. | 99.08 Cr. | (-) 6.085% Below | No. EG/WK/ 9105/75 dated 28.02.2019 | M/s.Kargwal Constructions Pvt. Ltd., Mumbai | -- | _ | Shri Rajendra Prasad SE (P) | The work is awarded to M/s. Kargwal KM Joint Venture, Mumbai and approval letter No.EG/ WK/ 9105/75 dated 28/02/19. The work shall be started after receipt of environment clearance from the concerned authorities. |
| 80. | Providing Legal, Technical and Financial transactions for all ongoing and future proposals of DPT on PPP / Captive Mode for the period of two years and further extendable for one year. | 3.27 Cr. | 1.98 Cr. | 39.25% below | EW/WK/ 4759/TA/79 dated 10/10/2019 | M/s. Infrastructure Development (Karnataka) Corpn. Ltd. (1deck) | 14/10/2019 as per work order | 2 years and further extendable for 1 year. | Shri Srinivas Rao, SE (D) | Work in progress. |
| 81. | Strengthening of existing Environmental Management Cell at DPT. Appointment of Experts for two year and further extendable for one year. | 1.23 Cr. | -- | -- | -- | -- | -- | -- | Shri Srinivas Rao, SE (D) | The Tender Committee meeting was held on 29/08/2020 for finalization of pre-qualification of bidder and minutes of the same is awaited. |
| 82. | Preparing and monitoring of Environmental Management Plan for DPT at Kandla. | 4.08 Cr. | 2.52 Cr. | 38.17% below | EW/WK/EMC/11023/ 2011-IV dated 05/12/2019 | M/s. Detox Corporation Pvt. Ltd. | 02/03/2020 | 01/03/2023 3 years. | Shri Srinivas Rao, SE (D) | Work in progress. |
| 83. | Third Party inspection and quality assurance for the works costing more that Rs. 1.00 Cr. of Civil Engineering Department of DPT. | 1.35 Cr. | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad, SE (D) | Technical bid has been opened and comparative statement submitted on 23/09/2019 for pre-audit report. |
| 84. | Appointment of Independent Engineer for the work of "Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis. | 1.44 Cr. | 1.18 Cr. | (-) 17.89% | EW/WK/ 4823/(IE) / 109 dated 22/10/2019 | M/s. Rina Services, s.p.A., Mumbai. | 01/11/2019 | 42 months | Shri Srinivas Rao, SE (D) | Work in progress. |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No | Name of work & location | Reserve price Per sq. mtr./ year | Premium received over and above reserve price during e-auction (per sq. mtr. / per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 84. | e-tender cum e-auction for the allotment of land admeasuring 70 Acres for the purpose of Liquid Storage Tanks (including Structures) on 30 years lease and on as is where is basis at Kandla. | Rs. 659.79 per sq. m./ per annum | -- | -- | -- | -- | ShriI A.P. Trivedi, XEN. (Kandla Land) | Tender is discharged due to no response. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6 .	MARINE DEPARTMENT							                                                                                      AS ON 31.08.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hiring of 04 Nos. of 50/60 tonn Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 308.00 Cr. | 19.89% below Estimated Cost - OSL Ltd. 20.08% below Estimated Cost - KNK Ship | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. T. Srinivas, Deputy Conservator Shri Sunilkumar, Flotilla Supdt. | Board vide Resolution No. 56 in its meeting held on 12.08.2016 have approved to award the work to contractors. W.O. has been issued on 03/10/2016 & 22/09/2016. Integrity Pact Agreement signed. |
| 2 | Hiring of 01 Nos. of 60 T Bollard Pull Tug for a period of Ten years extendable further by one year on time charter basis. | 9.00 Cr. per year | 90.03 Cr. | 23.18% below estimated cost | 31/05/2018 | M/s. Polestar Maritime Ltd. Mumbai | 30/05/2018 | 29/05/2028 | Capt. T. Srinivas COM, OOT, Vadinar. Shri Nayak, M.E. Gr.I | LOA issued on 28/03/2018. Work Order issued on 11/05/2018. Integrity Pact Agreement signed. |
| 3 | Supply, installation and commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | 30.11 Cr. | -- | M/s. Electronics Corporation of India Ltd., Hyderabad | 31/01/2019 | 24 months of supply installation & commissioning. AMC 10 years after installation | Capt. T. Srinivas, Deputy Conservator. Shri Sunilkumar, Flotilla Supdt. | LOA issued on 06/10/2018. Work Order issued on 31/01/2019. Integrity Pact Agreement signed. |
| 4 | Conversion of Pilot Launch ML Karishma as Dumb Barge. | 1.16 | 0.85 | 27% below | Executed on 05/08/2019 | M/s. SSR Marine Services Pvt. Ltd. Mumbai. | 01/08/2019 | 8 months 31/03/2020 | Capt. T. Srinivas, Deputy Conservator. Shri Sunilkumar, Flotilla Supdt. | LOA issued on 27/05/2018. Work Order issued on 30/07/2019. Integrity Pact Agreement signed. |
| 5. | Hiring of 3 Nos. 60T Bollard Pull Tug ( 2 Nos. for Vadinar & 1 No. for Kandla) on Charter / Rate per day for the period of 10 years extendable further by one year. | 8.80 Cr. Per Tug Per Year | 352.1 Cr. | 9.17% below estimate of KNK Ship Ltd. 7.42% below estimate of OSL | Executed on 06/01/2020 Executed on 06/01/2020 | M/s. KNK Ship Management, Mumbai M/s. Ocean Sparkle Ltd., Hyderabad. | 20/03/2020 20/12/2019 | 10 years. | Capt. T. Srinivas COM, OOT, Vadinar. | LOA issued on 28/03/2018 Work Order issued on 11/05/2018 LOA issued on 28/03/2018 Work Order issued on 11/05/2018 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 31.08.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of brand new make and model of 2018 on "monthly hire basis" and made and model not earlier than1st January, 2017 on "as and when required basis" diesel vehicles to DPT for a period of 03 years | 8.86 Cr. | 8.23 Cr. | 4.34% Below | Executed. | M/s. Shree Ganesh Travels, Mumdra | 01/01/2019 | 30/06/2022 | Shri Piyush Parag, Law Officer.. | Work in progress. |
| 2. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	MEDICAL DEPARTMENT										                                            AS ON 31.08.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 7.80 Cr. | Party offered 20% discount on the monthly bill amount. | 20% discount on the monthly bill amount. | MH/SP/11/ 2016-17 dated 03/10/2017 | M/s. Mars Remedies, Jamnagar | 25/10/2017 | 3 years extendable for six months on mutual consent on same discount terms and conditions. | Dr. (Mrs.) K. Gandhi Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	TRAFFIC DEPARTMENT											                	AS ON 31.08.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N I L |  |  |  |  |  |  |  |  |  |  |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

9.	FINANCE DEPARTMENT										                                     AS ON 31.08.2020

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |  |  |  |  |  |  |  |  |  |  |

*****