DEENDAYAL PORT TRUST

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 30.09.2022

| Sr. No. | Name of work and location | Estimated cost (Rs.) in lakhs | Tendered Cost (Rs.) in lakhs | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 1 | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 15570.46 | 14446.38 9685.90 towards capital cost &4760.48 towards O&M Charges. | 7.22 Below | EL/WK/2491/1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri D.K.Hazra, XEN (E) | Comprehensive A.M.C. work in progress. |
| 2 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 12094.14 | 12232.53 | 0.9% above the estimated cost | LoA issued vide MS/WK/4025-II/GIM-265 dtd. 31.03.2017 | M/s. RISHI Shipping, Gandhidham | 31/03/2017 | 10/07/2026 | Shri Rajesh Roat, (EIC) | LoA issued on 31.03.2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect upto10/07/2026. |
| 3 | Design, Manufacture, Supply Erection, Testing, Commissioning &Operation of 02 Nos .of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 9181.77 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit(LC) i.e., 10/08/2017 | 06/05/2023 | Shri Dana Manohar, XEN(M),DPT | CAMC work in progress. |
| 4 | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 8181.98 | 6359.61 | 18.91 Below | EL/WK/2472/480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Comm’ned on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri D.K. Hazra, XEN(E) | Comprehensive A.M.C. work in progress. |
| 5 | Revamping and upgradation of Fire fighting system and associated facilities at Oil jetty area- Task-I: SITC of water pump / water pumping system including AMC of 5 years. | 3377.00 (3701.80 with credit item of 324.80 ) | Net Rs. 3863.77[i.e. Part A (EPC(SITC) Rs. 3956.32 [i.e. Rs. 3967.32- (minus) Rs. 11.00 discount offered in negotiation] (plus) AMC of 5 years Rs. 99.45 (minus) Part B : Credit item : Rs. 192.00] | 14.41 % Above | W.O. ML/WK/4052(Re-tender)/ 343 dated 29/07/2022 | M/s. Jay Project, Vadodara | 29.8.2022 | 28/08/2023 for SITC work & 28/08/2028 for AMC Work | Shri Mani Pushpak Sethi Superintending | Work in progress. |
|  | Task-II: SITC Firefighting system & associated facilities alongwith Pipeline, civil structure etc. including AMC for a period of 5 Years | 4954.52 | 4499.99 | 9.17% Below | W.O. ML/WK/4058/ 350 dated 01/09/2022 | M/s. Patel Construction Co., Gandhidham | 01.9.2022 | 28/02/2024 for SITC work & 31/08/2028 for AMC Work | Shri Manipuspak Sethi, Superintending Engineer (M) | Work in Progress |
| 6 | Design, Supply, Installation, Testing & Commissioning of Firefighting system and associated facilities including Operation &Maintenance for a period of five years as per OISD-156 at Oil Jetty No. 08, Kandla, of Deendayal Port Authority ( EPC Contact) | 6362.32 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 18/10/2022 |
| 7 | Supply, installation, testing & commissioning of Sprinkling System for coal dust suppression in 34-hectare coal yard with five Years Operation & Comprehensive Maintenance contract. | 2811.33 | 2447.98 | 12.92% Below | MS/WK/4046-I/GIM/592 dated 18/02/2022 | M/s Omkar Enterprise, Ahmedabad | 18/02/2022 | 17/02/2023 for SITC work & 17/02/2028 of O&M work | Shri Mani Pushpak Sethi Superintending Engineer (M) | Work in progress. |
| 8 | Design, Supply, installation, testing & commissioning along with Comprehensive Operation & Maintenance for a period of Five Years of 02 Nos Column Type Vessel access telescopic gangway system at Oil Jetty No. 07 and 08 of DPA | 2283.27 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 03/10/2022 |
| 9 | Design, Supply, Installation, Testing, Commissioning of Firefighting facilities as per OISD–156 including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT. | 1534.34 | 1684.06 | 9.76% above | Work Order: MS/WK/4052/Gim-94 Dated 30.08.2022 | M/s. Sterling And Wilson Pvt. Lltd. | 30/08/2022 | 29/01/2023 for SITC work & 29/08/2028 for O&M Work. | Shri Aman Imran B. AXEN(M) | Work in Progress |
| 10 | Outsourcing of 02 Nos. each Truck Mounted Mist Cannon system, and, Truck Mounted Road Sweeper system, along with comprehensive operation & maintenance, for the period of three years at DPT. | 892.73 | 1018.80 | 14.12% above | MS/WK/4047/GIM-542 Dated 21/12/2021 | M/s Sambhav Corporation, Ahmedabad | 23/12/2021 | 22/12/2024 | Shri Mani Pushpak Sethi Superintending Engineer (M) | Work in Progress |
| 11 | Operation and Maintenance contract of industrial light at cargo handling area, open plots, jetty area, godowns, street lighting connecting to port gates including maintenance of 11/0.433 KV substation inside cargo jetty area from zero panel to berth no. 10 and 13th to 16th berth. | 851.05 | 529.45 | 30.39% | Work Order No. EL/AC/2709/2092 dated 05.7.2022 | M/s. Daxraj Electricals | 05.07.2022 | 04.07.2024 | Shri D. K. Hazra XEN (E) | AMC in progress |
| 12 | Operation & Maintenance Contract of 2 Nos. Liebherr make LHM 550 model Harbour Mobile Cranes along with 03 nos. Grabs inside cargo jetty area for a period of Two years | 819.90 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of submission on 14/10/2022 |
| 13 | Maintenance contract of 03 nos. 25T and 02 nos. 16 T capacity MB# crane wharf cranes, alongwith grabs for a period of 2 years at inside cargo jetty area. | 742.00 | Rs. 704.89 | 5.00% below | LOI No. EL/WK/2691/947 dated 25.02.2022 | M/s. R. S. Electricals, Gandhidham | 16/02/2022 | 15/02/2024 | Shri Dana Manohar, XEN(M) | AMC in progress |
| 14 | Supply, installation, testing & commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) unit, integral capstan and remote control type including Operation & Maintenance for five years at Oil Jetty No 08 of DPA | 689.40 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 10/10/2022 |
| 15 | Supply, installation, testing and commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) units, integral capstan and remote control type including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT | 621.11 | 549.60 | 11.51% Below | MS/WK/4051/Gim-64 dated 04/07/2022 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 04/07/2022 | 03/11/2022 for SITC work & 03/11/2027 for O & M work | Shri Aman Imran B., AXEN (M) | Work in progress |
| 16 | Maintenance contract of 2 Nos. ITALGRU make Harbour Mobile Crane of 63T capacity along with 6 nos. of grabs and comprehensive maintenance of Hydraulic (suspension and winch) pumps inside cargo jetty area for period of two years. | 570.00 | 432.00 | 24.21% | LOI No. EL/AC/2702/650dated 05-01-2022 | M/s. Italgru India Pvt. Ltd., New Delhi | 01/01/2023 | 31/12/2023 | Shri Dana Manohar, XEN(M), Deendayal Port Trust | AMC in progress |
| 17 | Design, Supply, Installation, Erection, Testing and Commissioning of DC Over Head/UG 11KV line for providing Power Supply to SIPC of DPT at Kandla. | 533.38 | 429.39 | 19.50% below | EL/WK/2613/4497 dated 05.02.21 | M/s.TechnisysEng.Pvt. Ltd, Ahmedabad | 05/02/2021 | Extension upto 15/09/2022 | Shri D.K.Hazra, XEN(E) | Work in Progress |
| 18 | Annual maintenance Contract of Liebherr make HMC:- LHM 550- S/N:- 141143 & LHM 550-S/N:- 141169 for the period of two year at Berth No. 13 inside Cargo Jetty area. | 484.16 | 312.00 | 35.56% below | EL/WK/2553/671 dated 20.07.2020 | M/s. R.S. Electricals, Gandhidham | 20/07/2020 | 19/07/2022 Provision extension upto 19/02/2023 under process for approval. | Shri Dana Manohar, XEN(M), | AMC in progress |
| 19 | Comprehensive Annual Maintenance Contract for Port owned five nos. of Pilot Launches, one no. Survey Launch & two nos. of Mooring Launches for a period of two years. | 435.70 | 349.40 | 19.81% below | W.O. No. ML/WK/3992/97 dated 18.03.2021 | M/s. SSR Marine Services Pvt. Ltd., Thane | 18/03/2021 | 17/03/2023 | Shri Rajdeo Marine Engineer Gr.I | Work in Progress. |
| 20 | Comprehensive AMC of Mech works and equipment | 431.40 | 411.60 | 4.59% Below | MS/WK/4048 Dated 14/01/2022 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 15/01/2022 | 14/01/2027 | Shri Aman Imran B. AXEN (M) | Work in progress. |
| 21 | Maintenance contract of 3 Nos. 25T capacity 4 rope TIL make ELL cranes along with Grabs at Berth No. 10 at Inside Cargo Jetty area for a period of 2 years | 412.92 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of submission on 14/10/2022 |
| 22 | Supply, Installation, Testing and Commissioning of High Mast Lighting Tower at Berth No. 14. | 401.08 | 277.75 | 30.75% | EL/WK/2655-work/745 dated 27-01-2022 | M/s. Vishal Electricals, B-4, Hans Plaza, Ambedkar Road, Ghaziabad 201001 | 27/01/2022 | 26/11/2022 | Shri Chitrang Vyas, AXEN(E) | Work in progress. |
| 23 | Comprehensive Annual Maintenance Contract for Channel Marking, Dumping and Mooring Buoys in the Kandla Channel along with operation & Maintenance of Heave up Barge Bhimsen for a period of three years. | 400.50 | Rs. 367.77 | 8.17% Below | W.O. ML/WK/4040/ 336 dated 01/08/2022 | M/s. Seacrafts Industries (P) Ltd., | 06.8.2022 | 05.08.2025 | Shri Rajdeo Kumar, Marine Engineer Gr.I | Work in progress. |
| 24 | Maintenance Contract for HT & LT Electrical, installation including substations, overhead Lines, Residential, Non-Residential, Hospital and School Buildings outside Cargo Jetty Area. | 398.48 | 357.89 | 10.18% below | EL/WK/2557/383 Dated 10.02.2020 | M/s. Sterling & Wilson Ltd | 10/02/2020 | 09/02/2023 | Shri D.K.Hazra, XEN(E) | AMC is in progress. |
| 25 | Maintenance Contract of 3 Nos. ELL Wharf Cranes of 25T capacity 4 Rope of M/s. TIL make alongwith Grab inside Cargo Jetty Area for a period of 2 years. | 360.00 | 394.20 | 9.5% above | EL/WK/2594/4050 dated 19.11.2020 LOI No. EL/AC/2594(a)/4157 dt. 05.11.2020 | M/s. R.S. Electricals, Gandhidham | 05/11/2020 | 04/11/2022 | Shri Dana Manohar, XEN(M), | AMC in progress. |
| 26 | Annual Rate contract for supply & laying of HT/LT underground cables at inside and outside cargo jetty area. | 261.18 | 232.43 | 11% below | EL/WK/2608/1295 dated 05-04-21 | M/s. Onix Structure Pvt. Ltd, Rajkot | 05/04/2021 | 04/04/2023 | Shri D.K.Hazra, XEN(E) | ARC is in progress. |
| 27 | Strengthening of overhead line from thermal to port power house and oil jetty DPA, Kandla. | 239.33 | Rs.179.10 | 25.17% below | LOI No. EL/AC/2686-TP-1067 dated 23-4-22 issued | M/s. NK Industrial Services, Gandhidham | 14/07/2022 | 13/12/2022 | Shri DK Hazra, XEN(E) | Work in progress. |
| 28 | Comprehensive Annual Maintenance Contract for 08 Nos. of weighbridges at Deendayal Port Premises, Kandla for the period of three Years | 196.00 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 20/10/2022 |
| 29 | Major Repair Work of Heave Up Barge Bhimsen. | 166.77 | 156.07 | 6.41% below | ML/WK/4020-I(d)/156 dated 01/06/2022 | M/s. Patel Construction Co., Gandhidham | 01/06/2022 | 30/09/2022 | Shri Rajdeo, Marine Engineer Gr.I | Work in progress. |
| 30 | Providing power supply from 11 KV overhead line to 7th Oil Jetty and Jetty illumination at Kandla | 157.84 | 129.06 | 18.23 % (-) | LOI No. EL/AC/2752/3037 dated 13.07.2022 | M/s. NK Industrial Services, Gandhidham | 23/07/2022 | 22/10/2022 | Shri.D.K. Hazra XEN (E) | Work in progress. |
| 31 | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhi-dham Area for period of three years. | 154.92 | 139.22 | 10.14% Below | DD/WK/4309/338 dated 04.08.2021 | M/s. Inspection & Engineering Services, Ahmedabad | 04/08/2021 | 03/08/2024 | Shri Rajesh Roat E.I.C.(DD) | Work in Progress. |
| 32 | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weighbridges (15Kmph speed) of 140Mt capacities including compre-hensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 150.79 | 147.67 | 2.07% below | W.O. No.ML/WK/3916-II/738 Dtd. 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., E-1, TVK Industrial Estate, Guindy, Chennai - 600032 | 05/01/2019 | 17/12/2028 | Shri Rajesh Roat, E.I.C. (Railway In-motion weigh Bridge) | Work Completed on 18/12/2021. The weighbridges installed are under guarantee period of two years under CAMC |
| 33 | Replacement of existing feeder pillar of High Mast & Lattice Towers with FRP Feeder Pillar | 109.59 | 107.97 | 44.99% below | EL/WK/1948/1253 DT. 26.03.21 | M/s.Rajdeep Electricals Pvt. Ltd, G’dham | 31/03/2021 | 22/08/2022 provisional extension | Shri Chitrang Vyas, AXEN(E) | Work is in progress. |
| 34 | Procurement of 02 Nos. of 100 MT & above capacity tyre mounted electric & diesel driven (DUO) HMCs with operation & comprehensive AMC (CAMC) of three years after free CAMC of two years | 96.11 Cr. | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of submission on 21/10/2022 |
| 35 | Sell of renewable power generated from DPT’s 14.7 MW wind power plant on Medium Term Open Access basis through tariff based competitive bidding through auction. | Rs. 4.26 per unit | Rs. 4.27per unit | - | LOI No. EL/C/2688/1158, dated 10.11.2021 | M/s. UPL Ltd. GIDC Jhagadia- Bharuch | 29/12/2021 | 29/12/2022 | Shri D.K.Hazra, XEN(E) | MTOA has been extended with GETCO on 29/12/2021 and valid upto 29/12/2022. |
| 36 | Operation and maintenance for operation and maintenance of 66 KV substation. | Not Applicable | 100.00 Per Year | Not Applicable | EL/WK/2736/3043 dated 14/07/2022 | M/s. PTC India Ltd., New Delhi | 12/08/2022 | 11/08/2024 | Shri D.K. Hazra XEN (E) | Work in progress. |
| 37 | Grant of license for Supply, Installation, Commissioning, Operation and Maintenance of 2 Nos. of 100 or above owned / hired / leased Mobile Harbour Cranes at Berth No.13 to 16 inside Deendayal Port for a period of 5 years, extendable on the basis of condition survey and performance on mutually agreed consent for handling the cargo on common user basis | Tender is based on revenue sharing | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of submission on 19/10/2022 |
| 38 | Build, Operate and Maintain of 10 nos. of 120 T capacity each Automated road weighbridges on Revenue Sharing basis at DPA for a period of 10 years and buy–back of 10 nos. of existing Road weighbridges of DPA | Tender is based on revenue sharing | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 11/10/2022 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 30.09.2022

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | 49.32 Cr. | 6.62% below | No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. | M/s. Parsh Construction and Foundations Pvt. Ltd., Mumbai | 26/03/2021 | 18 months | Shri Rajesh Meghani, XEN (C) | Work Order issued vide No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. The physical progress of the work is 15.25% and financial progress is 0.89% |
| 2. | Hiring of 2 Nos. Steel Hull Mooring Launches with Crew and Mooring Gang at OOT, Vadinar for the period of Five (05) years. Estimate: Rs. 12,53,49,780/- | 12.53 Cr. | 9.12 Cr. | 27.21 % below | OOT/ME/WK/8017/484 dated 21/05/2021. | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | 14/12/2021 | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. OOT/ME/WK/8017/484 dated 21/05/2021. |
| 3. | Hiring of Service Boat for OOT, Vadinar for the period of 5 (five) years. Estimate: Rs.8,76,00,000/- | 8.76 Cr. | 9.59 Cr. | 9.49% above. | MR/WK/ 1397/66 dated 28/03/2022 | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | -- | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. MR/WK/1397/66 dated 28/03/2022. The party will deploy the Service Boat w.e.f. 22/10/2022 as per terms and conditions. |
| 4. | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | No. OOT/ME/WK/3009-I/576 dated 26/12/2018. | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 5. | Painting work for residential and Non-residential buildings Port Colony at Vadinar Estimate: Rs. 2,58,32,912/- | 2.58 Cr, | 1.61 Cr. | 37.66% Below | MR/WK/ 1397/36 dated 06/09/2021 | M/s. Shreeji Enterprise Gondal | 13/09/2021 | 18 Months | Shri Vikash A.C. XEN (Civil), | Work Order issued vide MR/WK/1397/36 dated 06/09/2021 |
| 6. | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 Cr. | 5.01 % above | OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/1666 dated 10/01/2020. |
| 7. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.44 Cr. | 2.83% above | OOT/ME-WK/RM/6004/239 dated 04/03/2021. | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. |
| 8. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | 1.06 Cr. | 2.98% above | OOT/C-WK/RM/4002/2001 dated 12/03/2020 | M/s. Abhay Intelligence & Security Services, Vadodara. | 14/03/2020 | 2 years and extended for a period for one year | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-WK/RM/4002/2001 dated 12/03/2020 |
| 9. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | OOT/ME-WK/RM/ 6018/329 dated 26/03/2021. | M/s. Pariya Electricals, Vadinar. | 01/04/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2021. |
| 10. | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | OOT/ME/WK/RM/8009/1947 dated 03/03/2020. | M/s. Aeromarine Pvt. Ltd., Mumbai | 01/06/2020. | 3 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/RM/8009/1947 dated 03/03/2020. |
| 11. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 Cr. | 6.01 % below | OOT/ME/WK/6008/1795 dated 06/02/2020. | M/s. Safari Travels, Balasinor | 07/02/2020 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME/WK/6008/1795 dated 06/02/2020. |
| 12. | Running and Maintenance of Guest House and Staff Canteen at OOT, Vadinar Estimate Rs. 55,66,811/- | 0.56 Cr. | 0.53 Cr. | 5.61 % below | OOT/C-WK/RM4026/114 dated 29/042/2022 | M/s. Mahakal Enterprise, Jamnagar. | 01/05/2022 | 03 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide: OOT/C-WK/RM/4026/114 dated 29/04/2022 |
| 13 | Maintenance Contract of the Residential Building and Non Residential Building in Port Colony and Jetty at Vadinar. | 0.53 Cr. | 0.47 Cr. | 9.51% below | OOT/C-WK/ RM/4050-II/328 dated 29/07/2022 | M/s. G N Enterprise, Vadinar | 01/08/2022 | 02 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide: OOT/C-WK/RM/4050-II/328 Dt.29.07.2022 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 30.09.2022

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dredging in the Navigational Channel & Alongside Cargo Berths/Oil Jetties at Deendayal Port Trust for year 2020-23”. Location At Kandla | 393.80 | 310.04 | 21.27 % Below | LOA No. EG/WK/6116/182 dated 10.03.2021 | M/s Adani Ports and Special Economic Zone Ltd., Ahmedabad | 09/04/2021 | 36 months | Shri K. Srinivasa Rao, EXECUTIVE ENGINEER ( HYDRAULIC & DREDGING), | Work in progress |
| 2 | Augmentation of liquid cargo handling capacity by revamping of existing pipeline network at Oil Jetty are, Deendayal Port Trust, Kandla | 130.49 | 126.49 | 3.05% below | LOA No. EG/WK/8306/NIT-PQ/08 dated 31/08/2021 | M/s. Patel Corrrtech JV, Gandhidham | 30/09/2021 | 24 months | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 3 | Construction of Oil Jetty No.8 at Old Kandla. | 105.51 | 99.08 | 6.09% below | No.CN/WK/1571/work/243 dtd. 03/02/2021 | M/s Kargwal KM Joint Venture, Mumbai | 17/02/2021 | 18 months | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 4 | Development of backup area of oil Jetty No.8 to 11 (Phase-I) | 80.97 | - | - | - | - | - | 12 Months | Shri B. Rajendra Prasad, SE (P) | Price bid opened and sent for L1 for approval. |
| 5 | Development of area from Junction of West gate-I to west gate-II now renamed as "development of land west side of road in between junction of west gate 1&2 and railway line to 12th berth - Phase -I | 80.31 | - | - | - | - | - | 18 months | Shri Rajesh Meghani, XEN(C-I) | Proposal sent for L1 for approval. |
| 6 | Up - gradation of tuna road from two lane to four land (Phase-I) | 71.57 | - | - | - | - | - | - | Shri Rajesh Meghani, XEN(C-I) | Proposal sent for L1 for approval. |
| 7 | Development of four lane road common corridor from LC236B to 16th CB along railway line (Phase-I) | 71.57 | - | - | - | - | - | 18 Months | Shri Rajesh Meghani, XEN(C-I) | NIT issued with date of opening 27/09/2022 |
| 8 | Upgradation of Plots & S.W.D. in 66 Hectare area inside cargo jetty area | 65.8 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Preliminary bid schedule to be open on 21/10/2022 |
| 9 | Retrofitting cargo berth No.8 | 64.86 | 47.27 | 27.13% Below | - | M/s. BMS Project-Marymatha JV, Kerala | 15/02/2022 | 16 Months | Shri Rajesh Meghani XEN(C-I) | Work in progress. |
|  | Retrofitting cargo berth No.9 |  |  |  |  |  |  |  |  |  |
| 10 | Construction of new godowns in place of existing godown no. 19 to 21 & 25 inside C. J. Area | 53.20 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Preliminary bid schedule to be open on 28/10/2022 |
| 11 | Development of four lane road common corridor from LC236B to 16th CB along railway line (Phase-I) | 55.28 | - | - | - | - | - | 18 Months | Shri Rajesh Meghani, XEN(C-I) | Preliminary Bid opened on 27.09.2022 |
| 12 | Development of plots, Roads & SWD in 34 hectare area inside CJA | 57.08 | 36.60 | 35.89% below | HW/WK/2486/363 dated 20/02/2021 | M/s. Bhimji Velji Soratia Construction P Ltd., | 06/03/2021 | 05/03/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 13 | Construction of Dome Shaped Storage Sheds inside cargo jetty area – Phase-I | 46.53 | 35.93 | 22.78% below | HW/WK/ 2475/456 dated 16/06/2021 | M/s Patel Construction. Gandhidham | 30/06/2021 | 29/06/2022 12 months | Shri Srinivas Rao, SE (H) | Work in progress Extension upto 29/12/2022 submitted for approval. |
| 14 | Construction of Oil Jetty No.7 at Old Kandla. | 44.59 | 42.40 | 4.91 % below | No.CN/WK/ 1553/81 dated 26.10.2015 | M/s Kargwal Construction Pvt. Ltd., Mumbai | 24/03/2020 | 18 months, Extn.granted upto 30/09/22 | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 15 | Development of Land in the West of Existing 66 hectare area for storage of cargo (Extension of custom bonded area) | 42.81 | 33.38 | 22.02% below | HW/WK/2457/355 dated 17/02/2021 | M/s. Kalthia Engineering Construction Ltd. | 02/03/2021 | 01/03/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 16 | Upgradation of Plots, Roads & SWD in 40 hectare area inside Cargo Jetty Area. | 39.36 | 31.48 | 19.84% below | N.A. | M/s. Neelkanth Infratech Pvt. Ltd. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | LOA issued. |
| 17 | Upgradation of Kutchha Plot C1 to C6 of 66 Hectares and SWD Network inside Cargo Jetty area. | 22.84 | 21.23 | 7.05% below | NA | M/s. K.K. Sorathia J/v Hari Om Earthmovers and Transport | NA | NA | Shri Srinivas Rao, SE (H) | LOA issued. |
| 18 | Construction of A,B, C and D type quarters at Gopalpuri | 18.94 | 13.78 | 27.16% below | TW/WK/7775/299 dtd. 07/06/21 | M/s. VC Project & Infra Pvt. Ltd. | 05/06/2021 | 04/06/2023 | Shri Hemant Bhaskar XEN(TD) | Work in progress |
| 19 | Providing screen wall surrounding the coal stacking yard inside CJA of DPT | 18.63 | 14.97 | 19.630% below | HW/WK/2423/468 dated 29.06.2021 | M/s. Mohandas V Rajani, | 15/08/2021 | 14/08/2022 12 months | Shri Srinivas Rao, SE (H) | Work in progress.Proposal for extension upto 31/12/2022 submitted for approval. |
| 20 | Development of Parking yards for trucks/vehicles for pre checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 | 14.59 | 12.87% below | HW/WK/2446/463 dated 26.06.2021 | M/s. Indian Construction Co., | 08/07/2021 | 07/07/2022 12 months work and 24 months maintenance Extension granted upt 07/11/2022. | Shri Srinivas Rao, SE (H) | Work in progress |
| 21 | Up-gradation and strengthening of existing oil jetty No.3 | 15.78 | - | - | - | - | - | 8 months | Shri B. Rajendra Prasad, SE (P) | Preliminary bid opened and under scrutiny. |
| 22 | Retrofitting of the Bunder Basin Structures | 10.00 | 7.11 | 11.10% below | LOA No. EG/WK/8114/51 dated 25/02/2022 | M/s. Chetan Construction Co., Mehsana | 21/03/2022 | 15 months | Shri Rajesh Meghani XEN (C-I) | Work in progress. |
| 23 | Improving existing oil jetty structures at oil jetty No.1, 2, 4 | 8.21 | 8.08 | 1.551% below the est. cost & 1.26% below the PMR. | PL/WK/8421-I/2238 dated 10/06/2020 | M/s. Sarjan Construction Pvt. Ltd. | 20/06/2020 | 18 Months Extension granted upto 20/09/2022 | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in Progress. Further extension is under process. |
| 24 | SPECIAL REPAIRS TO EXISTING STORM WATER DRAIN NETWORK INSIDE CARGO JETTY AREA | 8.23 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Preliminary bid schedule to be open on 01/11/2022 |
| 25 | Construction of Ring Road (Periphery road ) from NH-8A (From KASEZ) to Adipur | 8.20 | 6.33 | 22.8276% below |  | M/s. Shree Ganesh Construction, Anjar | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | L1 under process. |
| 26 | Construction of road & SWD at SIPC Location -2 (Kandla) for Development of Smart Industrial Port City (SIPC) at Kandla - Gandhidham - Adipur Complex (Re-invited) | 8.15 | 5.67 | 30.40% below | CN/WK/5545-I(Road)/ SWD | M/s. Hariom Earthmovers & Transport | 13/05/2022 | 12/11/2022 | Shri K.J. Todarmal, SE(C) | Work in Progress. |
| 27 | Upgradation of internal road network from West gate I to Kutch Salt Junction LC 236 | 8.10 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Scrutiny report submitted and technical evaluation is under process |
| 28 | Resurfacing of Plots, Roads & SWD in 40 Hectare area inside Cargo Jetty area. | 8.09 | NA | NA | NA | NA | NA | NA | Shri Srinivas Rao, SE (H) | Submitted to competent authority for approval of L1 bidder |
| 29 | Extension of Custom Bounded area in Backup of 13th & 16th Berth | 8.02 | 5.28 | -34.24 % Below | LOA No. EG/WK/8115/264 dt. 22/06/2022 | M/s Mohit Enterprise, Rajkot | 08/08/2022 | 15 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 30 | SPECIAL REPAIRS of plot no 8 & 9 at bunder basin (5 hectares) | 7.99 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Preliminary bid schedule to be open on 04/11/2022 |
| 31 | Improving / Upgradation of Custom Fencing Wall of Cargo jetty and Bunder Area | 7.68 | 5.38 | 29.95 % below | HW/WK/2507-I/73 dated 15/02/2022 | M/s. Deosi Govindji Parmar (Lead Partner) J/v M/s. Shree Balaji Construction Co. | 28/02/2022 | 27/02/2023 12 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 32 | S/R to Road along side Godown no 18, 24, 32 & 33 inside cargo jetty area | 7.68 | 5.01 | 34.74% below | HW/WK/2520/98 dated 14/03/2022 | M/s. K.K. Sorathia JV Hariom Earthmovers and Transport | 29/03/2022 | 28/11/2022 8 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 33 | S/R to quarters / building at FCI & KDLB Colony | 6.87 | 4.66 | 32.1808% below | TW/WK/ 7788-I/203 dated 27/06/2022 | M/s. Ankita Construction, Adipur | 01/07/2022 | 30/09/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 34 | Strengthening of multi storey Building with micro concreting, plinth protection at Gopalpuri | 6.61 | 4.26 | 35.41% below | TW/WK/7794-I/ dtd. 26/03/2021 | M/s. Mohandas V. Rajani, Adipur | 01/04/2021 | 30/09/2022 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 35 | Appointment of Project Management Consultant (PMC) for Capital and Maintenance Dredging works of Deendayal Port Trust from firms/ consortiums Empanelled Consultants for dredging works (Class-A, Category-A) by Indian Port Association, New Delhi. | 6.36 | Rs. 5.33 | 15.32% Below | LOA No.EG/WK/6112/333 dated 15.11.2019 | M/s AECOM INDIA PVT LTD, GURGAON | 25/11/2019 | 36 months | Shri K. Srinivasa Rao, XEN (H &D) | Work in progress |
| 36 | Resurfacing of road from LC 236 to Statue of Maharav at Kandla | 4.44 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(Road) | Sent for pre-scrutiny. |
| 37 | Upgradation of Sewage treatment plant at Gopalpuri | 4.27 | 4.14 | 3.0363% below | TW/WK/7736-I/254 dated 21/07/2021 | M/s. Rajkamal Buildings, Infrastructure (P) Ltd., Gandhidham. | 01/08/2022 | 31/01/2026 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 38 | Construction of RCC Floor on surface of dismantled godown No.3& 4 inside Cargo Jetty Area. | 4.11 | 3.28 | 6.11% below | HW/WK/2535 /145 dated 21/06/2022 | M/s. Ankita Construction, Adipur | 01/07/2022 | 30/06/2023 12 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 39 | Preparing and monitoring of Environmental Management Plan for Deendayal Port Authority at Kandla. | 4.076 | 2.52 | 38.17 % below | EG/WK/EMC/11023/2011/IV dtd. 05/12/2019 | M/s Detox Corporation Pvt. Ltd. | 16/12/2019 | 36 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in Progress. |
| 40 | Construction of Fire Brigade Station Opposite Jetty Office in CKD Yard inside Cargo Jetty Area | 3.48 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Scrutiny Report submitted. |
| 41 | Providing Legal, Technical and financial transactions for all ongoing and future proposals of DPA on PPP / Captive Mode for the period of 2 years and further extendable for one year. | 3.26 | 1.985 | 39.25% below | EG/WK/4759/TA/79 dated 10/10/2019 | M/s.Infrastructure Development (Karnataka) Corporation Ltd (Ideck) | 14/10/2019 (as per Work Order) | 2 years and further extendable for 1 year | Shri K.J. Todarmal, SE(D) | Work is in Progress. |
| 42 | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 | Rs. 2.43 | 35.73% Below | W.O. No. HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd., Gurgaon - 122015 Haryana- India | 11/02/2021 | 36 months | Shri K. Srinivasa Rao, XEN (H&D) | Work is in progress |
| 43 | S/R to CISF complex building & Structure at New Kandla | 3.24 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar, XEN(Road) | S/R to CISF complex building & Structure at New Kandla |
| 44 | Maintenance of PH & UG drainage at Gopalpuri Port Colony & KDLB Colony for the period of two years | 3.15 | 1.56 | 50.51% below | TW/WK/7813-I/ dated 05/07/2022 | M/s. Patel Construction, Gandhidham. | 05/07/2022 | 04/07/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 45 | Annual Maintenance Contract for residential and non-residential building a Port Colony, Gopalpuri for two years. | 3.05 | 1.71 | 44.12% below | TW/WK/7806-I/126 dated 30/04/2022 | M/s. Dhanjibhai K. Patel, Anjar | 02/05/2022 | 01/05/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 46 | Construction of watch tower inside cargo jetty area | 3.04 | 2.84 | 6.22% below | HW/WK/2470/407 dated 09.04.2021 | M/s. Viyuha Infrabuild | 24/05/2021 | 8 months Extension granted upto 22/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 22/12/2022 submitted for approval. |
| 47 | Special repairs to RFID cum data centre building adjoining to Seva Sadan III at New Kandla | 3.01 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Preliminary bid schedule to be open on 04/10/2022 |
| 48 | Deployment of equipment for cleaning of all toilet blocks inside Port area and to maintain high standard of hygienic and to avoid pollution. | 2.99 | 2.23 | 25.40% below | N.A. | M/s. Shree Ganesh Construction, Anjar - Kutch | N.A. | N.A. | Shri Srinivas Rao, SE(H) | TCN Price Bid submitted for approval of competent authority |
| 49 | Improving the fendering arrangement inside cargo jetty area HD-14/19 | 2.85 | 3.54 | 24.39% above | HW/WK/2392/137 dated 02/06/2020 | M/s. Patel Construction Co., Gandhidham | 15.06.2020 | 12 months 2nd extension granted upto 14/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 17/12/2022 submitted for approval. |
| 50 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2022-24 | 2.78 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Sent for pre-scrutiny |
| 51 | R/m of Maintenance Jetty - Repairs and Maintenance of Pontoons and Walkways of SNA Jetty and Flotilla Jetty | 2.77 | 3.37 | 10.51% above | HW/WK/2494/462 dated 25.06.2021 | M/s Patel Construction. Gandhidham | 08/07/2021 | 07/07/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 52 | Maintenance Contract for Godown inside Cargo Jetty area for two years 2022-23 & 2023-24) | 2.70 | 1.67 | 38.00% below | N.A. | M/s. Rajput Infrastructure Co. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Present tender discharged and re-invitation is under process of approval. |
| 53 | Annual Maintenance Contract for AO Building at Gandhidham for 02 years | 2.67 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Price bid opened on 08/09/2022. |
| 54 | Special Repairs to ATM office, Marine Bhavan, Immigration Centre Inside Cargo Jetty Area | 2.63 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Scrutiny Report submitted. |
| 55 | Two years contract for supply and maintenance of railway tracks inside and outside cargo jetty area (for 02 years | 2.59 | 2.03 | 21.40 % below | HW/WK/2487/359 dated 20/02/2021 | M/s. Laxyo Entergy Ltd. | 06/03/2021 | 05/03/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 56 | Resurfacing of road from KK road junction to Mithirohar GIDC at Kandla | 2.52 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Technical Bid opened on 13.09.2022 |
| 57 | Improving Storm Water drainage system at old kandla. | 2.31 | 1.67 | 27.54% below | PL/WK/8408/944 dated 06/10/2021 | M/s. Shree Ganesh Cosntruction. | 30/11/2021 | 11 Months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in Progress |
| 58 | S/R to AO Building at Gandhidham - Renovation of toilet blocks, recreation room, old board room | 2.20 | 1.32 | 40.1319% below | TW/WK/7795-I/ 111 dt. 21/04/2022 | M/s. Ankita Construction, Adipur | 25/04/2022 | 24/04/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 59 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2020-22 | 2.19 | 1.15 | 47.36% below | TW/WK/7781-I/ 621 dt.14/10/2020 | M/s. Rajput Infrastructure, G’dham | 15/10/2020 | 14/10/2022 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 60 | House Keeping & Cleaning of Building of Office building and surrounding outside Cargo Jetty Area for the year 2021-23. | 1.97 | 1.07 | 45.36 % below | HW/WK/2538/68 dated 07/02/2022 | M/s. Rajput Infrastructure Co. , Gandhidham | 22/02/2022 | 21/02/2024 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 61 | Maintenance Contract of Fenders inside Cargo Jetty Area for two year 2022-23 & 2023-24) | 1.97 | 2.14 | 12.17% above | N.A. | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | N.A. | N.A. | Shri Srinivas Rao, SE(H) | TCN Price Bid submitted for approval of competent authority |
| 62 | Deployment of equipment for cleaning of all toilet block inside Port area to maintain high standard of hygienic and to avoid pollution (HD-20/19) | 1.88 | 1.16 | 38.04% below | HW/WK/2428/104 dated 21/04/20 | M/s. Patel Construction | 04/05/2020 Extension granted upto 31/10/2022 | 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 63 | Maintenance contract for roads and RCC culverts inside CJA at New Kandla for 02 years | 1.75 | 1.84 | 5.74 % above | HW/WK/2443/401dated 31.03.2021 | M/s Shree Ganesh Construction | 16/04/2021 | 15/04/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 64 | Construction of Fire Brigade Station at Old Kandla. | 1.65 | Part - A 1.34 Part - B 0.07 | 13.95% below the est. cost. | PL/WK/8446/919 dated 30/09/2021 | M/s. Ankita Construction. | 30/10/2021 | 12 Months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in Progress |
| 65 | Two years maintenance contract for office building outside Port area (Civil Work) | 1.63 | 1.12 | 30.99% below | N.A. | M/s. Sanjay K Sorathiya & Co. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Proposal to discharge the present tender and reinvite is under process of approval |
| 66 | Annual Maintenance Contract for cleaning & housekeeping work of DPT Hospital & Isolation Ward at Gopalpuri & Kandla (for 2years) | 1.62 | 0.85 | 47.70% below | TW/WK/7798 dtd. 30/01/2021 | M/s. Patel Const. co., G’dham | 02/10/2021 | 02/09/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 67 | Maintenance Contract for Residential & Non - Residential Building at New Port Colony at New Kandla for two years. | 1.59 | 1.06 | 33.30% below | RW/WK/7790-I/509 dtd.01/09/20 | M/s. Rajput Infrastructure Co., Gandhidham | 02/09/2020 | 01/09/2022 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress. |
| 68 | Providing Labour amenities centre at various locations inside Cargo Jetty Area. | 1.53 | 1.18 | 22.85 % below | HW/WK/2461/60 dated 25/01/2022 | M/s. Rajput Infrastructure Co. | 08/02/2022 | 07/02/2023 12 Months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 69 | Providing RCC drinking water tank. | 1.52 | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad B., SE (PL) | Technical bid under evaluation. |
| 70 | Appointment of Independent Engineer for the work of “Development of Marine Liquid Terminal Facilities consisting of SPM and Two Product Jetties in KPT waters at OOT, Vadinar for Handling Crude and Petroleum Products on Captive Use Basis”. | 1.44 | 1.18232 | 17.89% below | Work Order No.EG/WK/4823(IE)/109 dated 22/10/2019 | M/s RINA Services s.p.A,Mumbai | 01/11/2019 | 42 months | Shri K.J. Todarmal, SE(D) | As concessionaire has not started construction activity, the work order issued to M/s. RINA has been kept in abeyance. |
| 71 | Third Party Inspection and Quality Inspection and Quality Assurance for the works costing more than Rs. 1.00 Cr. of Civil Engineering Department of Deendayal Port Authority. | 1.358 | 1.17 | 14.05% below | Work Order No.EG/WK/5212/53 dtd.16/10/2021 | M/s. VCS Quality Services pvt. Ltd., Mumbai | 25/10/2021 | 2 years from 25/10/2021 | Shri Sunil Soren, XEN(D) | Work in Progress. |
| 72 | Maintenance Contract for Non-residential buildings inside Harbour area (Civil Work) | 1.31 | 0.95 | 27.55% below | HW/WK/2526/122 dated 20/04/2022 | M/s. Mepabhai Mandan & Co., Adipur | 05/05/2022 | 04/05/2024 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 73 | Annual Maintenance Contract for the Buildings, Walkway, trestles, fire fighting pipelines, garden insdie and outside oil jetty area at Old Kandla. | 1.29 credit part 0.04 | part A 1.17 Part B credit item 0.04 | 9.63% below the est. cost. | PL/WK/8316-II/125-A dated 12/02/2021 | M/s. Mahesh Construction, Adipur. | 15/02/2021 | 12 Months (ext. upto 14.06.2022) | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in progress. Extension proposed upto 14/09/2022 |
| 74 | Providing shed for parking at AO Building. | 1.26 | 0.79 | 36.903% below | TW/WK/7807-I/ 138 dtd. 10/05/2022 | M/s. Santoshi Buildings, Adipur | 16/05/2022 | 15/02/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 75 | Strengthening of existing environmental management cell at DPT: Appointment of environment experts for two years and further extendable for one year | 1.232 | 1.20 | 2.60% below | EG/WK/ 4783/V/131 dtd.05/02/21 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15/02/2021 | 24 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 76 | Two years maintenance contract for Railway track leading to Tuna from 0 to 11 Km KPT Line (Take off Point at 2.573 Km at GIM Yard to 13.54 Km including LC-1, LC-2) | 1.19 | 0.908 | 23.77% below | HW/WK/2515/432 DATED 31/05/2021 | M/s Patel Construction. Gandhidham | 14/06/2021 | 13/06/2023 24 Months | Shri Srinivas Rao, SE (H) | Work in progress |
| 77 | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years | 1.13 | 0.82 | 27.27% below | PL/WK/8461-I/25 dated 09/02/2022 | M/s. Sanjay K Sorathiya & Co. | 09/02/2022 | 24 Months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in Progress |
| 78 | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla. -HD-07/19 | 1.12 | 1.20 | 7.21% above | HW/WK/2379-III/332 dated 05/12/2019 | M/s. Patel Construction Co. | 18/12/2019 | 12 months Extension of work granted upto 17/12/2021. 2nd extension granted upto 17/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 17/12/2022 submitted for approval. |
| 79 | Maintenance contract for quay and transit area inside cargo jetty area for two years | 1.04 | 0.87 | 16.77% | HW/WK/2617/12 dated 24/09/2021 | M/s. Sanjay K Sorathiya & Co. | 10/10/2021 | 09/10/2023 24 Months | Shri Srinivas Rao, SE (H) | Work in progress |
| 80 | Maintenance Contract for Tree Plantation near offices, other buildings, along roads, islands, gates, etc. inside/outside cargo jetty area for two years | 0.97 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Preliminary bid schedule to be open on 07/10/2022 |
| 81 | Maintenance Contract for Residential & Non - Residential Building at New Port Colony at New Kandla for two years. | 0.97 | 0.62 | 36.20% below | - | M/s. Murlidhar Projects | - | - | XEN(Road), Shri Hemant Kumar Bhaskar | Pre-acceptance letter issued on 26.09.2022 |
| 82 | Dismantling of Residential and Non - Residential buildings at New Kandla | 0.96 | 1.58 | 64.42% above | RW/WK/7706-I/19 dtd. 08/12/2021 | M/s. Symcom Exim (P) Ltd., Mumbai | 16/12/2021 | 15/08/2022 | Shri Hemant Kumar Bhaskar XEN(Road) | Work in progress. |
| 83 | Dismantling of existing godown no.19 to 23 inside cargo jetty area | Part A 0.26 and PART ‘B’ 0.93(Credit item) | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Preliminary bid schedule to be open on 14/10/2022 |
| 84 | Providing of concrete flooring underneath pipeline inside oil jetty area at Old Kandla | 0.88 | 0.91 | 3.7079% above | PL/WK/8284-I/109-A dated 04/02/2022 | M/s. Sanjay K Sorathiya & Co. | 07/02/2022 | 08 Months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in progress. |
| 85 | Two years contract for cleaning of storm water drain inside cargo jetty area | 0.80 | 0.42 | 47.81% below | HW/WK/2444/180(A) dtd. 10/07/2020 | M/s. Narayan Construction Co. | 29/07/2020 | 28/07/2022 24 months | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 28/11/2022 submitted for approval. |
| 86 | Two years contract for cleaning of storm water drain inside cargo jetty area | 0.78 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Proposal to open price bid is sent to competent authority. |
| 87 | White washing, painting & distempering to residential and non-residential buildings & CISF complex at New Port Colony, New Kandla (for 2 years) | 0.67 | 0.38 | 43.20% | RW/WK/7790-I/ dated 05/2022 | M/s. Rajput Infrastructure Co., Gandhidham. | 01/06/2022 | 31/05/2024 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress. |
| 88 | Annual Maintenance Contract for Sports Complex at Gopalpuri for the period of 2 yrs. | 0.65 | 0.42 | 35.35% below | TW/WK/7764-I/ 371 dt. 14/04/2020 | M/s. Patel Const. Co., | 16/04/2020 | 15/04/2022 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. Extension applied for 6 months. |
| 89 | Annual Maintenance Contract for Sanitation of New Port Colony, New Kandla | 0.64 | 0.34 | 46.36% above | RW/WK/7808-I/394 dtd. 10/01/2022 | M/s. Rajput Infrastructure Co., Gandhidham | 11/01/2022 | 10/01/2023 | Shri Hemant Kumar Bhaskar XEN(Road) | Work in progress. |
| 90 | Maintenance contract for cleaning of SWD, along road sides for two (2) years (J.N. Road, Link Road, Bye Pass Road and outside cargo jetty etc) at New Port Colony , New Kandla | 0.58 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(Road), | TC meeting held on 16/08/2022 and Technical qualification of bidders is under process. |
| 91 | House keeping & cleaning of office building inside cargo jetty area (for 2 years) HD-10/19 | 0.54 | 0.4128 | 23.43% below | HW/WK/2422-I/367 dated 20/02/2021 | M/s. Shree Ganesh Construction, Anjar | 06/03/2021 | 05/03/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 92 | Maintenance Contract of 1.5 MLS Sewage treatment plant at New Port Colony, New Kandla for 2 years | 0.52 | 0.29 | 45.13% below | RW/WK | M/s. Gadhvi Construction Co., | 21/06/2022 | 20/06/2024 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress. |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No | Name of work & location | Reserve price Per sq. mtr./year | Premium received over and above reserve price during e-auction (per sq. mtr. / per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 93 | E-tender cum E-auction is for allotment of plot no. 08, ADMG. 11,695.00 sq. mtrs. (including structures) situated to the west of link road connecting Old Kandla for construction of liquid chemical storage installation on 30 years lease basis | Rs. 1060.10 | Rs. 20 | LW/PL/3483-I/522 DATED 16.05.2022 | M/s. Shreeji Power & Insulators Pvt. Ltd. | 30 years from date of Possession | Shri S.K. Rao. SE (KL) | E-auction has been carried out on 28-01-2022. pre-acceptance letter issued on 19.03.2022. Party had made payment of Advance Lease Rent & Security Deposit. Accordingly allotment letter was issued on 16.05.2022 & Possession of Land given on 16.05.2022 |
| 94 | E-Tender cum E-Auction for the allotment of Various size of plots for Salt manufacturing and salt related activities in between Village Veera to Village Jhungi on 30 years lease on as is where is basis. | Rs. 25923.30 (per acre/per annum) | Plot No.1-Rs.200 Plot No.2- Rs.400 Plot No.3 Rs.500 Plot No. 5 Rs.200 Plot No. 6 Rs.200 Plot No.07 Rs.300 Plot No.08 Rs.4200 Plot No. 09 Rs.4100 Plot No.10 Rs.700 | Plot No.01 LW/PL/3507-I/605 DATED 14.06.2022 Plot No.02 LW/PL/3507-I/607 DATED 14.06.2022 Plot No.03 LW/PL/3507-I/603 DATED 14.06.2022 Plot No.05 LW/PL/3507-I/604 DATED 14.06.2022 Plot No.06 LW/PL/3507-I/601 DATED 14.06.2022 Plot No.07 LW/PL/3507-I/602 DATED 14.06.2022 Plot No.08 LW/PL/3507-I/609 DATED 14.06.2022 Plot No.09 LW/PL/3507-I/606 DATED 14.06.2022 Plot No.10 LW/PL/3507-I/608 DATED 14.06.2022 | Plot No.1 - M/s. Priya Salt & Chemicals Pvt. Ltd. Plot No.2 - M/s. Shri Pingle-shwar Salt Industries. Plot No.03 - M/s. Lakshmiwadi Mines & Minerals Pvt. Ltd. Plot No. 5 - M/s Patel Salt & Alied Industries Plot No.06 - Aashwat Salt and chemicals Pvt. Ltd. Plot No.07 - M/s Daivya Salt & Chemicals pvt. Ltd. Plot No. 8 - M/s Patel Salt & Allied Industries Plot No. 09 & 10 - M/s. Shamji Kangad & Co. | 30 years from date of Possession | Shri S.K. Rao. SE (KL) | Online Price Bids opened on 03.03.2022.E-Auction of plots was carried out on 06.06.2022 to 10.06.2022. Pre acceptance letter issued on 13.06.2022. Allotment letter issued on 14.06.2022 & Possession was given on 15.06.2022 |
| 95 | E-Tender cum E-Auction for the allotment of plot Admg. 4000 Sq/Mtrs situated opposite to VTMS towers and behind boundary of DPT (East of dry dock) for the purpose of Barge Repairing/Beaching on 5 years lease basis on as where is basis. | Rs. 277.12 | Rs. 20 | LW/PL/3493/633 DATED 15.06.2022 | M/s. Amrut Dredging & Shipping Ltd. | 30 years from date of Possession | Shri S.K. Rao. SE (KL) | The tender has been re-invited and price bid opened on 27.04.2022. E-auction was carried on 05.05.2022 Board vide Resolution No.25 dated 27/05/2022. approved the proposed for allotment of Land to M/s. Amrut Dredging And Shipping Ltd. Accordingly, Pre-Acceptance Letter is issued on 08/06/2022. Allotment letter was issued on 15.06.2022 & Possession of Land given on 01.07.2022. |
| 96 | E-tender cum E-auction for the allotment of various size of plots for the purpose of Godowns/Warehouses situated at Kandla on 30 years lease on as is where is basis. | Rs. 231.86 , Rs. 151.36 & Rs.217.15 | plot No.31-Rs.10 Plot No.33- Rs.10 Plot No.34 Rs.10 Plot No. 35 Rs.10 Plot No. 38 Rs.10 Plot No.39 Rs.10 Plot No.52 Rs.10 Plot No. 53 Rs.10 | Plot No.31 LW/PL/3526-I/45 DATED 27.07.2022 Plot No.35 LW/PL/3526-I/46 DATED 27.07.2022 Plot No.39 LW/PL/3527-I/47 DATED 27.07.2022 Plot No.52 LW/PL/3527-I/48 DATED 27.07.2022 Plot No.38 LW/PL/3527-I/49 DATED 27.07.2022 Plot No.34 LW/PL/3527-I/43 DATED 27.07.2022 Plot No.33 LW/PL/3527-I/44 DATED 27.07.2022 Plot No.53 LW/PL/3527-I/137 | Plot No.31 - M/s Friends Salt works & Alied Ind. Plot No.33-M/s Friends Salt Works & Alied Ind. Plot No.34-M/s Friends Salt Works & Alied Ind. Plot No.35-M/s Friends Salt Works & Alied Ind. Plot No.38-M/s Shreeji Exports Plot No.39-M/s Friends Salt Works & Alied Ind. Plot No.52-M/s Shiv Shipping Services Plot No.53 M/s. Shidhivinayak Warehousing | …. | Shri S.K. Rao. SE (KL) | Pre- bid meeting held on 03-02-2022. Pre-Bid queries finalized Technical Bid opened on 31.03.2022. Price-bid opened on 04.05.2022.2022 E-Auction was carried out on 24-05-2022.pre-acceptance letter issued on 22.06.2022 to 08 bidders.08 Party had made payment of Advance Lease Rent & Security Deposit. Accordingly allotment letter was issued on 27.07.2022 & 06.09.2022 TO 08 parties. Possession of Land given on 03.09.2022 to M/s. Shiv Shipping Services & 28.09.2022 to M/s Shreeji Exports and M/s. Shidhivinayak Warehousing |
| 97 | E-tender cum E-auction for allotment of 06 Nos. of plots (with structure) situated at old/new Kandla for the purpose of liquid storage tanks (products permitted in the earlier Lease Deed/ Allotment Letter) on 30 years lease on as is where is basis(Phase-I). | Rs. 1060.56 | …. | …. | …. | …. | Shri S.K. Rao. SE (KL) | NIT published on 27/04/2022,pre-bid meeting held on 04/05/2022.Date of opening of tender extended up to 10.10.2022 |
| 98 | E-tender cum E-auction for allotment of 04 Nos. of plots (with structure) situated at old/new Kandla for the purpose of liquid storage tenks (products permitted in the earlier Lease Deed/ Allotment Letter) on 30 years lease on as is where is basis(Phase-II). | Rs. 1060.56 | …. | …. | …. | …. | Shri S.K. Rao. SE (KL) | NIT published on 27/04/2022,pre-bid meeting held on 04/05/2022.Date of opening of tender extended up to 15.10.2022 |

Ro-Ro / Rox-Pax Ferrry Service Cell

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 99 | Maintenance Dredging at Underneath/Periphery of Landing Pontoon of Ro-Pax facility at Dahej Terminal for 12 Months. | 2.43 | 2.22 | 8.5926% (Below) | Work Order No. CN/WK/1600/DAHEJ/17-A DATED – 11/05/2021 | M/s. Divine Shipping Services, Ahmedabad | 12-05-2021 | 12 Months Extension granted upto 10/9/2022 | Shri Rajendra Prasad Bethi, SE(P) | Further extension for 08 months or till finalization of new contract proposed. |
| 100 | Maintenance dredging at Berth pockets, surroundings of landing pontoon, Turning circle and approach channel of Ghogha – Gujarat. | 2.59 | 3.38 | 30.31% (Above) | Work Order No. CN/WK/1600/GRAB/BACKHOEDATED – 10/01/2022 | M/s. Divine Shipping Services, Ahmedabad | 10-01-2022 | 3 Months | Shri Rajendra Prasad Bethi, SE(P) | Work extended upto 30.04.2022. Final variation Stt. approved by competent authority. Final bill amount paid. |
| 101 | Construction of RORO/ROPAX facility at Muldwarka, Gujarat. | 84.74 | 76.69 | 9.5% (Below) | LOA No.CN/WK/1600-Const/Muldwarka/7 dated 14/01/2022 | M/s. BMS Projects – Marymatha JV | 10-05-2022 | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | Interim W/O for fabrication of Pontoon and Linkspan at Hazira, awarded on 10/05/2022. Final W/O shall be awarded after receipt of EC & CRZ. |
| 102 | Dredging in Approach channel Turning Circle, Berth pockets and surroundings of landing pontoon etc at Ghogha Ro-Ro Terminal Gujarat. | 28.63 | 45.81 | 60% (Above) | Work Order No. CN/WK/1600- GHOGHA (7BCD)/51 Dated – 25/04/2022 | M/s. Rock & Reef Dredging Pvt Ltd., Navi Mumbai | 25-04-2022 | 4 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Proposal for extension upto 31/12/2022 is submitted for approval. |
| 103 | Monitoring for smooth functioning of Ro-Ro Facility services located at Hazira, Dahej and Ghogha. | 1.94 | 1.66 | 14.36% (Below) | Work Order No. CN/WK/1600/38 Dated – 29/03/2022 | M/s. Dhanjibhai K Patel | 01-04-2022 | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress |
| 104 | Dredging at alongside Ro-Ro / Ropax berth at Hazira Terminal – Gujarat. | 300.55 | 45.08 | 85% (Below) | Work Order No. CN/WK/1600/HAZIRA DREDGING (7BCD)/37 Dated - 22/03/2022 | M/s. Essar Bulk Terminal Ltd, Hazira, Surat | 05-04-2022 | 2 Months | Shri Rajendra Prasad Bethi, SE(P) | Work completed on 15.04.2022. Amount after final variation is Rs.22,55,850/-. 1st & final bill amount paid. |
| 105 | Construction of RoRo / Ropax facility at Pipavav – Gujarat. | 110.17 | - | - | - | - | - | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | Technical bid opened on 02.03.2022. Price Bid yet to be opened. |
| 106 | Construction of Ro – Ro / Ro-Pax On – Shore facility at Muldwarka – Gujarat, EPC mode. | 30.81 | 33.88 | 9.97% (Above) | Work Order No.CN/WK/1600/Onshore Muldwarka/137 dated 15.07.2022 | M/s. MMC Projects (India) Pvt Ltd., Gandhidham | 25-07-2022 | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | LOA issued on 03/06/2022 |
| 107 | Annual Maintenance contract of Linkspan Pontoon and Terminal facilities of Dahej & Ghogha Ro-Pax ferry terminal | 3.90 | 3.90 | - | Supplementary Work Order No. CN/WK/1600/55 Dated – 09/07/2021 | M/s. Vishwakarma Mechanical works, Porbandar | 08-03-2019 | 07-03-2021 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. In principle approval of competent authority given for extension of work upto 07.11.2022 and Anticipated variation No.1 for net excess of Rs. 276.87 lakhs for Ghogha and Dahej respectively |
| 108 | Construction & Maintenance of Ro-Pax facility at Hazira-Gujarat on EPC mode | 66.34 | 69.06 | 4.09% above | CN/WK/1600/Pre-bid/10 dated 15.04.2021 | M/s. BMS Projects-Marymatha JV | 21-04-2021 | 14 Months Extended upto 20/09/2022 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Further extension upto 20/10/2022 is under process. |
| 109 | Construction of Ro-Ro/Ro-Pax On-shore facility at Pipavav-Gujarat on EPC mode | 36.53 | - | - | - | - | - | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | Technical bid scheduled to be opened on 11/10/2022 |
| 110 | Annual Maintenance Contract of Navigational Channel Marking System (Buoys) at Ghogha Ro-Pax | 0.86 | - | - | - | - | - | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Technical bid opened on 29/09/2022 |
| 111 | Annual Maintenance Contract of Navigation Channel Marking System (Buoys) at Dahej & Ghogha – Ro Pax Online Tender ID 383191 | 0.48 | 0.48 |  | Supplementary Work Order No. CN/WK/1600/49 Dated – 29/06/2021 | M/s. Sai Sagar Dredging & Marine Services Pvt. Ltd., Bharuch | 03-03-2020 | 02-03-2021 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. In principle approval of competent authority given for extension of work upto 01.11.2022 and Anticipated variation No.1 for net excess of Rs. 31.94 lakhs for Ghogha and Dahej respectively |
| 112 | Annual Maintenance Contract for Link spans, Pontoons and Terminal facilities at Ghogha | 2.98 | - | - | - | - | - | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Technical bid opened on 21/09/2022 |
| 113 | Annual Maintenance Contract for Link Spans, Pontoons and Terminal facilities at Dahej | 3.00 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | Technical bid opened on 30/09/2022 |
| 114 | Annual Maintenance contract for Navigational Channel marking system (Buoys) at Dahej - Ro- Pax | 3.69 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | Technical Bids scheduled to be opened on 07.10.2022 |
| 115 | Maintenance Dredging at Periphery of landing pontoon of Ro-Pax facility at Dahej Terminal for 12 months | 2.22 | - | - | - | - | - | 12 months | Shri Rajendra Prasad Bethi, SE(P) | Technical Bids scheduled to be opened on 04.11.2022 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6 .	MARINE DEPARTMENT							                                                                                      AS ON 30.09.2022

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | - | Executed on 09/03/2022 | M/s. Electronics Corporation of India Ltd., Hyderabad | 25/11/2021 | 24 months for supply, installation and commissioning AMC 10 years after installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Supply & Installation work completed on 25/11/2020. AMC work in progress. |
| 2 | Hiring of 04 Nos. of 50/60 tonn Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below Estimated Cost-OSL Ltd. 20.08% below Estimated Cost - KNK Ship | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator | Board vide Resolution No. 56 in its meeting held on 12.08.2016 have approved to award the work to contractors. W.O. has been issued on 03/10/2016 & 22/09/2016. |
| 3 | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | 26/04/2021 | 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 13/10/2020. Work Order issued on 05/01/2021.. |
| 4 | Renewal of Steal Plates & painting of various crafts / Tugs of DPT | 2.09 Cr. | 1.80 Cr. | 14.19% below | Executed on 16/06/2021 | M/s. Patel Engineering Works, Gandhidham. | 06/08/2021 | 2 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 21/05/2021. Work Order issued on 13/07/2021. |
| 5. | Hiring or 2 Nos. of Steel Hull Mooring Launches and Moorings Gangs at Deendayal Port, Kandla for a period of 5 years. | 14.60 Cr. | 10.76 Cr. | 26.24% below | Yet not executed | M/s. Pacific Shipping Services, Mumbai | Yet not commenced | 5 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 28/09/2022 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 30.09.2022

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |
| 2. | Hiring of brand new make and model of 2018 on "monthly hire basis" and made and model not earlier than1st January, 2017 on "as and when required basis" diesel vehicles to DPT for a period of 03 years | 8.86 Cr. | 8.23 Cr. | 4.34% Below | Executed. | M/s. Shree Ganesh Travels, Mumdra | 01/01/2019 | 30/09/2022 Extension for further period of 3 months w.e.f. 01/07/2022 or till the finalization of new contract, whichever is earlier granted vide letter No. GA/GN/5240/2018/1554 dated 23/06/2022 | Shri Shailendra Paney, Sr. Asstt. Secretary. | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	MEDICAL DEPARTMENT										                                            AS ON 30.09.2022

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. | Dr. (Mrs.) K. Gandhi Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	TRAFFIC DEPARTMENT											                	AS ON 30.09.2022

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Engagement of manpower service provider for providing various categories of outsourced staff to carry out railway operation inside Cargo Jetty area for a period of 3 years. | 3.88 Cr. | 2.87 Cr. | 26.00% below | Executed on dated 26/07/2021 | M/s. Dhanjibhai K. Patel, Anjar. | 01/05/2021 | 30/04/2024 | Shri T.D. Maheshwari, ATM (Railway), | Work in progress. |
| 2. | Outsourcing of Establishing and operating of occupational health services at Deendayal Port Authority, New Kandla for the period for 5 years. | 3.54 Cr. | 2.98 Cr. | 16.59% below | Executed on dated 15/12/2021 | M/s. Accord Multispecialty Hospital, Bhuj | 15/05/2021 | 5 years from the date of commencement | Safety Officer | Work in progress. |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

9.	FINANCE DEPARTMENT										                                     AS ON 30.09.2022

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |  |  |  |  |  |  |  |  |  |  |

*****