## May
HARBOUR DIVISION
Statement showing the details of Bills of various parties and its payment status for the month of June'2021.
Sr. No. | Nature of Work | Name of firm | GSTIN | Address with Pin | Phone / Mobile No. & Email | Amount (Rs.) | Bill No. & Date | Date of Receipt | Date of forward | Time taken by Division (Days) | Date of payment | Time taken by Accounts (Days) | Total Time (Days) | Reasons for delay, if any
1 | Development of Land in the West of Existing 66 hectare area for storage of cargo (Extension of custom bonded area) | M/s. Kalthia Engineering & Construction Limited, Ahmedabad | 24AAACK8944N1Z2 | Kalthia Group, Shivdham Farm, 744, Makraba Gam, S.G. Highway, B/h Karnavati Club, Ahmedabad | piyush@kalthiagroup.com | 40583504 | 2nd RA Bill | 01.06.2021 | 01.06.2021 | 1 day
2 | Providing Rail Connectivity to berth Nos.13,14,15 & 16 from takeoff point to West end of berth at Deendayal Port Trust | Indian Port Rail & Ropeway Corporation Limited, Mumbai - 400010 | 24AADCI8930M1Z9 | 4th Floor, Nirman Bhavan, Mumbai Port Trust Building, M.P. Road, Mazgaon East, Mumbai - 400010 |  | 90000000 |  | 01.06.2021 | 01.06.2021 | 1 day
3 | Repairs and cleaning of storm water drain for cargo jetty area for a period of two years. | M/s. Premji Kanji Sorathia, Light Industrial Area, Plot No.47, 10-A, Post Box No.87, Gandhidham - Kutch | 24AAAKFM1287H1Z7 | M/s. Premji Kanji Sorathia, Light Industrial Area, Plot No.47, 10-A, Post Box No.87, Gandhidham - Kutch |  | 1209939 | 5th & Final Bill | 01.06.2021 | 01.06.2021 | 1 day
4 | R/M of Roads, SWD and removal of waste material inside and outside Harbour Area - Providing GSB in various plots in 66 Hectare area inside cargo jetty area. | M/s. Neelkanth Infratech Private Limited, Gandhidham | 24AAGCN9504P1ZZ | M/s. Neelkanth Infratech Private Limited, NEELKANTH, BBZ-S-60, Zanda Chowk, Gandhidham | 02836 220421 9825227199 info@neelkanth.co.in, www.neelkanth.co.in | 447876 | 1st & Final Bill | 01.06.2021 | 03.06.2021 | 2 days
5 | Two Years Maintenance Contract for cleaning and sweeping of office buildings & surrounding outside at New Kandla | M/s. Dhanjibhai K. Patel, 63, Ramkrishna Mahavir Nagar, Ganga Gate, Octroi Chowki, Anjar - Kutch | 24AAHFD1913C1Z4 | M/s. Dhanjibhai K. Patel, 63, Ramkrishna Mahavir Nagar, Ganga Gate, Octroi Chowki, Anjar - Kutch | dkp7600@gmail.com | 1109077 | 8th RA Bill | 05.06.2021 | 07.06.2021 | 2 days
6 | Annual Maintenance Contract of RO Plants at Kandla for year 2020-21 | M/s. Raindrops Water Technologies, 144, 145, Pushpak Industrial Estate, Phase-I, GIDC, Vatva, Ahmedabad | 24BBAPS5074A1Z0 | M/s. Raindrops Water Technologies, 144, 145, Pushpak Industrial Estate, Phase-I, GIDC, Vatva, Ahmedabad |  | 340817 | 2nd RA Bill | 05.06.2021 | 07.06.2021 | 2 days
7 | Improving the Road network inside Cargo jetty area- Providing Ashphalt paving - Stage-II | M/s. Ravji Manji Sorathia & Co., Adipur | 24AAHFR1846C2ZH | Plot No.460/461,Near Vandana Ground, Shree Khodiyar Tower, Ward – 3/B, Adipur – Kutch – 370205 |  | 11668474 | 5th RA & Pre-Final Bill | 10.06.2021 | 11.06.2021 | 1 day
8 | Deployment of equipment to remove cargo / solid waste periodically from road to maintain high standard of hygienic and to avoid pollution and contamination of cargo in Port area | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | 24ADEPK3468M1ZA | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | 02836 220421 9825227199 info@neelkanth.co.in, www.neelkanth.co.in | 774200 | 6th RA Bill | 18.06.2021 | 19.06.2021 | 1 day
9 | Upgrading the Road network of 66 hectare | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd, Village Antarjal, Adipur | 24AAFCB4960Q1Z8 | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd, Plot No.112-113, Arbuda Nagar, Survey No.10/2 & 10/3, Village Antarjal, Adipur (Kutch) 370205 |  | 22531133 | 5th RA Bill | 22.06.2021 | 23.06.2021 | 1 day
10 | Providing Rail Connectivity to berth Nos. 13, 14, 15 & 16 from take-off point to west end of berth at Deendayal Port | Sr. Divisional Finance Manager, Western Railway, Ahmedabad |  | Sr. Divisional Finance Manager, Western Railway, Ahmedabad |  | 11964303 |  | 21.06.2021 | 23.06.2021 | 2 days
11 | Construction of West Gate-II Office Building along with Landscapuing work (Phase-V) | M/s. Quality Constructions, 18, Shri Krishna Shopping Complex, Plot No.4, Ward-12/A, Gandhidham | 24AAAFQ4510B1Z1 | M/s. Quality Constructions, 18, Shri Krishna Shopping Complex, Plot No.4, Ward-12/A, Gandhidham |  | 1172115 |  | 27.06.2021 | 28.06.2021 | 1 day