## June-22
HARBOUR DIVISION
Statement showing the details of Bills of various parties and its payment status for the month of June - 2022
Sr. No. | Nature of Work | Name of firm | GSTIN | Address with Pin | Phone / Mobile No. & Email | Amount (Rs.) | Bill No. & Date | Date of Receipt | Date of forward | Time taken by Division (Days) | Date of payment | Time taken by Accounts (Days) | Total Time (Days) | Reasons for delay, if any
1 | Development of Plots, Roads & SWD in 34 hectare area inside C J area. | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd, Plot No.112-113, Arbuda Nagar, Survey No.10/2 & 10/3, Village Antarjal, Adipur (Kutch) 370205 | 24AAFCB4960Q1Z8 | M/s. Bhimji Velji Sorathia Construction Pvt. Ltd, Plot No.112-113, Arbuda Nagar, Survey No.10/2 & 10/3, Village Antarjal, Adipur (Kutch) 370205 | ravji@bvscpl.in | 29523251 | 13th RA Bill | 01.06.2022 | 01.06.2022 | 1 day
2 | Sanitization of Office Buildings, Gate offices & Public places inside & outside Cargo Jetty area at New Kandla. | M/s. Mohit Construction, B-168, NU-10-B, Gandhidham. | 24AIIPB4140N1ZF | M/s. Mohit Construction, B-168, NU-10-B, Gandhidham. | maheshanandani.adipur@gmail.com | 180000 | 1st & Final Bill | 07.06.2022 | 07.06.2022 | 1 day
3 | Two Years Maintenance Contract for Office Buildings Outside Port Area (Civil Work) | M/s. Mohit Construction, B-168, NU-10-B, Gandhidham. | 24AIIPB4140N1ZF | M/s. Mohit Construction, B-168, NU-10-B, Gandhidham. | maheshanandani.adipur@gmail.com | 600635 | 5th RA Bill | 06.06.2022 | 07.06.2022 | 2 days
4 | Sprinkling system inside Cargo Jetty area for Coal Dust Suppression in Coal Yard - AMC WORK | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | 24ADEPK3468M1ZA | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | pcc.neelkanth@co.in | 3857444 | 12th RA Bill | 06.06.2022 | 08.06.2022 | 3 days
5 | Development of Land in the West of Existing 66 hectare area for storage of cargo (Extension of custom bonded area) | M/s. Kalthia Engineering & Construction Limited, Ahmedabad | 24AAACK8944N1Z2 | Kalthia Group, Shivdham Farm, 744, Makraba Gam, S.G. Highway, B/h Karnavati Club, Ahmedabad | piyush@kalthiagroup.com | 10800502 | 12th RA Bill | 13.06.2022 | 13.06.2022 | 1 day
6 | Special Repairs to the Road along side Godown no 18, 24, 32 & 33 inside cargo jetty area. | M/s. K.K. Sorathia, J/v Hari Om Earthmovers and Transport Bhuj | 24AAJAK9127E1ZN | M/s. K.K. Sorathia, J/v Hari Om Earthmovers and Transport (Through Lead Partner : M/s. K. K. Sorathia, 11, Shree Hari Centre, Near Tree Top Hotel, Navavas, Madhapar – Bhuj | kksorathiaco@rediffmail.com | 6423902 | 1st RA Bill | 15.06.2022 | 16.06.2022 | 2 days
7 | Construction of Dome Shaped Storage Sheds Inside Cargo Jetty Area (Phase-I) | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | 24ADEPK3468M1ZA | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | pcc.neelkanth@co.in | 45112668 | 7th RA Bill | 27.06.2022 | 28.06.2022 | 2 days