## Sheet1
Category wise Seniority List For Pending Application for Dry Docking As on 22 /03/2022
Sr. | Description | Date of Application receipt | Last updation Date | Name of the Party | Name of the Vessel. | LOA (mtrs) | Page No. | File No 1131-XXVII | Tentative no. of days req. | Remarks
No.
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Vessels in the Dry Dock at presents |  |  | DPT | ML Magh | 19 | 376 |  | 5 | Ready for Docking
1 | a) Port/ Private Vessels
2 | b) Repair & maintenance to SFDD :
3 | c) Vessels belongs to Navy/Coast guard/Govt. Deptt.:
The agencies/contractors having contract with our Port and directly benefiting to our Port Provided whose craft/vessels which should have been utilized performingits work for the said contract of port and no other craftvessels shall be considered which are working at destination/ port/contract.
4
5 | General Category
| 1 | 08.09.2021 | 17.0.3.2022 | Genesis Shipping Services | Tug Adel 1 | 32 | 385 |  | 18 | Ready for Docking
| 2 | 13.09.2021 | 17.03.2022 | Genesis Shipping Services | Ocean Citrine | 49.5 | 386 |  | 20 | Slot required onorafter 4th week of March'22
| 3 | 15.09.2021 | 14.01.2022 | Polestar Maritime Ltd., | Palash star | 30.8 | 350 |  | 12 | Slot required first available slot
| 4 | 27.09.2021 |  | Genesis Shipping Services | Ocean Garnet | 67 | 160 |  | 25 | Slot required 2nd week of Dec'21
| 5 | 01.10.2021 | 14.02.2022 | Malara Shipping Pvt. Ltd., | Ocean Leader | 32 | 353 |  | 15 | Slot ready for docking 1st week of Mar'22
| 6 | 01.10.2021 | 14.02.2022 | Malara Shipping Pvt. Ltd., | Ocean Legacy | 32 | 353 |  | 15 | Slot ready for docking 2nd week of Mar'22
| 7 | 22.10.2021 | 02.12.2021 | Malara Shipping Pvt. Ltd., | Ocean Divine | 30.31 | 224 |  | 7 | Docking Programme is cancelled
| 8 | 27.10.2021 |  | Genesis Shipping Services | Ocean Opal | 49.5 | 196 |  | 20 | Slot required for 3rd week of Feb'22
| 9 | 09.12.2021 | 03.03.2022 | Genesis Shipping Services | Coastal Comd'der | 53.828 | 239 |  | 14 | Slot required for 1st week of June'22
| 10 | 20.12.2021 |  | SSR Marine Services Pvt. Ltd., | Sanghi Trishul | 93 | 246 |  | 25 | Slot required for 3rd week of June'2022
| 11 | 20.12.2021 |  | SSR Marine Services Pvt. Ltd., | Sanghi Sudarshan | 93 | 244 |  | 25 | Slot required for 4th week of May'2022
| 12 | 20.12.2021 |  | Amrut Dred. & Shg Ltd., | Priya 25 | 67.4 | 249 |  | 15 | Slot required for 1st week of Jan'22
| 13 | 22.12.2021 |  | Genesis Shipping Services | JSW Bajrang | 33.6 | 253 |  | 10 | Slot required on or after 1st week of Jan'22
| 14 | 23.12.2021 |  | Malara Shipping Pvt. Ltd., | Ocean Challenger | 32 | 260 |  | 15 | Slot required in 2nd week of March 2022
| 15 | 23.12.2021 |  | Malara Shipping Pvt. Ltd., | Ocean Champion | 32 | 261 |  | 15 | Slot required in 2nd week of March 2022
| 16 | 28.12.2021 |  | Polestar Maritime Ltd., | Tug Blue Bell | 24.8 | 278 |  | 12 | Slot required on or after 1st Week of 2022
| 17 | 03.01.2022 |  | Genesis Shipping Services | Emerald | 70 | 291 |  | 7 | Slot rquired on or after 21/01/2022
| 18 | 04.01.2022 |  | Malara Shipping Pvt. Ltd., | Sudharshan | 67 | 297 |  | 6 | Slot required 1st week of January'2022
| 19 | 05.01.2022 |  | Orion Offshore Services Pvt. Ltd., | Orion Laxmi | 43 | 301 |  | 10 | Slot required 1st week of March'2022
| 20 | 17.01.2022 |  | Patel Engineering Works | Ambuja Keerti | 80 | 313 |  | 32 | Slot required in 2nd 0r 3rd Week of Feb'22
| 21 | 17.01.2022 |  | Polestar Maritime Ltd., | Parijat | 25 | 309 |  | 12 | Slot required in 3rd week of April-2022
| 22 | 20.01.2022 |  | Polestar Maritime Ltd., | Cosmos Star | 32 | 317 |  | 12 | Slot required in 1st week of May'2022
| 23 | 28.01.2022 |  | Malara Shipping Pvt. Ltd., | Ocean Empire | 31.5 | 327 |  | 15 | Slot required in 2nd week of May'2022
| 24 | 04.02.2022 |  | Malara Shipping Pvt. Ltd., | Tug Nivarak | 30 | 337 |  | 15 | Slot required in 2nd week of April' 2022
| 25 | 04.02.2022 | 22.03.2022 | Malara Shipping Pvt. Ltd., | MV Shakti | 45.5 | 379 |  | 15 | Slot required in Last week of April' 2022
| 26 | 08.02.2022 |  | Polestar Maritime Ltd., | Tug Lilac | 38 | 348 |  | 12 | Slot required in 4th week of April' 2022
| 27 | 15.02.2022 |  | Patel Engineering Works | Relgas Vikram | 66.24 | 355 |  | 32 | Slot required in 2nd Week of October'2022
| 28 | 18.02.2022 |  | Amrut Dred. & Shg Ltd., | Kamal XL | 99.36 | 363 |  | 12 | Slot required first avaialble slot
| 29 | 07.03.2022 |  | Genesis Shipping Services | Shanti Sagar | 47 | 367 |  | 20 | Slot required first week ofMay'22
| 30 | 16.03.2022 |  | Polestar Maritime Ltd., | Orchid Star | 31.5 | 383 |  | 12 | Slot required 4th week of April'2022
| Divisional Accountant (D/D) | [6 empty] | EIC DD
| Deendayal Port Trust | [5 empty] | Deendayal Port Trust