## Sheet1
Category wise Seniority List For Pending Application for Dry Docking As on 18/10/2021
Sr. | Description | Date of Application receipt | Last updation Date | Name of the Party | Name of the Vessel. | LOA (mtrs) | Page No. | File No 1131-XXVII | Tentative no. of days req. | Remarks
No.
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Vessels in the Dry Dock at presents
1 | a) Port/ Private Vessels | 29.06.2021 | 16.10.2021 | M/s. Patel Engineering Works | ML REL GAS ISHITA | 90.07 | 156 |  | 32 | Ready for un-docking on or after 22.10.2021
2 | b) Repair & maintenance to SFDD :
3 | c) Vessels belongs to Navy/Coast guard/Govt. Deptt.:
|  | 24.03.2021 | 19.05.2021 | M/s. Patel Engineering Works | TUG GMB-I | 32 | 2 |  | 25
The agencies/contractors having contract with ourPort and directly benefiting to our Port Provided whose craft/vessels which should have been utilized performingits work for the said contract of port and no other craftvessels shall be considered which are working at destination/ port/contract.
4
5 | General Category
| 1 | 25.02.2021 | 31.07.2021 | M/s. Jevan Dredging Limited | ML Vivek Prem | 64.6 | 73 |  | 7 | Dry docks slot requested in two slots
| 2 | 09.03.2021 | 16.10.2021 | M/s. Patel Engineering Works | DSV Rel Sagar | 55 | 173 |  | 22 | Slot required 4th week of Oct'21
| 3 | 12.05.2021 | 11.10.2021 | M/s. Malara Shipping Pvt Ltd | Ocean Gallant | 34.85 | 167 |  | 15 | Slot required in 2nd week of Nov'2021
| 4 | 15.06.2021 | 31.08.2021 | M/s. Polestar Marine Ltd. | Lotus Star | 30.8 | 101 |  | 12 | Slot Required in 1st week of December,21
| 5 | 30.06.2021 |  | M/s.Emerald Marine System | MT Buraq IV | 24.5 | 50 |  | 20 | Slot Required first week of Oct, 2021.
| 6 | 22.07.2021 | 22.07.2021 | M/s. Patel Engineering Works | Relgas Virkam | 66.24 | 58 |  | 32 | Slot requiredion 1st week of March 2022
| 7 | 22.07.2021 |  | M/s. Patel Engineering Works | Reltug 18 | 31.26 | 60 |  | 12 | Slot required on 1st week of Nov'2021
| 8 | 22.07.2021 | 22.07.2021 | M/s. Patel Engineering Works | Reltug 19 | 31.26 | 63 |  | 12 | Slot required in 1st week of December 21
| 9 | 09.08.2021 |  | Adani Harbour Services LTd., | Dolphin 20 | 31.18 | 90 |  | 12 | Slot required in 1st week of November 21
| 10 | 09.08.2021 |  | Adani Harbour Services LTd., | Dolphin 21 | 32.15 | 90 |  | 12 | Slot required in 1st week of December 21
| 11 | 09.08.2021 |  | Adani Harbour Services LTd., | Dolphin 7 | 31.32 | 90 |  | 12 | Slot required in 1st week of January 21
| 12 | 16.08.2021 |  | Adani Harbour Services LTd., | Dolphin 15 | 34.5 | 93 |  | 15 | Slot required in 1st week of December 21
| 13 | 16.08.2021 | 14.10.2021 | James Mackintosh & Co. Pvt. Ltd., | Adsun Genesis | 57.5 | 172 |  | 15 | Slot required on or after 20.10.2021
| 14 | 08.09.2021 |  | Genesis Shipping Services | Tug Adel 1 | 32 | 112 |  | 20 | Slot Required first week of Feb'22
| 15 | 10.09.2021 |  | Polestar Maritime Ltd., | Tug Water Lily | 31 | 118 |  | 15 | Slot rquired 1st weeek of Jan,22
| 16 | 13.09.2021 |  | Genesis Shipping Services | Ocean Citrine | 45.74 | 123 |  | 15 | Slot required on or after 26th Nov'21
| 17 | 13.09.2021 |  | AdaniPetronet Dahej Port Pvt.Ltd., | Dolphin 6 | 31.32 | 124 |  | 15 | Slot required 1st week of Dec'21
| 18 | 15.09.2021 |  | Polestar Maritime Ltd., | Palash star | 30.8 | 126 |  | 10 | Slot required 2nd week of Jan'22
| 19 | 20.09.2021 |  | Tauras Shipping | Tug Mermaid 3 | 31.32 | 142 |  | 2 | Slot required for two days
| 20 | 27.09.2021 |  | Genesis Shipping Services | Ocean Garnet | 67 | 160 |  | 25 | Slot required 2nd week of Dec'21
| 21 | 01.10.2021 | 11.10.2021 | Malara Shipping Pvt. Ltd., | Ocean Leader | 32 | 166 |  | 15 | Slot required 3rd week of Dec'21
| 22 | 01.10.2021 | 11.10.2021 | Malara Shipping Pvt. Ltd., | Ocean Legacy | 32 | 163 |  | 15 | Slot required 3rd week of Dec'21
| 23 | 13.10.2021 |  | SSR Marine Services Pvt. Ltd., | Tug Pirotan | 35 | 171 |  | 30 | Slot required for 30 Days
EIC (DD) may confirm the date of undocking of vessels mentioned in sr. no. 1 above
| Divisional Accountant (D/D) | [5 empty] | Engineer-in-charge (M), (D/D)
| Deendayal Port Trust | [5 empty] | Deendayal Port Trust