## Sheet1
Category wise Seniority List For Pending Application for Dry Docking As on 19/01/2023
Sr. | Description | Date of Application receipt | Last updation Date | Name of the Party | Name of the Vessel. | LOA (mtrs) | Page No. | File No 1131-XXVII | Tentative no. of days req. | Remarks
No.
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | a) Port/ Private Vessels |  |  | DPT | ML Alok | 32.3 |  |  |  | Ready for Docking
2 | b) Repair & maintenance to SFDD :
3 | c) Vessels belongs to Navy/Coast guard/Govt. Deptt.:
|  | 31.12.2022 | 11.01.2023 | Malara Shipping P. Ltd., | ICGS C -156 | 27.65 | 567 |  | 12 | Ready for Docking
4 | The agencies/contractors having contract with our Port and directly benefiting to our Port Provided whose craft/vessels which should have been utilized performingits work for the said contract of port and no other craftvessels shall be considered which are working at destination/ port/contract.
5 | General Category
| 1 | 19.08.2022 |  | Amrut Dred. & Shg Ltd., | Tug Bharathiar | 31.271 | 493 |  | 18 | No Response
| 2 | 16.09.2022 |  | Patel Engineering Works | RELTUG 14 | 33 | 515 |  | 25 | Slot required in 1st week of Feb'23
| 3 | 29.09.2022 | 18.10.2022 | Shreeji shipping / Genesis | VAITARNA | 24 | 517 |  | 20 | No Response
| 4 | 28.10.2022 |  | The Adani Harbour Services | Dolphin 33 | 35.3 | 534 |  | 10 | 2nd Week of Feb'23
| 5 | 29.11.2022 | 17.01.2023 | Genesis Shipping Serv. | Ocean Divine | 32.72 | 573 |  | 15 | Ready for Docking
| 6 | 29.11.2022 |  | Genesis Shipping Services | M.T. Rakshak | 32 | 538 |  | 30 | 1st week of Jan'23
| 7 | 14.12.2022 |  | Polestar Maritime Ltd., | Tug Blue Bell | 24.8 | 547 |  | 8 | 4th Week of January 2023
| 8 | 27.12.2022 |  | Polestar Maritime Ltd., | Tug Rose Star | 31.62 | 558 |  | 12 | 2nd Week of May 2023
| 9 | 27.12.2022 |  | Polestar Maritime Ltd., | Tug Gulmohar | 31.62 | 560 |  | 12 | 2nd Week of May 2023
| 10 | 07.01.2023 |  | Noorani Shipping | Tug Ashwani | 31 | 565 |  | 12 | 3rd Week of January 2023
| 11 | 12.01.2023 |  | Patel Engineering Works | Reltug 04 | 35.3 | 572 |  | 33 | 1st Week of March 2023
| A E ( F /C ) | [6 empty] | SE ( M )
| Deendayal Port Authority | [5 empty] | Deendayal Port Authority