DEENDAYAL PORT AUTHORITY

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 28.02.2023

| Sr. No. | Name of work and location | Estimated cost (Rs.) in lakhs | Tendered Cost (Rs.) in lakhs | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 1 | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 155.70 | 144.46 96.86 towards capital cost & 47.60 towards O&M Charges. | 7.22 Below | EL/WK/2491/1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri D.K.Hazra, XEN (E) | Comprehensive A.M.C. work in progress. |
| 2 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 120.94 | 122.33 | 0.9% above | LoA issued vide MS/WK/4025-II/GIM-265 dtd. 31.03.2017 | M/s. RISHI Shipping, Gandhidham | 31/03/2017 | 10/07/2026 | Shri Rajesh Roat, (EIC) | LoA issued on 31.03.2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect upto10/07/2026. |
| 3 | Design, Manufacture, Supply Erection, Testing, Commissioning & Operation of 02 Nos .of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 91.82 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit(LC) i.e., 10/08/2017 & CAMC Work commence from 07/05/2018 | 06/05/2023 | Shri Dana Manohar, XEN(M),DPT | CAMC work in progress. |
| 4 | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 81.82 | 63.60 | 22.27 Below | EL/WK/2472/480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Comm’ned on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri D.K. Hazra, XEN(E) | Comprehensive A.M.C. work in progress. |
| 5 | Design, Supply, Installation, Testing & Commissioning of Firefighting system and associated facilities including Operation & Maintenance for a period of five years as per OISD-156 at Oil Jetty No. 08, Kandla, of Deendayal Port Authority ( EPC Contact) | 63.62 | --- | --- | --- | --- | --- | --- | --- | Price Bid opened & submitted for L1 Bidder Approval. |
| 6 | Revamping and upgradation of Fire fighting system and associated facilities at Oil jetty area- Task-I: SITC of water pump / water pumping system including AMC of 5 years. | 33.77 (37.02 with credit item of 3.25 ) | Net Rs. 38.64[i.e. Part A (EPC(SITC) Rs. 39.56 [i.e. Rs. 39.67- (minus) Rs. 0.11 discount offered in negotiation] (plus) AMC of 5 years Rs. 1.00 (minus) Part B : Credit item : Rs. 1.92] | 14.41 % Above | W.O. ML/WK/4052(Re-tender)/ 343 dated 29/07/2022 | M/s. Jay Project, Vadodara | 29/08/2022 | 28/08/2023 for SITC work & 28/08/2028 for AMC Work | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
|  | Task-II: SITC Firefighting system & associated facilities alongwith Pipeline, civil structure etc. including AMC for a period of 5 Years | 49.55 | 45.00 | 9.17% Below | W.O. ML/WK/4058/ 350 dated 01/09/2022 | M/s. Patel Construction Co., Gandhidham | 01.9.2022 | 28/02/2024 for SITC work & 31/08/2028 for AMC Work | Shri Mani Pushpak Sethi SE(M) | Work in Progress |
| 7 | Supply, installation, testing & commissioning of Sprinkling System for coal dust suppression in 34-hectare coal yard with five Years Operation & Comprehensive Maintenance contract. | 28.11 | 24.48 | 12.92% Below | MS/WK/4046-I/GIM/592 dated 18/02/2022 | M/s Omkar Enterprise, Ahmedabad | 18/02/2022 | 17/02/2023 for SITC work & 17/02/2028 of O&M work | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
| 8 | Design, Supply, installation, testing & commissioning along with Comprehensive Operation & Maintenance for a period of Five Years of 02 Nos Column Type Vessel access telescopic gangway system at Oil Jetty No. 07 and 08 of DPA | 22.83 | --- | --- | --- | --- | --- | --- | --- | Technical Bid opened & Submitted for scrutiny. |
| 9 | Design, Supply, Installation, Testing, Commissioning of Firefighting facilities as per OISD–156 including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT. | 15.34 | 16.84 | 9.76% above | Work Order: MS/WK/4052/Gim-94 Dated 30.08.2022 | M/s. Sterling And Wilson Pvt. Lltd. | 30/08/2022 | 31/03/2023 for SITC work & 31/03/2028 for O&M Work. | Shri Aman Imran B. AXEN(M) | Work in Progress |
| 10 | Comprehensive AMC for Port owned two nos. of Pilot Launches & four nos. of Mooring Launches and complete O&M for one Pilot Launch & one Survey Launch for a period of three years | 8.94 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 13/03/2023. |
| 11 | Outsourcing of 02 Nos. each Truck Mounted Mist Cannon system, and, Truck Mounted Road Sweeper system, along with comprehensive operation & maintenance, for the period of three years at DPT. | 8.93 | 10.19 | 14.12% above | MS/WK/4047/GIM-542 Dated 21/12/2021 | M/s Sambhav Corporation, Ahmedabad | 23/12/2021 | 22/12/2024 | Shri Mani Pushpak Sethi SE(M)) | Work in Progress |
| 12 | Operation and Maintenance contract of industrial light at cargo handling area, open plots, jetty area, godowns, street lighting connecting to port gates including maintenance of 11/0.433 KV substation inside cargo jetty area from zero panel to berth no. 10 and 13th to 16th berth. | 8.51 | 5.29 | 37.84% Below | Work Order No. EL/AC/2709/2092 dated 05.7.2022 | M/s. Daxraj Electricals | 05/07/2022 | 04/07/2024 | Shri D. K. Hazra XEN (E) | AMC in progress |
| 13 | Operation & Maintenance Contract of 2 Nos. Liebherr make LHM 550 model Harbour Mobile Cranes along with 03 nos. Grabs inside cargo jetty area for a period of Two years | 8.20 | 6.92 | 15.60% Below | W. O. No. EL/WK/2028 17/02/2023 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 20.02.2023 | 19.02.2025 | Shri Aman Imran B. AXEN(M) | Work in progress |
| 14 | Maintenance contract of 03 nos. 25T and 02 nos. 16 T capacity MB# crane wharf cranes, alongwith grabs for a period of 2 years at inside cargo jetty area. | 7.42 | Rs. 7.05 | 5.00% below | LOI No. EL/WK/2691/947 dated 25.02.2022 | M/s. R. S. Electricals, Gandhidham | 16/02/2022 | 15/02/2024 | Shri Dana Manohar, XEN(M) | AMC in progress |
| 15 | Supply, installation, testing & commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) unit, integral capstan and remote control type including Operation & Maintenance for five years at Oil Jetty No 08 of DPA | 6.89 | 6.43 | 6.68% below | W. O. No. MS/WK/4058/AOB-05 dated 15.02.2023 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 15.02.2023 | 14/06/2023 for SITC work & 14/06/2028 for O&M Work. | Shri Dana Manohar, XEN(M) | Work in progress |
| 16 | SPECIAL REPAIRS TO STEEL FLOATING DRY DOCK – SELF DOCKING AND REPAIRS OF PONTOON NO. - 5 & 6. | 6.60 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 16/03/2023. |
| 17 | Outsourcing of Technical Manpower & staffs for attending various technical projects & works of the department for the period of five years | 6.41 | --- | --- | --- | --- | --- | --- | --- | Tender invited with last date of Bid submission on 10/03/2023. |
| 18 | Supply, installation, testing and commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) units, integral capstan and remote control type including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT | 6.21 | 5.50 | 11.51% Below | MS/WK/4051/Gim-64 dated 04/07/2022 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 04/07/2022 | 31/03/2023 for SITC work & 31/03/2028 for O & M work | Shri Aman Imran B., AXEN (M) | Work in progress. |
| 19 | Supply, Installation, Erection, Testing and Commissioning of S/C Overhead / Underground 66KV Line for providing power supply to IOCL, Kandla. | 6.11 | 6.09 | 0.3 % below | EL/WK/2757 LOI No. EL/AC/2757/1104 | M/s. Devangi Power Private limited, | 24.01.2023 | 150days (i.e from 11th day from issue of LOI | Shri D.K. Hazra, XEN ( E) & PTC | LOI issued on 24.01.2023 (Deposit Work) Work order issued 20/2/2023. |
| 20 | Annual Rate Contract for 11 KV distribution network at license area of DPA at Kandla. | 5.95 | 4.18 | 29.74% below | LOI No EL/AC/2708(TP/1223 dated 23/02/2023 | M/s. NK Industrial Services, Gandhidham | --- | --- | Shri D.K. Hazra, XEN (E) | LOI issued. |
| 21 | Maintenance contract of 2 Nos. ITALGRU make Harbour Mobile Crane of 63T capacity along with 6 nos. of grabs and comprehensive maintenance of Hydraulic (suspension and winch) pumps inside cargo jetty area for period of two years. | 5.70 | 4.32 | 24.21% | LOI No. EL/AC/2702/650dated 05-01-2022 | M/s. Italguru India Pvt. Ltd., New Delhi | 01/01/2023 | 31/12/2023 | Shri Dana Manohar, XEN(M), | AMC in progress |
| 22 | Annual maintenance contract works at A.O. Building and Gopalpuri colony for a period of two years. | 4.96 | 3.48 | 29.84% below | W.O. No El/WK/2699/1219 dated 23/02/2023 | M/s N.K. Industrial Services | 01/03/2023 | 28/02/2025 | Shri D.K. Hazra, XEN (E) | AMC in progress |
| 23 | Supply, Installation, Erection, Testing and Commissioning of Mast Tower 34 hectares area | 4.68 | 3.46 | 26.075 % below | LOI No. EL/AC/2723 Dtd 27.02.2023 | M/s. N. K. Industrial Services, Gandhidham | 27/02/2023 | 26.12.2023 | Shri Anil Runtia AXEN ( E ) | LOI issued on 27.02.2023 |
| 24 | Comprehensive Annual Maintenance Contract for Port owned five nos. of Pilot Launches, one no. Survey Launch & two nos. of Mooring Launches for a period of two years. | 4.36 | 3.49 | 19.81% below | W.O. No. ML/WK/3992/97 dated 18.03.2021 | M/s. SSR Marine Services Pvt. Ltd., Thane | 18/03/2021 | 17/03/2023 | Shri Rajdeo Marine Engineer Gr.I | Work in Progress. |
| 25 | Comprehensive AMC of Mech works and equipment | 4.31 | 4.12 | 4.59% Below | MS/WK/4048 Dated 14/01/2022 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 15/01/2022 | 14/01/2027 | Shri Aman Imran B. AXEN (M) | Work in progress. |
| 26 | Maintenance contract of 3 Nos. 25T capacity 4 rope TIL make ELL cranes along with Grabs at Berth No. 10 at Inside Cargo Jetty area for a period of 2 years | 4.13 | 2.88 | 30.26% Below | W.O. No El/WK/2049/1247 dated 01/03/2023 | M/s. R. S. Electricals, Gandhidham | 05/02/2023 | 04/02/2025 | Shri Anil Rautiya, AXEN (E) | Work in progress. |
| 27 | Supply, Installation, Testing and Commissioning of High Mast Lighting Tower at Berth No. 14. | 4.01 | 2.78 | 30.75% | EL/WK/2655-work/745 dated 27-01-2022 | M/s. Vishal Electricals, B-4, Hans Plaza, Ambedkar Road, Ghaziabad 201001 | 27/01/2022 | 26/03/2023 | Shri D.K.Hazra, XEN(E) | Work in progress in under Extension period. |
| 28 | Comprehensive Annual Maintenance Contract for Channel Marking, Dumping and Mooring Buoys in the Kandla Channel along with operation & Maintenance of Heave up Barge Bhimsen for a period of three years. | 4.00 | Rs. 3.68 | 8.17% Below | W.O. ML/WK/4040/ 336 dated 01/08/2022 | M/s. Seacrafts Industries (P) Ltd., | 06.8.2022 | 05.08.2025 | Shri Rajdeo Kumar, Marine Engineer Gr.I | Work in progress. |
| 29 | Maintenance Contract for HT & LT Electrical, installation including substations, overhead Lines, Residential, Non-Residential, Hospital and School Buildings outside Cargo Jetty Area. | 3.98 | 3.58 | 10.18% below | EL/WK/2557/383 Dated 10.02.2020 | M/s. Sterling & Wilson Ltd | 10/02/2020 | 19/02/2023 | Shri D.K.Hazra, XEN(E) | Work Completed. |
| 30 | Upgradation of 66/11 KV GIS substation by replacement of the existing HT panel & control relay panels including civil building. | 3.40 | 3.08 | 9.35% below | EL/AC/2725/ TP/1065 Dtd: 12/01/2023. | Shree Vallabh Electricals Anand | 12/01/2023 | 330 days | Shir Anil R, AXEN (E) | Work order No. EL/WK/2725/1187. 15/02/2023 issued |
| 31 | Annual Rate contract for supply & laying of HT/LT underground cables at inside and outside cargo jetty area. | 2.61 | 2.32 | 11% below | EL/WK/2608/ 1295 dated 05/04/2021 | M/s. Onix Structure Pvt. Ltd, Rajkot | 05/04/2021 | 04/04/2023 | Shri D.K.Hazra, XEN(E) | ARC is in progress. |
| 32 | Strengthening of overhead line from thermal to port power house and oil jetty DPA, Kandla. | 2.39 | Rs.1.79 | 25.17% below | EL/AC/2686/ 3035 dated 14/07/2022 | M/s. NK Industrial Services, Gandhidham | 14/07/2022 | 13/04/2023 | Shri DK Hazra, XEN(E) | Work in progress |
| 33 | Construction of Dome Shaped Storage sheds inside cargo jetty area- Electrification work. | 1.86 | 2.26 | 22.50% Above | EL/WK/2650-II, LOI No EL/AC/2650-II/3433, dated 06.10.2022 | M/s. Vishal Electricals, Ghaziabad (UP) | 09.12.2022 | 08.06.2023 | Shri D.K. Hazra, XEN (E ) | Work in progress. |
| 34 | Major Repair Work of Heave Up Barge Bhimsen. | 1.67 | 1.56 | 6.41% below | ML/WK/4020-I(d)/156 dated 01/06/2022 | M/s. Patel Construction Co., Gandhidham | 01/06/2022 | 31/03/2023 | Shri Rajdeo, Marine Engineer Gr.I | Work in progress in under Extension period. |
| 35 | Providing power supply from 11 KV overhead line to 7th Oil Jetty and Jetty illumination at Kandla | 1.58 | 1.29 | 18.23 % | LOI No. EL/AC/2752/3037 dated 13.07.2022 | M/s. NK Industrial Services, Gandhidham | 23/07/2022 | 04/03/2023 | Shri.D.K. Hazra XEN (E) | Work in progress in under Extension period. |
| 36 | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhi-dham Area for period of three years. | 1.55 | 1.39 | 10.14% Below | DD/WK/4309/338 dated 04.08.2021 | M/s. Inspection & Engineering Services, Ahmedabad | 04/08/2021 | 03/08/2024 | Shri Himmat Makeana AXEN(M) | Work in Progress. |
| 37 | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weighbridges (15Kmph speed) of 140Mt capacities including comprehensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 1.51 | 1.48 | 2.07% below | W.O. No.ML/WK/3916-II/738 Dtd. 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., E-1, TVK Industrial Estate, Guindy, Chennai - 600032 | 05/01/2019 | 17/12/2028 | Shri Rajesh Roat, E.I.C. | Work Completed on 18/12/2021. The weighbridges installed are under guarantee period of two years under CAMC |
| 38 | Electrical work for 66 KV feeder bay GETCO Substation and for feeder bay Extension | 0.87 | 0.82 | 5.03 % below | LOI No. EL/AC/2575/ feederbay/ 3534, dated 02.11.2022 | M/s OM Power Transmission Ahmedabad | 02.11.2022 | 150days(i.e from 11th day from issue of LOI | Shri Kumthekar & PTC | Work Order issued (Deposit Work) |
| 39 | Supply, installation, testing and Commissioning of Stad-ium High Mast with LED Flood Lights for cricket ground at sports Complex, Gopalpuri | 0.77 | 0.87 | 12.78% Above | EL/WK/2077-II, W.O. No EL/WK/2077-II/3516 dated 01.11.2022 | M/s. Rajdeep Electricals Pvt Ltd., | 02/11/2022 | 01/04/2023 | Shri D.K. Hazra, XEN (E) | Work in progress. |
| 40 | Sell of renewable power generated from DPT’s 14.7MW wind power plant on Medium Term Open Access basis through tariff based competi-tive bidding through auction. | Rs. 4.26 per unit | Rs. 4.27per unit | - | LOI No. EL/C/2688/1158, dated 10.11.2021 | M/s. UPL Ltd. GIDC Jhagadia- Bharuch | 29/12/2021 | 29/12/2022 Extension till 31/12/2023 | Shri D.K.Hazra, XEN(E) | MTOA has been extended with GETCO on 29/12/2021 and valid upto 31/12/2023. |
| 41 | Operation and maintenance for operation and main-tenance of 66 KV substation. | Not Applicable | 1.00 Per Year | Not Applicable | EL/WK/2736/3043 dated 14/07/2022 | M/s. PTC India Ltd., New Delhi | 12/08/2022 | 11/08/2024 | Shri D.K. Hazra XEN (E) | Work in progress. |
| 42 | Build, Operate and Maintain of 10 nos. of 120 T capacity each Automated road weighbridges on Revenue Sharing basis at DPA for a period of 10 years and buy–back of 10 nos. of existing Road weighbridges of DPA | Tender is based on revenue sharing | --- | --- | --- | --- | --- | --- | --- | Price Bid opened & submitted for L1 Bidder Approval. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 28.02.2023

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | 49.32 Cr. | 6.62% below | No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. | M/s. Parsh Construction and Foundations Pvt. Ltd., Mumbai | 26/03/2021 | 18 months | Shri Rajesh Meghani, XEN (C) | Work Order issued vide No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. Extended vide O.O. No. OOT/C-WK/CG/7041 (Jetty)/190 dated 08/06/2022. |
| 2. | Hiring of 2 Nos. Steel Hull Mooring Launches with Crew and Mooring Gang at OOT, Vadinar for the period of Five (05) years. Estimate: Rs. 12,53,49,780/- | 12.53 Cr. | 9.12 Cr. | 27.21 % below | OOT/ME/WK/8017/484 dated 21/05/2021. | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | 14/12/2021 | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. OOT/ME/WK/8017/484 dated 21/05/2021. |
| 3. | Hiring of Service Boat for OOT, Vadinar for the period of 5 (five) years. Estimate: Rs.8,76,00,000/- | 8.76 Cr. | 9.59 Cr. | 9.49% above. | MR/WK/ 1397/66 dated 28/03/2022 | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | -- | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. MR/WK/1397/66 dated 28/03/2022. The party will deploy the Service Boat w.e.f. 22/10/2022 as per terms and conditions. Party has applied for 3 months extension and the same is under process. |
| 4. | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | No. OOT/ME/WK/3009-I/576 dated 26/12/2018. | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 5. | Painting work for residential and Non-residential buildings Port Colony at Vadinar Estimate: Rs. 2,58,32,912/- | 2.58 Cr, | 1.61 Cr. | 37.66% Below | MR/WK/ 1397/36 dated 06/09/2021 | M/s. Shreeji Enterprise Gondal | 13/09/2021 | 18 Months | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide MR/WK/1397/36 dated 06/09/2021 |
| 6. | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 Cr. | 5.01 % above | OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/1666 dated 10/01/2020. |
| 7. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.44 Cr. | 2.83% above | OOT/ME-WK/RM/6004/239 dated 04/03/2021. | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. |
| 8. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | 1.06 Cr. | 2.98% above | OOT/C-WK/RM/4002/2001 dated 12/03/2020 | M/s. Abhay Intelligence & Security Services, Vadodara. | 14/03/2020 | 2 years and extended for a period for one year | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-WK/RM/4002/2001 dated 12/03/2020 |
| 9. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | OOT/ME-WK/RM/ 6018/329 dated 26/03/2021. | M/s. Pariya Electricals, Vadinar. | 01/04/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2021. |
| 10. | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | OOT/ME/WK/RM/8009/1947 dated 03/03/2020. | M/s. Aeromarine Pvt. Ltd., Mumbai | 01/06/2020. | 3 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/RM/8009/1947 dated 03/03/2020. |
| 11. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 Cr. | 6.01 % below | OOT/ME/WK/6008/1795 dated 06/02/2020. | M/s. Safari Travels, Balasinor | 07/02/2020 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME/WK/6008/1795 dated 06/02/2020. |
| 12. | Running and Maintenance of Guest House and Staff Canteen at OOT, Vadinar Estimate Rs. 55,66,811/- | 0.56 Cr. | 0.53 Cr. | 5.61 % below | OOT/C-WK/RM4026/114 dated 29/042/2022 | M/s. Mahakal Enterprise, Jamnagar. | 01/05/2022 | 03 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide: OOT/C-WK/RM/4026/114 dated 29/04/2022 |
| 13 | Maintenance Contract of the Residential Building and Non Residential Building in Port Colony and Jetty at Vadinar. | 0.53 Cr. | 0.47 Cr. | 9.51% below | OOT/C-WK/ RM/4050-II/328 dated 29/07/2022 | M/s. G N Enterprise, Vadinar | 01/08/2022 | 02 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide: OOT/C-WK/RM/4050-II/328 Dt.29.07.2022 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 28.02.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dredging in the Navigational Channel & Alongside Cargo Berths/Oil Jetties at Deendayal Port Trust for year 2020-23”. Location At Kandla | 393.80 | 310.04 | 21.27 % Below | LOA No. EG/WK/6116/182 dated 10.03.2021 | M/s Adani Ports and Special Economic Zone Ltd., Ahmedabad | 04/09/2021 | 36 months | Shri K. Srinivasa Rao, EXECUTIVE ENGINEER ( HYDRAULIC & DREDGING), | Work in progress |
| 2 | Augmentation of liquid cargo handling capacity by revamping of existing pipeline network at Oil Jetty are, Deendayal Port Trust, Kandla | 130.49 | 126.49 | 3.05% below | PL/WK/8306 NIT-PQ/08 dated 31/08/2021 | M/s. Patel Corrrtech JV, Gandhidham | 30/09/2021 | 24 months | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 3 | Construction of Oil Jetty No.8 at Old Kandla. | 105.51 | 99.08 | 6.09% below | No.CN/WK/1571/work/243 dtd. 03/02/2021 | M/s Kargwal KM Joint Venture, Mumbai | 17/02/2021 | 18 months Extension granted upto April, 2023. | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 4 | Development of land from Junction of WG 1 & 2 to LC 236B at Kandla (Phase-1) | 81.99 | 67.67 | - | - | - | - | 18 months | Shri Rajesh Meghani, XEN(C-I) | Technical bid opened & the same is under scrutiny. |
| 5 | Development of backup area of oil Jetty No.8 to 11 (Phase-I) | 80.97 | 66.58 | 17.77% below | LOA No. EG/WK/9129/374 dated 19/10/2022. | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 21/12/2022 | 12 Months | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 6 | Development of area from Junction of West gate-I to west gate-II now renamed as "development of land west side of road in between junction of west gate 1&2 and railway line to 12th berth - Phase -I | 80.31 | 55.73 | 30.60% below | LOA No. EG/WK/8117/373 dated 17/10/2022 | M/s. Digvijay Construction Pvt. Ltd., Gandhinagar. | 07/11/2022 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 7 | Up - gradation of tuna road from two lane to four land (Phase-I) | 71.57 | 57.43 | 19.74% below | LOA No. EG/WK/8116/349 dated 03/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 10/11/2022 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 8 | Development of four lane road common corridor from LC236B to 16th CB along railway line (Phase-I) | 66.90 | 55.28 | - | - | - | - | 18 Months | Shri Rajesh Meghani, XEN(C-I) | L1 proposal under consideration |
| 9 | Upgradation of Plots & S.W.D. in 66 Hectare area inside cargo jetty area | 65.80 | 59.55 | 9.51% below | N.A. | M/s. Baldaniya Construction, Anjar. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | L1 Offer submitted for approval. |
| 10 | Retrofitting cargo berth No.8 | 64.86 | 47.27 | 27.13% Below | - | M/s. BMS Project-Marymatha JV, Kerala | 15/02/2022 | 16 Months | Shri Rajesh Meghani XEN(C-I) | Work in progress. |
|  | Retrofitting cargo berth No.9 |  |  |  |  |  |  |  |  |  |
| 11 | Development of plots, Roads & SWD in 34 hectare area inside CJA. | 57.08 | 36.60 | 35.89% below | HW/WK/2486/363 dated 20/02/2021 | M/s. Bhimji Velji Soratia Construction PLtd., | 06/03/2021 | 05/03/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 12 | Development of Backup Area and Alloed Facilities at the Existing Tuna Barge Jetty | 54.30 | 45.29 | - | - | - | - | 11 Months | Shri Rajesh Meghani, XEN(C-I) | NIT issued |
| 13 | Construction of new godowns in place of existing godown no. 19 to 21 & 25 inside C. J. Area | 53.20 | 42.94 | 19.27% below | - | M/s. Patel Construction Co. Gandhidham. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | LOA issued |
| 14 | Development of Backup Area and Allowed Facilities at the Existing Tuna Barge Jetty | 45.29 | - | - | - | - | - | 11 Months | Shri Rajesh Meghani, XEN(C-I) | NIT issued |
| 15 | Up gradation of roads & SWD outside cargo jetty area at New Kandla (Cement Concrete Pavement) | 40.35 | 24.65 | 38.88% | - | M/s. Neelkanth Infratech Pvt. Ltd., Gandhidham. | - | - | Shri Hemant Kumar Bhaskar, XEN(Road) | Submitted L1 for approval. |
| 16 | Upgradation of Plots, Roads & SWD in 40 hectare area inside Cargo Jetty Area. | 39.36 | 31.48 | 19.84% below | HW/WK/2456/579A dated 31/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd. | 22/10/2022 | 21/04/2024 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 17 | Widening of Road from Junction of WG 1 & 2 to 12th Berth | 38.50 | 32.24 | - | - | - | - | 18 months | Shri Rajesh Meghani, XEN(C-I) | L1 proposal under consideration |
| 18 | Construction of Dome shaped Storage Sheds inside C.J. Area - Phase-II | 30.63 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Scrutiny report submitted to SA (Circle Office) |
| 19 | Upgradation of Kutchha Plot C1 to C6 of 66 Hectares and SWD Network inside Cargo Jetty area. | 22.84 | 21.23 | 7.06% below | HW/WK/2545 202A dated 01/11/2022 | M/s. K.K. Sorathia J/v Hari Om Earthmovers and Transport | 15/11/2022 | 14/11/2023 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 20 | Construction of A,B, C and D type quarters at Gopalpuri | 18.94 | 13.78 | 27.16% below | TW/WK/7775/ 299 dtd. 07/06/21 | M/s. VC Project & Infra Pvt. Ltd. | 05/06/2021 | 04/06/2023 | Shri Hemant Bhaskar XEN(TD) | Work in progress |
| 21 | Development of Parking yards for trucks/vehicles for pre checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 | 14.59 | 12.87% below | HW/WK/2446/463 dated 26.06.2021 | M/s. Indian Construction Co., | 08/07/2021 | 07/07/2022 12 months work and 24 months maintenance Extension granted upt 07/03/2023. | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 07/03/2023 submitted for approval. |
| 22 | Up-gradation and strengthening of existing oil jetty No.3 | 15.78 | - | - | - | - | - | 8 months | Shri B. Rajendra Prasad, SE (P) | Tender opened & under scrutiny. |
| 23 | Retrofitting of the Bunder Basin Structures | 10.00 | 7.11 | 11.10% below | LOA No. EG/WK/8114/51 dated 25/02/2022 | M/s. Chetan Construction Co., Mehsana | 21/03/2022 | 15 months | Shri Rajesh Meghani XEN (C-I) | Work in progress. |
| 24 | Annual Maintenance contract for roads at Kandla for two years | 8.31 | 5.97 | 28.23% below | RW/WK/7810-I/239 dated 05/01/2023 | M/s. Dhanjibhai K. Patel, Anjar. | 05/01/2023 | 04/01/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 25 | Construction of Ring Road (Periphery road ) from NH-8A (From KASEZ) to Adipur | 8.20 | 6.33 | 22.8276% below | TW/WK/7804-I/418 dt.04.11.2022 | M/s. Shree Ganesh Construction, Anjar | 10.11.2022 | 09.10.2023 | XEN(TD), Shri Hemant Kumar Bhaskar | Work in progress |
| 26 | Upgradation of internal road network from West gate I to Kutch Salt Junction LC 236 | 8.10 | 7.86 | 2.92% below | LOA No.EG/WK/ 1190/33 dated 02/03/2023 | M/s. Dhanjibhai K. Patel, Anjar | N.A. | N.A. | Shri Srinivas Rao, SE (H) | LOA issued. |
| 27 | Resurfacing of Plots, Roads & SWD in 40 Hectare area inside Cargo Jetty area. | 8.09 | 7.95 | 1.68% below | HW/WK/2523/616 dated 09/12/2022 | M/s. Shree Ganesh Construction, Anjar. | 24/12/2022 | 23/07/2023 | Shri Srinivas Rao, SE (H) | Work in progress. |
| 28 | Extension of Custom Bounded area in Backup of 13th & 16th Berth | 8.02 | 5.28 | -34.24 % Below | LOA No. EG/WK/8115/264 dt. 22/06/2022 | M/s Mohit Enterprise, Rajkot | 08/08/2022 | 13 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 29 | Special Repairs of plot no 8 & 9 at bunder basin (5 hectares) | 7.99 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Submitted proposal for opening the Price Bids |
| 30 | Construction of Storage Shed Over Existing Floor of Godown No. 3 & 4 inside C. J. Area | 7.81 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Scrutiny report submitted to SA (Circle Office) |
| 31 | Improving / Upgradation of Custom Fencing Wall of Cargo jetty and Bunder Area | 7.68 | 5.38 | 29.95 % below | HW/WK/2507-I/73 dated 15/02/2022 | M/s. Deosi Govindji Parmar (Lead Partner) J/v M/s. Shree Balaji Construction Co. | 28/02/2022 | 27/02/2023 12 months | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension processed. |
| 32 | Strengthening to Residential & Non - Residential Building at New Port Colony, New Kandla | 7.56 | 4.99 | 34.05% below | - | M/s. Patel Construction Co., Gandhidham. | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Price Bid opened submitted for L1 approval. |
| 33 | Providing RCC and asphalt roads inside and outside of oil jetty area at Old Kandla | 7.12 | 4.79 | 32.76% Below | PL/WK/8490-I/189 dated 27/02/2023 | M/s. Mepabhai Mandan and Co., Adipur |  | 11 months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work Order issued. |
| 34 | S/R to quarters / building at FCI & KDLB Colony | 6.87 | 4.66 | 32.1808% below | TW/WK/7788 -I/203 dated 27/06/2022 | M/s. Ankita Construction, Adipur | 01/07/2022 | 30/09/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 35 | Appointment of Project Management Consultant (PMC) for Capital and Maintenance Dredging works of Deendayal Port Trust from firms/ consortiums Empanelled Consultants for dredging works (Class-A, Category-A) by Indian Port Association, New Delhi. | 6.36 | Rs. 5.33 | 15.32% Below | LOA No.EG/WK/6112/333 dated 15.11.2019 | M/s AECOM INDIA PVT LTD, GURGAON | 25/11/2019 | 36 months Extension grated upto November, 2023 | Shri K. Srinivasa Rao, XEN (H &D) | Work in progress |
| 36 | Appointment of technical, legal and financial experts from the firms of Transaction Advisor for "providing legal, technical and financial transactions for all ongoing and future proposals of DPA on PP / Captive Mode for the period of two years and further extendable for one year. | 5.46 | 3.60 | 34.06% below | -- | M/s. Infrastructure Development (Karnataka) Corporation Ltd (Ideck) | 14/10/2022 | 2 years and further extendable for 1 year | Shri K.J. Todarmal, SE(D) | Work is in Progress. |
| 37 | Improving & up-gradation of gardens and land scrapping at Gopalpuri (Renovation of Nehru Part and rain water harvesting by strengthening of SWD network near recharging pond at Gopalpuri | 4.79 | 2.4 | 49.81% below | TW/WK/7802-I/404 dtd.16.07.2021 | M/s. Rainbow Infrastructure, Rajkot | 03.07.2021 | 02.07.2022 | Shri Hemant Kumar Bhaskar XEN(TD) | Main Work completed. Maintenance work is in progress |
| 38 | Upgradation of Sewage treatment plant at Gopalpuri | 4.27 | 4.14 | 3.0363% below | TW/WK/7736-I/254 dated 21/07/2021 | M/s. Rajkamal Buildings, Infrastructure (P) Ltd., Gandhidham. | 01/08/2022 | 31/01/2026 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 39 | Construction of RCC Floor on surface of dismantled godown No.3& 4 inside Cargo Jetty Area. | 4.11 | 3.28 | 6.11% below | HW/WK/2535 /145 dated 21/06/2022 | M/s. Ankita Construction, Adipur | 01/07/2022 | 30/06/2023 12 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 40 | Preparing and monitoring of Environmental Management Plan for Deendayal Port Authority at Kandla. | 4.076 | 2.52 | 38.17 % below | EG/WK/EMC/11023/2011/IV dtd. 05/12/2019 | M/s Detox Corporation Pvt. Ltd. | 16/12/2019 | 36 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Existing work has completed & further frees work to be awarded to GEMI nomination base & the proposal is submitted to Board 03.02.2023 |
| 41 | Construction of Fire Brigade Station Opposite Jetty Office in CKD Yard inside Cargo Jetty Area | 3.48 | 2.94 | 15.62% below | N.A. | M/s. Murlidhar Projects | N.A. | N.A. | Shri Srinivas Rao, SE(H) | L1 Offer submitted for approval. |
| 42 | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 | Rs. 2.43 | 35.73% Below | W.O. No. HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd., Gurgaon - 122015 Haryana- India | 02/11/2021 | 36 months Extension grated upto November, 2023 | Shri K. Srinivasa Rao, XEN (H&D) | Work is in progress |
| 43 | S/R to CISF complex building & Structure at New Kandla | 3.24 | 2.40 | 26.04% below | LOA No. EG/WK/ 2185/23 dated 01/03/2023 | M/s. Acer Infra Trade, Gandhidham | - | - | Shri Hemant Kumar Bhaskar, XEN(Road) | LOA issued. |
| 44 | Maintenance of PH & UG drainage at Gopalpuri Port Colony & KDLB Colony for the period of two years. | 3.15 | 1.56 | 50.51% below | TW/WK/7813-I/ dated 05/07/2022 | M/s. Patel Construction, Gandhidham. | 05/07/2022 | 04/07/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 45 | Annual Maintenance Contract for residential and non-residential building a Port Colony, Gopalpuri for two years. | 3.05 | 1.71 | 44.12% below | TW/WK/7806-I/126 dated 30/04/2022 | M/s. Dhanjibhai K. Patel, Anjar | 02/05/2022 | 01/05/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 46 | Construction of watch tower inside cargo jetty area | 3.04 | 2.84 | 6.22% below | HW/WK/2470/ 407 dated 09/04/2021 | M/s. Viyuha Infrabuild | 24/05/2021 | 8 months Extension granted upto 22/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. Extension granted for 6 months from the date of handing over the site. |
| 47 | Special repairs to RFID cum data centre building adjoining to Seva Sadan III at New Kandla | 3.01 | 2.49 | 17.22% below | HW/WK/2582/ 284 dated 31/01/2023 | M/s. Vihat Construction, Gandhidham. | 03/02/2023 | 02/08/2023 | Shri Srinivas Rao, SE(H) | Work Order issued. |
| 48 | Deployment of equipment for cleaning of all toilet blocks inside Port area and to maintain high standard of hygienic and to avoid pollution. | 2.99 | 2.23 | 25.40% below | HW/WK/2551/202 dated 31/10/2022 | M/s. Shree Ganesh Construction, Anjar - Kutch | 01/11/2022 | 30/10/2024 | Shri Srinivas Rao, SE(H) | Work in progress. |
| 49 | Improving the fendering arrangement inside cargo jetty area HD-14/19 | 2.85 | 3.54 | 24.39% above | HW/WK/2392/137 dated 02/06/2020 | M/s. Patel Construction Co., Gandhidham | 15.06.2020 | 12 months 1st extension upto 14/12/2021 2nd extension upto 14/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 14/06/2023 submitted for approval. |
| 50 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2022-24 | 2.78 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Technical bid opened on 26/01/2023. |
| 51 | R/m of Maintenance Jetty - Repairs and Maintenance of Pontoons and Walkways of SNA Jetty and Flotilla Jetty | 2.77 | 3.37 | 10.51% above | HW/WK/2494/462 dated 25.06.2021 | M/s Patel Construction. Gandhidham | 08/07/2021 | 07/07/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 52 | Maintenance Contract for Godown inside Cargo Jetty area for two years 2022-23 & 2023-24) | 2.70 | 1.67 | 38.00% below | N.A. | M/s. Rajput Infrastructure Co. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Scrutiny report submitted to SA (Circle) |
| 53 | Annual Maintenance Contract for AO Building at Gandhidham for 02 years | 2.67 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Hemant Kumar Bhaskar XEN(TD) | Price Bid opened and submitted L1 proposal for approval. |
| 54 | Special Repairs to ATM office, Marine Bhavan, Immigration Centre Inside Cargo Jetty Area | 2.63 | 2.12 | 18.52% below | N.A. | M/s. Murlidhar Projects | N.A. | N.A. | Shri Srinivas Rao, SE(H) | L1 Offer submitted for approval. |
| 55 | Two years contract for supply and maintenance of railway tracks inside and outside cargo jetty area (for 02 years | 2.59 | 2.03 | 21.40 % below | HW/WK/2487/359 dated 20/02/2021 | M/s. Laxyo Entergy Ltd. | 06/03/2021 | 05/03/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress |
| 56 | Resurfacing of road from KK road junction to Mithirohar GIDC at Kandla | 2.52 | 2.56 | 1.68% above | LOA No. EG/WK/ 5849/423 dated 10/11/2023 | M/s. Ravji Manji Sorathia & Co., Adipur. | - | - | Shri Manoj Gohel, XEN(R) | Pre-Acceptance letter issued on 10/01/2023. |
| 57 | S/R to AO Building at Gandhidham - Renovation of toilet blocks, recreation room, old board room | 2.20 | 1.32 | 40.1319% below | TW/WK/7795-I/ 111 dt. 21/04/2022 | M/s. Ankita Construction, Adipur | 25/04/2022 | 24/04/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 58 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2020-22 | 2.19 | 1.15 | 47.36% below | TW/WK/7781-I/ 621 dt.14/10/2020 | M/s. Rajput Infrastructure, G’dham | 15/10/2020 | 14/10/2022 Extension is granted upto 14/02/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. Applied for extension upto to 14/02/2023. |
| 59 | House Keeping & Cleaning of Building of Office building and surrounding outside Cargo Jetty Area for the year 2021-23. | 1.97 | 1.07 | 45.36 % below | HW/WK/2538/68 dated 07/02/2022 | M/s. Rajput Infrastructure Co. , Gandhidham | 22/02/2022 | 21/02/2024 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 60 | Maintenance Contract of Fenders inside Cargo Jetty Area for two year 2022-23 & 2023-24) | 1.97 | 2.14 | 12.17% above | N.A. | M/s. Patel Construction Co., Neelkanth, B.B.Z. S-60, Gandhidham | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Tender is discharged and re-invitation is under process for approval. |
| 61 | Maintenance contract for roads and RCC culverts inside CJA at New Kandla for 02 years | 1.75 | 1.84 | 5.74 % above | HW/WK/2443/401dated 31.03.2021 | M/s Shree Ganesh Construction | 16/04/2021 | 15/04/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 62 | Two years maintenance contract for office building outside Port area (Civil Work) | 1.63 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Scrutiny report submitted to SA (Circle Office) |
| 63 | Providing Labour amenities centre at various locations inside Cargo Jetty Area. | 1.53 | 1.18 | 22.85 % below | HW/WK/2461/60 dated 25/01/2022 | M/s. Rajput Infrastructure Co. | 08/02/2022 | 07/02/2023 12 Months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 64 | Providing RCC drinking water tank. | 1.52 | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad B., SE (PL) | Technical bid under evaluation. |
| 65 | AMC for White Washing, Distempering, Painting to Res. & Non-resi. Bldg. at G’puri, KDLB, G’dham & Adipur for the year 2022-23 | 1.45 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar, XEN(TD) | Processed for opening of Price bids. |
| 66 | Appointment of Independent Engineer for the work of “Development of Marine Liquid Terminal Facilities consisting of SPM and Two Product Jetties in KPT waters at OOT, Vadinar for Handling Crude and Petroleum Products on Captive Use Basis”. | 1.44 | 1.18232 | 17.89% below | Work Order No.EG/WK/4823(IE)/109 dated 22/10/2019 | M/s RINA Services s.p.A,Mumbai | 01/11/2019 | 42 months | Shri K.J. Todarmal, SE(D) | As concessionaire has not started construction activity, the work order issued to M/s. RINA has been kept in abeyance. |
| 67 | Third Party Inspection and Quality Inspection and Quality Assurance for the works costing more than Rs. 1.00 Cr. of Civil Engineering Department of Deendayal Port Authority. | 1.358 | 1.17 | 14.05% below | Work Order No.EG/WK/5212/53 dtd.16/10/2021 | M/s. VCS Quality Services pvt. Ltd., Mumbai | 25/10/2021 | 24/10/2023 | Shri Sunil Soren, XEN(D) | Work in Progress. |
| 68 | Maintenance Contract for Non-residential buildings inside Harbour area (Civil Work) | 1.31 | 0.95 | 27.55% below | HW/WK/2526/122 dated 20/04/2022 | M/s. Mepabhai Mandan & Co., Adipur | 05/05/2022 | 04/05/2024 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 69 | Strengthening of existing environmental management cell at DPT: Appointment of environment experts for two years and further extendable for one year | 1.232 | 1.20 | 2.60% below | EG/WK/ 4783/V/131 dtd.05/02/21 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15/02/2021 | 14/02/2023 24 months Extension granted upto 15/02/2024 | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 70 | Two years maintenance contract for Railway track leading to Tuna from 0 to 11 Km KPT Line (Take off Point at 2.573 Km at GIM Yard to 13.54 Km including LC-1, LC-2) | 1.19 | 0.908 | 23.77% below | HW/WK/2515/432 DATED 31/05/2021 | M/s Patel Construction. Gandhidham | 14/06/2021 | 13/06/2023 24 Months | Shri Srinivas Rao, SE (H) | Work in progress |
| 71 | Dismantling of existing godown no.19 to 23 inside cargo jetty area | Part A 0.26 and PART ‘B’ 0.93 (Credit item) | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE (H) | Revised scrutiny report submitted SA (CE) |
| 72 | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years | 1.13 | 0.82 | 27.27% below | PL/WK/8461-I/25 dated 09/02/2022 | M/s. Sanjay K Sorathiya & Co. | 09/02/2022 | 24 Months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in Progress |
| 73 | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla. -HD-07/19 | 1.12 | 1.20 | 7.21% above | HW/WK/2379-III/332 dated 05/12/2019 | M/s. Patel Construction Co. | 18/12/2019 | 12 months 1st Extension upto 17/12/2021. 2nd extension upto 17/06/2022 | Shri Srinivas Rao, SE (H) | Work in progress. Proposal for extension upto 17/06/2023 submitted for approval. |
| 74 | Maintenance contract for quay and transit area inside cargo jetty area for two years | 1.04 | 0.87 | 16.77% | HW/WK/2617/12 dated 24/09/2021 | M/s. Sanjay K Sorathiya & Co. | 10/10/2021 | 09/10/2023 24 Months | Shri Srinivas Rao, SE (H) | Work in progress |
| 75 | Maintenance Contract for Tree Plantation near offices, other buildings, along roads, islands, gates, etc. inside/outside cargo jetty area for two years | 0.97 | 0.62 | 35.82% below | LOA No. EG/WK/ 1173/03 dated 16/02/2023 | M/s. Vihat Construction, Gandhidham | - | -- | Shri Srinivas Rao, SE(H) | LOA issued. |
| 76 | Maintenance Contract for Residential & Non - Residential Building at New Port Colony at New Kandla for two years. | 0.97 | 0.62 | 36.20% below | RW/WK/7816-I/242 dtd. 17/10/2022 | M/s. Murlidhar Projects | 17/10/2022 | 16/10/2024 | XEN(Road), Shri Hemant Kumar Bhaskar | Work in progress. |
| 77 | Dismantling of Residential and Non - Residential buildings at New Kandla | 0.96 | 1.58 | 64.42% above | RW/WK/7706-I/19 dtd.08.12.2021 | M/s. Symcom Exim (P) Ltd., Mumbai | 16.12.2021 | 15.08.2022 | XEN(Road), Shri Hemant Kumar Bhaskar | Work is under dispute and the matter is referred to court |
| 78 | AMC for Sports complex at G,puri for the period of 2 yrs | 0.93 | - | - | - | - | - | - | Shri Hemant Bhaskar, XEN(TD) | Submitted for the approval to discharge the tender and to re-invite with some modification. |
| 79 | Running & housekeeping of Guest house, A-9 bungalow & bachelor accommodation / bungalow at Port colony, Gopalpuri, Gandhidham for 03 years | 0.90 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(Road) | Technical bid opened on 21/11/2022 and sent for approval. |
| 80 | Providing firefighting pipeline at 34 hectares inside cargo jetty area (A) Appointment of Technical Advisor for the work of Upgradation of firefighting system & associated facilities inside cargo jetty area. DPA | 0.86 | 0.80 | 6.39% below | PL/WK/8476-I/21 dated 21.12.2022 | M/s. S.R. Engineers | 26.12.2022 | 18 months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in progress |
| 81 | Two years contract for cleaning of storm water drain inside cargo jetty area | 0.78 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Srinivas Rao, SE(H) | Scrutiny report submitted to SA (Circle Office) |
| 82 | White washing, painting & distempering to residential and non-residential buildings & CISF complex at New Port Colony, New Kandla (for 2 years) | 0.67 | 0.38 | 43.20% | RW/WK/7790-I/ dated 05/2022 | M/s. Rajput Infrastructure Co., Gandhidham. | 01/06/2022 | 31/05/2024 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress. |
| 83 | Annual Maintenance Contract for Sanitation of New Port Colony, New Kandla | 0.64 | 0.34 | 46.36% above | RW/WK/7808-I/394 dtd. 10/01/2022 | M/s. Rajput Infrastructure Co., Gandhidham | 11/01/2022 | 10/01/2023 | Shri Manoj Gohel XEN(Road) | Work in progress. Extension of 3 months submitted for approval. |
| 84 | Maintenance contract for cleaning of SWD, along road sides for two (2) years (J.N. Road, Link Road, Bye Pass Road and outside cargo jetty etc) at New Port Colony , New Kandla | 0.58 | 0.34 | 41.40% below | - | M/s. Vihat Construction Co. Adipur | - | - | Shri Hemant Kumar Bhaskar XEN(Road), | Proposal to discharge the tender is submitted to competent authority. |
| 85 | House keeping & cleaning of office building inside cargo jetty area (for 2 years) HD-10/19 | 0.54 | 0.4128 | 23.43% below | HW/WK/2422-I/367 dated 20/02/2021 | M/s. Shree Ganesh Construction, Anjar | 06/03/2021 | 05/03/2023 24 months | Shri Srinivas Rao, SE (H) | Work in progress. |
| 86 | Maintenance Contract of 1.5 MLS Sewage treatment plant at New Port Colony, New Kandla for 2 years | 0.52 | 0.29 | 45.13% below | RW/WK | M/s. Gadhvi Construction Co., | 21/06/2022 | 20/06/2024 | Shri Manoj Gohel XEN(Road), | Work in progress. |

MEGA INFRASTRUCTURE PROJECTS

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 87 | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT basis under PPP mode | 4243.64 | NA | NA | Tender No. CE/13 | M/S Hindustan Infralog Private Limited | LOA Awarded Dated 28/01/2023 | 36 months from the date of award of concession | Shri K. J Todarmal S.E (Design) | RFP opened on 27.01.2023, M/S Hindustan Infralog Private Limited declared as successful Bidder . |
| 88 | Development of multipurpose cargo (other than container/ liquid) berth off Tuna Tekra outside Kandla Creek at Kandla on BOT basis | 1719.22 | NA | NA | Tender No. CE/14 | NA | under Bidding stage | 30 months from the date of award of concession | Shri K. J Todarmal S.E (Design) | RFP yet to be received and yet to be opened. Date of submission RFP 11/04/2023. |
| 89 | Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis | 448.00 | NA | NA | Tender No. 05/SE(D) Dated 16.11.2013 | M/s Nayara Energy Limited (formerly Essar Oil Limited) | Work not yet started | 36 months from date of award of concession (Revised : 42 months from date of award of concession) ( six months extension granted by DPT due to COVID 19 Force Majeure) | Shri K. J Todarmal S.E (Design) | Concessionaire not yet started the construction of project |
| 90 | Development of Oil Jetty to handle liquid cargo and ship bunkering terminal at Old Kandla on BOT basis | 343.00 | NA | NA | Tender No. 026/XEN (Design) Dated 16.04.2015 | M/s IMC Limited | 11.12.2020 | 24 months from date of award of concession | Shri K. J Todarmal S.E (Design) | Delayed in Construction |

Ro-Ro / Ro-Pax Ferry Service Cell

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 91 | Maintenance Dredging at Underneath/Periphery of Landing Pontoon of Ro-Pax facility at Dahej Terminal for 12 Months. | 2.43 | 2.22 | 8.5926% (Below) | Work Order No. CN/WK/1600/DAHEJ/17-A DATED – 11/05/2021 | M/s. Divine Shipping Services, Ahmedabad | 12-05-2021 | 12 Months Extension granted upto 10/01/2023 | Shri Rajendra Prasad Bethi, SE(P) | 1st extension from 11.05.2022 to 10.09.2022 and 2nd extension from 11.09.2022 to 10.01.2023 has been approved by Competent authority. |
| 92 | Construction of RORO/ROPAX facility at Muldwarka, Gujarat. | 84.74 | 76.69 | 9.5% (Below) | LOA No.CN/WK/1600-Const/Muldwarka/7 dated 14/01/2022 | M/s. BMS Projects – Marymatha JV | 10-05-2022 | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | Interim W/O for fabrication of Pontoon and Linkspan at Hazira, awarded on 10/05/2022. Final W/O shall be awarded after receipt of EC & CRZ. |
| 93 | Dredging in Approach channel Turning Circle, Berth pockets and surroundings of landing pontoon etc at Ghogha Ro-Ro Terminal Gujarat. | 28.63 | 45.81 | 60% (Above) | Work Order No. CN/WK/1600- GHOGHA (7BCD)/51 Dated – 25/04/2022 | M/s. Rock & Reef Dredging Pvt Ltd., Navi Mumbai | 25-04-2022 | 4 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. 4 months extension from 23.08.2022 to 15.12.2022 and 2nd extension from 16/12/2022 to 31/03/2023 has been granted by competent authority subject to ratification of Board |
| 94 | Monitoring for smooth functioning of Ro-Ro Facility services located at Hazira, Dahej and Ghogha. | 1.95 | 1.67 | 14.36% (Below) | Work Order No. CN/WK/1600/38 Dated – 29/03/2022 | M/s. Dhanjibhai K Patel | 01-04-2022 | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress |
| 95 | Construction of Ro – Ro / Ro-Pax On – Shore facility at Muldwarka – Gujarat, EPC mode. | 30.81 | 33.88 | 9.97% (Above) | Work Order No.CN/WK/1600/Onshore Muldwarka/137 dated 15.07.2022 | M/s. MMC Projects (India) Pvt Ltd., Gandhidham | 25-07-2022 | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | Work Order issued. |
| 96 | Annual Maintenance contract of Linkspan Pontoon and Terminal facilities of Dahej & Ghogha Ro-Pax ferry terminal | 3.90 | 3.90 | - | Supplementary Work Order No. CN/WK/1600/55 Dated – 09/07/2021 | M/s. Vishwakarma Mechanical works, Porbandar | 08-03-2019 | 07-03-2021 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Proposal for extension of work from 07.09.2021 to 06.07.2023 (22 months) and Anticipated variation statement No.2 with extra items for net excess of Rs.3,94,36,435.00 i.e. 101.11% excess on the tendered cost of Rs.390.04 lakhs submitted for Board Approval in its meeting on 03.02.2023 |
| 97 | Annual Maintenance Contract of Navigational Channel Marking System (Buoys) at Ghogha Ro-Pax | 0.86 | - | - | - | - | - | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Technical bid opened on 29/09/2022. Two bids received. Price Bids opened on 06/01/2023. |
| 98 | Annual Maintenance Contract of Navigation Channel Marking System (Buoys) at Dahej & Ghogha – Ro Pax Online Tender ID 383191 | 0.48 | 0.48 |  | Supplementary Work Order No. CN/WK/1600/49 Dated – 29/06/2021 | M/s. Sai Sagar Dredging & Marine Services Pvt. Ltd., Bharuch | 03-03-2020 | 02-03-2021 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Proposal for extension of work from 02/09/2021 to 01/07/2023 (22 months) and Anticipation Variation Statement No.2 for net excess of Rs.75,69,087/- i.e. 156.26% excess on the tendered cost of Rs.48,43,830/- submitted for Board approval in its meeting on 03.02.2023. |
| 99 | Annual Maintenance Contract for Link spans, Pontoons and Terminal facilities at Ghogha | 2.99 | - | - | - | - | - | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Tender Re-invited. Preliminary bids scheduled to be opened on 27/03/2023. |
| 100 | Annual Maintenance Contract for Link Spans, Pontoons and Terminal facilities at Dahej | 3.00 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | Proposal to discharge and reinvite the tender is submitted for approval. |
| 101 | Annual Maintenance contract for Navigational Channel marking system (Buoys) at Dahej - Ro- Pax | 3.69 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | Bids opened on 10/11/2022. 2 bids received. Competent authority approved the proposal for discharge and reinvite the tender. |
| 102 | Maintenance Dredging at Periphery of landing pontoon of Ro-Pax facility at Dahej Terminal for 12 months | 2.22 | - | - | - | - | - | 12 months | Shri Rajendra Prasad Bethi, SE(P) | Technical Bids opened on 16.11.2022. Four bids received. Price bids opened on21/02/2023. |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No | Name of work & location | Reserve price Per sq. mtr./year | Premium received over and above reserve price during e-auction (per sq. mtr. / per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 103 | E-tender cum E-auction is for allotment of plot no. 08, ADMG. 11,695.00 sq. mtrs. (including structures) situated to the west of link road connecting Old Kandla for construction of liquid chemical storage installation on 30 years lease basis | Rs. 1060.10 | Rs. 20 | LW/PL/3483-I/522 DATED 16.05.2022 | M/s. Shreeji Power & Insulators Pvt. Ltd. | 30 years from date of Possession | Shri S.K. Rao. SE (KL) | E-auction has been carried out on 28-01-2022. pre-acceptance letter issued on 19.03.2022. Party had made payment of Advance Lease Rent & Security Deposit. Accordingly allotment letter was issued on 16.05.2022. Lease deed is under execution. |
| 104 | E-Tender cum E-Auction for the allotment of Various size of plots for Salt manufacturing and salt related activities in between Village Veera to Village Jhungi on 30 years lease on as is where is basis. | Rs. 25923.30 (per acre/per annum) | Plot No.1-Rs.200 Plot No.2- Rs.400 Plot No.3 Rs.500 Plot No. 5 Rs.200 Plot No. 6 Rs.200 Plot No.07 Rs.300 Plot No.08 Rs.4200 Plot No. 09 Rs.4100 Plot No.10 Rs.700 | Plot No.01 LW/PL/3507-I/605 DATED 14.06.2022 Plot No.02 LW/PL/3507-I/607 DATED 14.06.2022 Plot No.03 LW/PL/3507-I/603 DATED 14.06.2022 Plot No.05 LW/PL/3507-I/604 DATED 14.06.2022 Plot No.06 LW/PL/3507-I/601 DATED 14.06.2022 Plot No.07 LW/PL/3507-I/602 DATED 14.06.2022 Plot No.08 LW/PL/3507-I/609 DATED 14.06.2022 Plot No.09 LW/PL/3507-I/606 DATED 14.06.2022 Plot No.10 LW/PL/3507-I/608DATED 14.06.2022 | Plot No.1 - M/s. Priya Salt & Chemicals Pvt. Ltd. Plot No.2 - M/s. Shri Pingleshwar Salt Industries. Plot No.03 - M/s. Lakshmiwadi Mines & Minerals Pvt. Ltd. Plot No. 5 - M/s Patel Salt & Alied Industries Plot No.06 - Aashwat Salt and chemicals Pvt. Ltd. Plot No.07 - M/s Daivya Salt & Chemicals pvt. Ltd. Plot No. 8 - M/s Patel Salt & Allied Industries Plot No. 09 & 10 - M/s. Shamji Kangad & Co. | 30 years from date of Possession | Shri S.K. Rao. SE (KL) | Online Price Bids opened on 03.03.2022.E-Auction of plots was carried out on 06.06.2022 to 10.06.2022. Pre acceptance letter issued on 13.06.2022. Allotment letter issued on 14.06.2022 & Possession was given on 15.06.2022. Lease Deed is under execution. |
| 105 | E-Tender cum E-Auction for the allotment of plot Admg. 4000 Sq/Mtrs situated opposite to VTMS towers and behind boundary of DPT (East of dry dock) for the purpose of Barge Repairing/Beaching on 5 years lease basis on as where is basis. | Rs. 277.12 | Rs. 20 | LW/PL/3493/633 DATED 15.06.2022 | M/s. Amrut Dredging & Shipping Ltd. | 30 years from date of Possession | Shri S.K. Rao. SE (KL) | The tender has been re-invited and price bid opened on 27.04.2022. E-auction was carried on 05.05.2022 Board vide Resolution No.25 dated 27/05/2022. approved the proposed for allotment of Land to M/s. Amrut Dredging And Shipping Ltd. Accordingly, Pre-Acceptance Letter is issued on 08/06/2022. Allotment letter was issued on 15.06.2022 & Possession of Land given on 01.07.2022. Lease Deed is under execution. |
| 106 | E-tender cum E-auction for the allotment of various size of plots for the purpose of Godowns/Warehouses situated at Kandla on 30 years lease on as is where is basis. | Rs. 231.86 , Rs. 151.36 & Rs.217.15 | plot No.31-Rs.10 Plot No.33- Rs.10 Plot No.34 Rs.10 Plot No. 35 Rs.10 Plot No. 38 Rs.10 Plot No.39 Rs.10 Plot No.52 Rs.10 Plot No. 53 Rs.10 | Plot No.31 LW/PL/3526-I/45 DATED 27.07.2022 Plot No.35 LW/PL/3526-I/46 DATED 27.07.2022 Plot No.39 LW/PL/3527-I/47 DATED 27.07.2022 Plot No.52 LW/PL/3527-I/48 DATED 27.07.2022 Plot No.38 LW/PL/3527-I/49 DATED 27.07.2022 Plot No.34 LW/PL/3527-I/43 DATED 27.07.2022 Plot No.33 LW/PL/3527-I/44 DATED 27.07.2022 Plot No.53 LW/PL/3527-I/137 | Plot No.31 - M/s Friends Salt works & Alied Ind. Plot No.33-M/s Friends Salt Works & Alied Ind. Plot No.34-M/s Friends Salt Works & Alied Ind. Plot No.35-M/s Friends Salt Works & Alied Ind. Plot No.38-M/s Shreeji Exports Plot No.39-M/s Friends Salt Works & Alied Ind. Plot No.52-M/s Shiv Shipping Services Plot No.53 M/s. Shidhivinayak Warehousing | …. | Shri S.K. Rao. SE (KL) | Pre- bid meeting held on 03-02-2022. Pre-Bid querries finalized Technical Bid opened on 31.03.2022. Price-bid opened on 04.05.2022. E-Auction was carried out on 24-05-2022. Pre-acceptance letter issued on 22.06.2022 to 08 bidders. 08 Parties had made payment of Advance Lease Rent & Security Deposit. Accordingly allotment letter was issued on 27.07.2022 & 06.09.2022 to 08 parties. Possession of Land given on 03.09.2022 to M/s. Shiv Shipping Services & on 28.09.2022 to M/s Shreeji Exports and M/s. Shidhivinayak Warehousing & on 10.10.2022 to M/s Friends Salt Works & Allied Industries. M/s Shiv Shipping Services lease deed executed on 15.12.2022 & M/s. Shreeji Export executed Lease Deed on 19/01/2023 & other parties' Lease Deeds are under process. |
| 107 | E-tender cum E-auction for allotment of 06 Nos. of plots (with structure) situated at old/new Kandla for the purpose of liquid storage tanks (products permitted in the earlier Lease Deed/ Allotment Letter) on 30 years lease on as is where is basis(Phase-I). | Rs. 1060.56 | Rs.30 (Area 14250) Rs.10 (Area 13770) Rs.10 (Area 25000) | …. | M/s Samayak Steel Company (14250) M/s M.R. Shah Logistic Ltd. (13770) M/s CRL Terminals Private Limited (25000) | …. | Shri S.K. Rao. SE (KL) | NIT published on 27/04/2022,pre-bid meeting held on 04/05/2022. Technical bid OPENED on 11.10.2022 .price bid opened on 28.12.2022. E-Auction was carried out on 16-01-2023 to 17.01.2023. In auction single bid received on Sr No. 01,03, & 06. Re-invite the E-tender cum E-auction for 03 nos. of plots in which single bid are recieved on same terms and conditions as approved by the Board vide resolution No.44 except submission of the Solvancy Certificates which is deleted as per the Finance dept. Note No. FA/WA/Tendering/1475 dated 04.01.2022, keeping the reserve price of Rs.1081.77 (G1 category). |
| 108 | E-tender cum E-auction for allotment of 04 Nos. of plots (with structure) situated at old/new Kandla for the purpose of liquid storage tenks (products permitted in the earlier Lease Deed/ Allotment Letter) on 30 years lease on as is where is basis(Phase-II). | Rs. 1060.56 | …. | …. | …. | …. | Shri S.K. Rao. SE (KL) | NIT published on 27/04/2022,pre-bid meeting held on 04/05/2022.Date of opening of tender extended up to 28.02.2023 |
| 109 | E-Tender-cum-e-auction for allotment of land admeasuring 2772.00 Sq. Mtrs. (with structure) for the purpose of Service Station cum petrol pump on 30 years lease on as is where is basis. | Rs. 1060.55 | Rs.20 | ….. | M/s. Shree Ashapura Stevedores, | ….. | Shri S.K. Rao. SE (KL) | NIT published on 19/10/2022,pre-bid meeting held on 01/11/2022. Price Bid opened on 28/12/2022. E-auction carried on 09.01.2023. Pre acceptance letter issued on 19.01.2023. Allotment letter issued on 24.01.2023 & Possession was given on 31.01.2023. Lease deed is under execution. |
| 110 | E-Tender-cum-e-auction for allotment of 04 Nos. of plots for the purpose of Liquid Storage Tanks situated at Kandla on 30 years Lease on as is where is basis. | Rs. 1060.56 | …… | ….. | …… | ….. | Shri S.K. Rao. SE (KL) | NIT published on 04/01/2023,pre-bid meeting held on 16/01/2023. Opening of technical bid 15.03.2023 |
| 111 | E-Tender-cum-e-auction for allotment of 06 Nos. of Plots for the purpose of Godown / Warehouse situated at Kandla on 30 years Lease on as is where is basis. | Rs.231.86 | …… | ….. | …… | ….. | Shri S.K. Rao. SE (KL) | NIT published on 03/01/2023,pre-bid meeting held on 16/01/2023. Opening of technical bid 28.02.2023 |
| 112 | E-Tender cum e-auction for allotment of 3 Nos. of Plots (with structure) situated at Old / New Kandla for the purpose of Liquid Storage Tanks (Products permitted in the earlier Lease Deed / Allotment letter) on 30 years Lease basis on as is where is basis. | 1081.77 | …… | ….. | …… | ….. | Shri S.K. Rao. SE (KL) | NIT published on 28/02/2023,pre-bid meeting held on 10/03/2023. Opening of technical bid 27.03.2023 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6 .	MARINE DEPARTMENT							                                                                                      AS ON 28.02.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | - | Executed on 09/03/2022 | M/s. Electronics Corporation of India Ltd., Hyderabad | 25/11/2021 | 24 months for supply, installation and commissioning AMC 10 years after installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Supply & Installation work completed on 25/11/2020. AMC work in progress. |
| 2. | Hiring or 2 Nos. of Steel Hull Mooring Launches and Moorings Gangs at Deendayal Port, Kandla for a period of 5 years. | 14.60 Cr. | 10.76 Cr. | 26.24% below | Yet not executed | M/s. Pacific Shipping Services, Mumbai | Yet not commenced | 5 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 28/09/2022 Work Order issued on 02/11/2022 |
| 3 | Hiring of 04 Nos. of 50/60 tonn Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below Estimated Cost-OSL Ltd. 20.08% below Estimated Cost - KNK Ship | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator | Board vide Resolution No. 56 in its meeting held on 12.08.2016 have approved to award the work to contractors. W.O. has been issued on 03/10/2016 & 22/09/2016. |
| 4 | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | 26/04/2021 | 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 13/10/2020. Work Order issued on 05/01/2021. |
| 5 | Renewal of Steal Plates & painting of various crafts / Tugs of DPT | 2.09 Cr. | 1.80 Cr. | 14.19% below | Executed on 16/06/2021 | M/s. Patel Engineering Works, Gandhidham. | 06/08/2021 | 2 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 21/05/2021. Work Order issued on 13/07/2021. |
| 6 | Hiring of 165 Nos. of Manpower in the cadre at Firefighters for Port services at DPA, Kandla on Contractual basis for a period of 3 years. | 6.58 Cr. | 6.38 Cr. | 12.93% below | Yet not executed | M/s. Krishna Industrial Security & Fire Services Pacific Shipping Services , Anand Gujarat. | Yet not commenced | 3 years | Capt. Pradeep Mohanty,, Deputy Conservator | LOA issued on 13/02/2023. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 28.02.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |
| 2. | Hiring of brand new make and model of 2018 on "monthly hire basis" and made and model not earlier than1st January, 2017 on "as and when required basis" diesel vehicles to DPT for a period of 03 years | 8.60 Cr. | 8.23 Cr. | 4.34% below | Executed. | M/s. Shree Ganesh Travels, Mumdra | 01/01/2019 | 30/09/2022 Extension for further period of 3 months w.e.f. 01/07/2022 or till the finalization of new contract, whichever is earlier granted vide letter No. GA/GN/5240/2018/1554 dated 23/06/2022 | Shri Shailendra Paney, Sr. Asstt. Secretary. | Work in progress. Extension for further period of 3 months granted w.e.f. 01/01/2023 or till the award of new contract, whichever is earlier vide letter No. GA/GN/5240 /2018/2938 . dated 27/12/2022. |
| 3. | Engagement of Security Agency for providing Watch & Ward Security Supervisors & Security Guards without arms for various Departments of DPA for the period of 02 years. | 5.92 Cr. | 5.13 Cr. | 13.34% blow | Executed Work Order No. ES/SR/2443/ Security/1 dated 26.03.2021 ES/SR/2443/ Security/2 dated 26.03.2021 ES/SR/2443/ Security/3 dated 26.03.2021 | M/s. Shakti Secuirty, Surat. M/s. Panther Surveillance, Ahmedabad. M/s. Rajput Security Services, Ahmedabad. | 26/03/2021 | 25/03/2023 | Shri Omprakash Dadlani, TP & PRO & Nodal Officer, (Security) | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	MEDICAL DEPARTMENT										                                            AS ON 28.02.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |
| 2 | Outsourcing of Vadinar Hospital for treatment of employees of DPA, CISF Personnel and CISF employees engaged by DPA and IOCL and their family members as well as other persons as decided by DPA at Vadinar | 2.88 Cr. | 2.07 Cr. | 26.80% below | MH/SP/85/ 2020-21 | M/s. Shree Samarpan Wellness Pvt. Ltd., Rajkot | 16/05/2022 | 3 years. | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	TRAFFIC DEPARTMENT											                	AS ON 28.02.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Engagement of manpower service provider for providing various categories of outsourced staff to carry out railway operation inside Cargo Jetty area for a period of 3 years. | 3.88 Cr. | 2.87 Cr. | 26.00% below | Executed on dated 26/07/2021 | M/s. Dhanjibhai K. Patel, Anjar. | 01/05/2021 | 30/04/2024 | Shri T.D. Maheshwari, ATM (Railway), | Work in progress. |
| 2. | Outsourcing of Establishing and operating of occupational health services at Deendayal Port Authority, New Kandla for the period for 5 years. | 3.54 Cr. | 2.98 Cr. | 16.59% below | Executed on dated 15/12/2021 | M/s. Accord Multispecialty Hospital, Bhuj | 15/05/2021 | 5 years from the date of commencement | Safety Officer | Work in progress. |
| 3. | Engagement of Consultant to authenticate / validate the reports submitted by the PPP Operator for three (3) years | 2.56 Cr. | 2.77 Cr. | 9.99% Above | Executed on dated 10/10/2022 | M/s. Aarvee Associates Architects Engineering & Consultant Pvt. Ltd., Hyderabad | 17/10/2022 | 16/10/2025 | Asstt. Traffic Manager (PPP) | Work in progress. |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

9.	FINANCE DEPARTMENT										                                     AS ON 28.02.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |  |  |  |  |  |  |  |  |  |  |

*****