DEENDAYAL PORT AUTHORITY

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 30.06.2023

| Sr. No. | Name of work and location | Estimated cost (Rs.) in Crores | Tendered Cost (Rs.) in Crores | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 1 | Global Tender for Engineering, procurement and construction for development of mechanized fertilizer and other clean cargo handling facility at Berth No.14 in DPA, Kandla. | 290.85 | -- | --- | --- | --- | --- | --- | --- | Bid opening date 14.07.2023 |
| 2 | Procurement of 04 Nos. of 100 M.T. & above capacity Tyre mounted Electric and Diesel driven (Duo) HMC’s with Five Years Operation & comprehensive AMC (CAMC) after free CAMC of Two years. | 210.95 | -- | --- | --- | --- | --- | --- | --- | Bid opening date 10.07.2023. |
| 3 | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 155.70 | 144.46 96.86 towards capital cost & 47.60 towards O&M Charges. | 7.22 Below | EL/WK/2491/1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri D.K.Hazra, XEN (E) | Comprehensive A.M.C. work in progress. |
| 4 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 120.94 | 122.33 | 0.9% above | LoA issued vide MS/WK/4025-II/GIM-265 dtd. 31.03.2017 | M/s. RISHI Shipping, Gandhidham | 31/03/2017 | 10/07/2026 | Shri Aman Imran B. AXEN(M) | LoA issued on 31.03.2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect upto10/07/2026. |
| 5 | Design, Manufacture, Supply Erection, Testing, Commissioning & Operation of 02 Nos .of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 91.82 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit(LC) i.e., 10/08/2017 & CAMC Work commence from 07/05/2018 | 06/11/2023 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | CAMC work in progress. |
| 6 | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 81.82 | 63.60 | 22.27 Below | EL/WK/2472/480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Comm’ned on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri D.K. Hazra, XEN(E) | Comprehensive A.M.C. work in progress. |
| 7 | Design, Supply, Installation, Testing & Commissioning of Firefighting system and associated facilities including Operation & Maintenance for a period of five years as per OISD-156 at Oil Jetty No. 08, Kandla, of Deendayal Port Authority ( EPC Contact) | 63.62 | 69.98 | 10% Above | W.O. No. MS/WK/4054/AOB/29 dated 08/05/2023 | M/s. Jay Project, Vadodara | 08.05.2023 | 07/01/2024 for SITC work & 07/01/2029 for O & M Work | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
| 8 | Revamping and upgradation of Firefighting system and associated facilities at Oil jetty area- Task-I: SITC of water pump / water pumping system including AMC of 5 years. | 33.77 (37.02 with credit item of 3.25 ) | Net Rs. 38.64[i.e. Part A (EPC(SITC) Rs. 39.56 [i.e. Rs. 39.67- (minus) Rs. 0.11 discount offered in negotiation] (plus) AMC of 5 years Rs. 1.00 (minus) Part B : Credit item : Rs. 1.92] | 14.41 % Above | W.O. ML/WK/4052(Re-tender)/ 343 dated 29/08/2022 | M/s. Jay Project, Vadodara | 29/08/2022 | 28/08/2023 for SITC work & 28/08/2028 for AMC Work | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
|  | Task-II: SITC Firefighting system & associated facilities alongwith Pipeline, civil structure etc. including AMC for a period of 5 Years | 49.55 | 45.00 | 9.17% Below | W.O. ML/WK/4058/ 350 dated 01/09/2022 | M/s. Patel Construction Co., Gandhidham | 01.9.2022 | 28/02/2024 for SITC work & 31/08/2029 for AMC Work | Shri Mani Pushpak Sethi SE(M) | Work in Progress |
| 9 | Supply, installation, testing & commissioning of Sprinkling System for coal dust suppression in 34-hectare coal yard with five Years Operation & Comprehensive Maintenance contract. | 28.11 | 24.48 | 12.92% Below | MS/WK/4046-I/GIM/592 dated 18/02/2022 | M/s Omkar Enterprise, Ahmedabad | 18/02/2022 | 03/04/2028 | Shri Mani Pushpak Sethi SE(M) | O & M Work in progress. |
| 10 | Design, Supply, installation, testing & commissioning along with Comprehensive Operation & Maintenance for a period of Five Years of 02 Nos Column Type Vessel access telescopic gangway system at Oil Jetty No. 07 and 08 of DPA | 22.83 | 18.97 | 16.90% Below | MS/WK/4056-I/AOB-30 dt. 08/05/2023 | M/s. Woodfield Systems International Pvt Ltd, Mumbai | 08.05.2023 | 07/02/2024 for SITC work & 07/02/2029 for O&M Work. | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
| 11 | Operation and maintenance of 66 K.v. Substation and overhead / underground 66 K.v. Transmission Line, AMC of H.T. /L.T. Electrical Installation of Residential & Non- Residential Buildings with-in Kandla premises including Tuna Port & engagement of service operator and advisory services distribution business metering and billing for a period of Three Years. | 16.18 | - | - | - | - | - | - | - | Tender up-loaded on June-2023 |
| 12 | Design, Supply, Installation, Testing, Commissioning of Firefighting facilities as per OISD–156 including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT. | 15.34 | 16.84 | 9.76% above | Work Order: MS/WK/4052/Gim-94 Dated 30.08.2022 | M/s. Sterling And Wilson Pvt. Lltd. | 30/08/2022 | 31/08/2023 for SITC work & 31/08/2028 for O&M Work. | Shri Aman Imran B. AXEN(M) | SITC work under is progress under extension period. (95 % work completed) |
| 13 | Operation and maintenance contract of 02 Nos. Italguru make HMC of 120 Ton capacity along-with grabs inside C.J. area for period of two years. | 11.02 | - | - | - | - | - | - | - | Tender up-loaded in June - 2023 |
| 14 | Comprehensive AMC for Port owned two nos. of Pilot Launches & four nos. of Mooring Launches and complete O&M for one Pilot Launch & one Survey Launch for a period of three years | 8.94 | 7.92 | 11.36% Below | LOA No. ML/WK/4068/692 dt. 15/05/2023 | M/s. Hoger Offshore and Marine Pvt. Ltd. Mumbai | 18.05.2023 (After 3 Days from LOA) | 17.05.2026 | Shri Rajdeo Marine Engineer Gr.I | Work in Progress |
| 15 | Outsourcing of 02 Nos. each Truck Mounted Mist Cannon system, and, Truck Mounted Road Sweeper system, along with comprehensive operation & maintenance, for the period of three years at DPT. | 8.93 | 10.19 | 14.12% above | MS/WK/4047/GIM-542 Dated 21/12/2021 | M/s Sambhav Corporation, Ahmedabad | 23/12/2021 | 22/12/2024 | Shri Dana Manohar, XEN(M) | Work in Progress |
| 16 | Operation and Maintenance contract of industrial light at cargo handling area, open plots, jetty area, godowns, street lighting connecting to port gates including maintenance of 11/0.433 KV substation inside cargo jetty area from zero panel to berth no. 10 and 13th to 16th berth. | 8.51 | 5.29 | 37.84% Below | Work Order No. EL/AC/2709/2092 dated 05.7.2022 | M/s. Daxraj Electricals | 05/07/2022 | 04/07/2024 | Shri D. K. Hazra XEN (E) | AMC in progress |
| 17 | Operation & Maintenance Contract of 2 Nos. Liebherr make LHM 550 model Harbour Mobile Cranes along with 03 nos. Grabs inside cargo jetty area for a period of Two years | 8.20 | 6.92 | 15.60% Below | W. O. No. EL/WK/2028 17/02/2023 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 20.02.2023 | 19.02.2025 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | Work in progress. |
| 18 | Maintenance contract of 03 nos. 25T and 02 nos. 16 T capacity MBE crane wharf cranes, alongwith grabs for a period of 2 years at inside cargo jetty area. | 7.42 | Rs. 7.05 | 5.00% below | LOI No. EL/WK/2691/947 dated 25.02.2022 | M/s. R. S. Electricals, Gandhidham | 16/02/2022 | 15/02/2024 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | AMC in progress. |
| 19 | Supply, installation, testing & commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) unit, integral capstan and remote control type including Operation & Maintenance for five years at Oil Jetty No 08 of DPA | 6.89 | 6.43 | 6.68% below | W. O. No. MS/WK/4058/AOB-05 dated 15.02.2023 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 15.02.2023 | 14/06/2023 for SITC work & 14/06/2028 for O&M Work. | Shri Dana Manohar, XEN(M) | Civil Work in progress and QRMH Work will commence after completion of Civil work. |
| 20 | SPECIAL REPAIRS TO STEEL FLOATING DRY DOCK – SELF DOCKING AND REPAIRS OF PONTOON NO. - 5 & 6. | 6.60 | --- | --- | --- | --- | --- | --- | --- | Price Bid opened & submit for Approval. |
| 21 | Outsourcing of Technical Manpower & staffs for attending various technical projects & works of the department for the period of five years | 6.41 | 5.41 | 15.62 Below | MS/WK/4059/AOB/40 Dated 01.06.2023 | M/s. B M SORATHIA, MADHAPAR | 01.06.2023 | 31.05.2028 | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
| 22 | Supply, installation, testing and commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) units, integral capstan and remote control type including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT | 6.21 | 5.50 | 11.51% Below | MS/WK/4051/Gim-64 dated 04/07/2022 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 04/07/2022 | 31/01/2028 | Shri Dana Manohar, XEN(M) | O & M work is under progress since 01.02.2023. |
| 23 | Supply, Installation, Erection, Testing and Commissioning of S/C Overhead / Underground 66KV Line for providing power supply to IOCL, Kandla. | 6.11 | 6.09 | 0.3 % below | EL/WK/2757 LOI No. EL/AC/2757/1104 | M/s. Devangi Power Private limited, | 03.02.2023 (i.e. 11th day from issuance of LOI) | 03/07/2023 (150 days (i.e from 11th day from issue of LOI) | Shri D.K. Hazra, XEN (E) & PTC | Work in progress. LOI issued on 24.01.2023 (Deposit Work). Work order issued 20/2/2023. |
| 24 | Annual Rate Contract for 11 KV distribution network at license area of DPA at Kandla. | 5.95 | 4.18 | 29.74% below | LOI No EL/AC/2708(TP/1223 dated 23/02/2023 | M/s. NK Industrial Services, Gandhidham | 01.04.2023 | 31.03.2025 | Shri D.K. Hazra, XEN (E) | AMC in progress |
| 25 | Maintenance contract of 2 Nos. ITALGRU make Harbour Mobile Crane of 63T capacity along with 6 nos. of grabs and comprehensive maintenance of Hydraulic (suspension and winch) pumps inside cargo jetty area for period of two years. | 5.70 | 4.32 | 24.21% | LOI No. EL/AC/2702/650dated 05-01-2022 | M/s. Italguru India Pvt. Ltd., New Delhi | 01/01/2023 | 31/12/2023 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | AMC in progress |
| 26 | ARC for supply & Laying of HT/LT/UG Cable, HT/LT/UG Cable fault finding inside & Outside Cargo Jetty area. | 5.39 | --- | --- | --- | --- | --- | --- | --- | Technical Bid opened on 07.07.2023 |
| 27 | Providing Power Supply & Illumination to oil Jetty No 08 at DPA, Kandla. | 4.97 | --- | --- | --- | --- | --- | --- | --- | Technical bid opened on 09/05/2023 & Proposal submitted for opening of Price Bid. |
| 28 | Annual maintenance contract works at A.O. Building and Gopalpuri colony for a period of two years. | 4.96 | 3.48 | 29.84% below | W.O. No El/WK/2699/1219 dated 23/02/2023 | M/s N.K. Industrial Services | 01/03/2023 | 28/02/2025 | Shri D.K. Hazra, XEN (E) | AMC in progress |
| 29 | Providing of 11 Kv H.T. Power plug point on wharf side for operation of MHC from Berth No 6 to 10 & 13 to 16. | 4.89 | --- | --- | --- | --- | --- | --- | --- | Tender up-loaded in 22.06.2023 |
| 30 | Supply, Installation, Erection, Testing and Commissioning of Mast Tower 34 hectares area | 4.68 | 3.46 | 26.075 % below | LOI No. EL/AC/2723 Dtd 27.02.2023 | M/s. N. K. Industrial Services, Gandhidham | 27/02/2023 | 26.12.2023 | Shri Anil Runtia AXEN (E) | Work order issued EL/WK/2723 03/4/2023 |
| 31 | Comprehensive AMC of Mech works and equipment | 4.31 | 4.12 | 4.59% Below | MS/WK/4048 Dated 14/01/2022 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 15/01/2022 | 14/01/2027 | Shri Dana Manohar, XEN(M) | Work in progress. |
| 32 | Maintenance contract of 3 Nos. 25T capacity 4 rope TIL make ELL cranes along with Grabs at Berth No. 10 at Inside Cargo Jetty area for a period of 2 years | 4.13 | 2.88 | 30.26% Below | W.O. No El/WK/2049/1247 dated 01/03/2023 | M/s. R. S. Electricals, Gandhidham | 05/02/2023 | 04/02/2025 | Shri Anil Rautiya, AXEN (E) | Work in progress. |
| 33 | Supply, Installation, Testing and Commissioning of High Mast Lighting Tower at Berth No. 14. | 4.01 | 2.78 | 30.75% | EL/WK/2655-work/745 dated 27-01-2022 | M/s. Vishal Electricals, B-4, Hans Plaza, Ambedkar Road, Ghaziabad 201001 | 27/01/2022 | 08/08/2023 | Shri D.K.Hazra, XEN(E) | Work in progress in under Extension period. |
| 34 | Comprehensive Annual Maintenance Contract for Channel Marking, Dumping and Mooring Buoys in the Kandla Channel along with operation & Maintenance of Heave up Barge Bhimsen for a period of three years. | 4.00 | 3.68 | 8.17% Below | W.O. ML/WK/4040/ 336 dated 01/08/2022 | M/s. Seacrafts Industries (P) Ltd., | 06.8.2022 | 05.08.2025 | Shri Rajdeo Kumar, Marine Engineer Gr.I | Work in progress. |
| 35 | Construction of 16th berth for multipurpose cargo (other than Liquid/Container Cargo) – Supply, installation, testing and commissioning of High Mast Lighting Towers at Berth No. 16. | 3.83 | 2.72 | 28.98% below | EL/WK/2715/3554 Dtd. 14.11.22. | M/s. N.K. Industrial Service | 14.11.22. | 13.09.2023 | Shri D.K. Hazra, XEN ( E) | Work in progress. |
| 36 | Upgradation of 66/11 KV GIS substation by replacement of the existing HT panel & control relay panels including civil building. | 3.40 | 3.08 | 9.35% below | EL/AC/2725/ TP/1065 Dtd: 12/01/2023. | Shree Vallabh Electricals Anand | 12/01/2023 | 08.12.2025 (330 Days) | Shir Anil R, AXEN (E) | Work order No. EL/WK/2725/1187. 15/02/2023 issued |
| 37 | Refurbishing of Power supply of A.O.B. | 2.83 |  | - | - | - | - | - | - | Tender up-loaded in 12.06.2023 |
| 38 | Construction of Dome Shaped Storage sheds inside cargo jetty area- Electrification work. | 1.86 | 2.26 | 22.50% Above | EL/WK/2650-II, LOI No EL/AC/2650-II/3433, dated 06.10.2022 | M/s. Vishal Electricals, Ghaziabad (UP) | 09.12.2022 | 08.08.2023 | Shri D.K. Hazra, XEN (E ) | Work in progress in under Extension period. |
| 39 | Major Repair Work of Heave Up Barge Bhimsen. | 1.67 | 1.56 | 6.41% below | ML/WK/4020-I(d)/156 dated 01/06/2022 | M/s. Patel Construction Co., Gandhidham | 01/06/2022 | 30/06/2023 | Shri Rajdeo, Marine Engineer Gr.I | Work in progress in under Extension period. |
| 40 | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhi-dham Area for period of three years. | 1.55 | 1.39 | 10.14% Below | DD/WK/4309/338 dated 04.08.2021 | M/s. Inspection & Engineering Services, Ahmedabad | 04/08/2021 | 03/08/2024 | Shri Himmat Makeana AXEN(M) | Work in Progress. |
| 41 | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weighbridges (15Kmph speed) of 140Mt capacities including comprehensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 1.51 | 1.48 | 2.07% below | W.O. No.ML/WK/3916-II/738 Dtd. 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., Chennai | 05/01/2019 | 17/12/2028 | Shri Aman Imran B. AXEN (M) | Work Completed on 18/12/2021. The weighbridges installed are under guarantee period of two years under CAMC |
| 42 | Electrical work for 66 KV feeder bay GETCO Substation and for feeder bay Extension | 0.87 | 0.82 | 5.03 % below | LOI No. EL/AC/2575/ feederbay/ 3534, dated 02.11.2022 | M/s OM Power Transmission Ahmedabad | 12.11.2022 | 31.08.2023 | Shri Kumthekar, AE (E) & PTC | Work is under progress under extension period. |
| 43 | Re-wiring of 160 Nos. of FCI & DLB Colony Qtr. For allotment and shifting CISF family Qtrs. –Kandla to FCI & DLB Colony (Phase-II.) | 0.55 | -- | - | - | - | - | - | Shri D.K.Hazra, XEN(E) | Tender up-loaded in 04.07.2023 |
| 44 | Up gradation of Power Supply Including Lighting Arrangement at Periphery at Tuna Port. | 0.54 | -- | - | - | - | - | - | - | Tender up-loaded on 06/2023. |
| 45 | Sell of renewable power generated from DPT’s 14.7MW wind power plant on Medium Term Open Access basis through tariff based competi-tive bidding through auction. | Rs. 4.26 per unit | Rs. 4.27 per unit | - | LOI No. EL/C/2688/1158, dated 10.11.2021 | M/s. UPL Ltd. GIDC Jhagadia- Bharuch | 29/12/2021 | 29/12/2022 Extension till 31/12/2023 | Shri D.K.Hazra, XEN(E) | MTOA has been extended with GETCO on 29/12/2021 and valid upto 31/12/2023. |
| 46 | Operation and maintenance for operation and main-tenance of 66 KV substation. | Not Applicable | 1.00 Per Year | Not Applicable | EL/WK/2736/3043 dated 14/07/2022 | M/s. PTC India Ltd., New Delhi | 12/08/2022 | 11/08/2024 | Shri D.K. Hazra XEN (E) | Work in progress. |
| 47 | Build, Operate and Maintain of 10 nos. of 120 T capacity each Automated road weighbridges on Revenue Sharing basis at DPA for a period of 10 years and buy–back of 10 nos. of existing Road weighbridges of DPA | Tender is based on revenue sharing | Rs. 1.89 per Ton | Not Applicable | ML/WK/4013-II Dated 06.03.2023 | M/s. Serwell Cargo India Pvt Ltd, Mumbai | 10.04.2023 | --- | Shri Aman Imran B. AXEN (M) | Work in progress. |

ENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 30.06.2023

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | 49.32 Cr. | 6.62% below | No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. | M/s. Parsh Construction and Foundations Pvt. Ltd., Mumbai | 26/03/2021 | 18 months Extended Upto 30/06/2023 | Shri Rajesh Meghani, XEN (C) | Work Order issued vide No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. Extended vide O.O. No. OOT/C-WK/CG/7041 (Jetty)/190 dated 08/06/2022. Further Extended Upto 30/06/2023. |
| 2. | Hiring of 2 Nos. Steel Hull Mooring Launches with Crew and Mooring Gang at OOT, Vadinar for the period of Five (05) years. Estimate: Rs. 12,53,49,780/- | 12.53 Cr. | 9.12 Cr. | 27.21 % below | OOT/ME/WK/8017/484 dated 21/05/2021. | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | 14/12/2021 | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. OOT/ME/WK/8017/484 dated 21/05/2021. |
| 3. | Hiring of Service Boat for OOT, Vadinar for the period of 5 (five) years. Estimate: Rs.8,76,00,000/- | 8.76 Cr. | 9.59 Cr. | 9.49% above. | MR/WK/ 1397/66 dated 28/03/2022 | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | -- | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. MR/WK/1397/66 dated 28/03/2022. The party will deploy the Service Boat w.e.f. 22/10/2022 as per terms and conditions. Party has applied for 3 months extension and the same is under process. |
| 4. | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | No. OOT/ME/WK/3009-I/576 dated 26/12/2018. | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 5 | Engagement of Security Agency for providing watch and ward security supervisor and security guard at OOT, Vadinar. | 2.88 Cr. | 2.90 Cr. | 0.77% above | GEMC-511687725619008 dated .26.04.2023 | M/s. Kutch Security Services, Ahmedabad | 14.05.2023 | 04 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide:GEMC-511687725619008 Dt.26.04.2023 |
| 6. | Painting work for residential and Non-residential buildings Port Colony at Vadinar Estimate: Rs. 2,58,32,912/- | 2.58 Cr, | 1.61 Cr. | 37.66% Below | MR/WK/ 1397/36 dated 06/09/2021 | M/s. Shreeji Enterprise Gondal | 13/09/2021 | 18 Months | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide MR/WK/1397/36 dated 06/09/2021 |
| 7. | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 Cr. | 5.01 % above | OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/1666 dated 10/01/2020. |
| 8. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.44 Cr. | 2.83% above | OOT/ME-WK/RM/6004/239 dated 04/03/2021. | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. |
| 9. | Engagement of Security Agency for providing watch and ward security supervisor and security guards at OOT, Vadinar. Estimate: Rs. 1,03,05,216/- | 1.03 Cr. | 1.06 Cr. | 2.98% above | OOT/C-WK/RM/4002/2001 dated 12/03/2020 | M/s. Abhay Intelligence & Security Services, Vadodara. | 14/03/2020 | 2 years and extended for a period for one year | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-WK/RM/4002/2001 dated 12/03/2020 Extended vide OO No. OOT/C-WK/4002/Vol-XIII/27 dated 16/03/2023 Work completed. final bill yet to be realeased. |
| 10. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | OOT/ME-WK/RM/ 6018/329 dated 26/03/2021. | M/s. Pariya Electricals, Vadinar. | 01/04/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2021. |
| 11. | Maintenance of beacons, leading lights & channel marking bouys in DPT waters at OOT-Vadinar for a period of three years. Estimate: Rs. 70,02,000/- | 0.70 Cr. | 0.57 Cr. | 18.59% | OOT/ME/WK/RM/8009/1947 dated 03/03/2020. | M/s. Aeromarine Pvt. Ltd., Mumbai | 01/06/2020. | 3 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/RM/8009/1947 dated 03/03/2020. |
| 12. | Providing, Operating and Maintaining of 02 Nos. of TATA Winger AC Ambulance at OOT, Vadinar for a period of 3 years. Estimate: Rs. 61,71,120/- | 0.62 Cr. | 0.58 Cr. | 6.01 % below | OOT/ME/WK/6008/1795 dated 06/02/2020. | M/s. Safari Travels, Balasinor | 07/02/2020 | 3 years and extended upto 30/06/2023 | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME/WK/6008/1795 dated 06/02/2020. Extended vide O.O. No. OOT/ME-WK/6008/pt/387 dated 27/12/2022 Extended vide O.O. No. OOT/ME-WK/6006/pt/49 dated 30/03/2023 |
| 13. | Running and Maintenance of Guest House and Staff Canteen at OOT, Vadinar Estimate Rs. 55,66,811/- | 0.56 Cr. | 0.53 Cr. | 5.61 % below | OOT/C-WK/RM4026/114 dated 29/042/2022 | M/s. Mahakal Enterprise, Jamnagar. | 01/05/2022 | 03 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide: OOT/C-WK/RM/4026/114 dated 29/04/2022 |
| 14. | Maintenance Contract of the Residential Building and Non Residential Building in Port Colony and Jetty at Vadinar. | 0.53 Cr. | 0.47 Cr. | 9.51% below | OOT/C-WK/ RM/4050-II/328 dated 29/07/2022 | M/s. G N Enterprise, Vadinar | 01/08/2022 | 02 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide: OOT/C-WK/RM/4050-II/328 Dt.29.07.2022 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 30.06.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dredging in the Navigational Channel & Alongside Cargo Berths/Oil Jetties at Deendayal Port Trust for year 2020-23”. Location At Kandla | 393.80 | 310.04 | 21.27 % Below | LOA No. EG/WK/6116/182 dated 10.03.2021 | M/s Adani Ports and Special Economic Zone Ltd., Ahmedabad | 04/09/2021 | 36 months | Shri K. Srinivasa Rao, XEN (H & D) | Work in progress |
| 2 | Augmentation of liquid cargo handling capacity by revamping of existing pipeline network at Oil Jetty are, Deendayal Port Trust, Kandla | 130.49 | 126.49 | 3.05% below | PL/WK/8306 NIT-PQ/08 dated 31/08/2021 | M/s. Patel Corrrtech JV, Gandhidham | 30/09/2021 | 24 months | Shri B. Rajendra Prasad, SE (P) | Work in progress. 53% physical progress 48% financial progress. |
| 3 | Construction of Oil Jetty No.8 at Old Kandla. | 105.51 | 99.08 | 6.09% below | No.CN/WK/1571/work/243 dtd. 03/02/2021 | M/s Kargwal KM Joint Venture, Mumbai | 17/02/2021 | 18 months Extension granted upto Oct., 2023. | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 4 | Development of land from Junction of WG 1 & 2 to LC 236B at Kandla (Phase-1) | 81.99 | 67.67 | - | - | M/s. Shree Ram Infrastructure | - | 18 months | Shri Rajesh Meghani, XEN(C-I) | L1 proposal is submitted. |
| 5 | Development of backup area of oil Jetty No.8 to 11 (Phase-I) | 80.97 | 66.58 | 17.77% below | LOA No. EG/WK/9129/374 dated 19/10/2022. | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 21/12/2022 | 12 Months | Shri B. Rajendra Prasad, SE (P) | Work in progress. 15% physical progress 10% financial progress. |
| 6 | Development of area from Junction of West gate-I to west gate-II now renamed as "development of land west side of road in between junction of west gate 1&2 and railway line to 12th berth - Phase -I | 80.31 | 55.73 | 30.60% below | LOA No. EG/WK/8117/373 dated 17/10/2022 | M/s. Digvijay Construction Pvt. Ltd., Gandhinagar. | 07/11/2022 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 7 | Up - gradation of tuna road from two lane to four land (Phase-I) | 71.57 | 57.43 | 19.74% below | LOA No. EG/WK/8116/349 dated 03/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 10/11/2022 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 8 | Development of four lane road common corridor from LC236B to 16th CB along railway line (Phase-I) | 66.90 | 55.28 | 30.41% below | CN-I/WK/3072/ Work/01 Dated 03/04/2023 | M/s. Hariom Earthmovers & Transport | 10/04/2023 | 18 Months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 9 | Upgradation of Plots & S.W.D. in 66 Hectare area inside cargo jetty area | 65.80 | 59.55 | 9.51% below | HW/WK/2488/704 dated 11/01/2023 | M/s. Baldaniya Construction, Anjar. | 17/04/2023 | 16/10/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 10 | Retrofitting cargo berth No.8 | 64.86 | 47.27 | 27.13% Below | - | M/s. BMS Project-Marymatha JV, Kerala | 15/02/2022 | 16 Months | Shri Rajesh Meghani XEN(C-I) | Work in progress. |
|  | Retrofitting cargo berth No.9 |  |  |  |  |  |  |  |  |  |
| 11 | Development of four lane road common corridor from LC236B to 16th CB along railway line (Phase-I) | 55.28 | 38.47 | 30.41% below | LOA No.EG/WK/8116/349 dtd.03.10.2022 | M/s. Hariom Earthmovers & Transport | - | 18 Months | Shri Rajesh Meghani, XEN(C-I) | Work in progress |
| 12 | Development of Backup Area and Allotted Facilities at the Existing Tuna Barge Jetty | 54.30 | 45.29 | - | - | - | - | 11 Months | Shri Rajesh Meghani, XEN(C-I) | Technical bid opened & the same is under scrutiny. |
| 13 | Construction of new godowns in place of existing godown no. 19 to 21 & 25 inside C. J. Area | 53.20 | 42.94 | 19.27% below | HW/WK/2580/705 dated 11/04/2023 | M/s. Patel Construction Co. Gandhidham. | 17/04/2023 | 16/10/2024 18 months | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 14 | Raising & upgrading the RCC Plots adjoining to track no. 10,11&12 inside Cargo Jetty Area | 53.13 | 43.27 | 18.56% below | N.A. | M/s. Radhe Associated, Mehsana | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | LOA issued on 09/06/2023. |
| 15 | Up gradation of roads & SWD outside cargo jetty area at New Kandla (Cement Concrete Pavement) | 40.35 | 24.65 | 38.88% | RW/WK/7821-I/362 dated 18/05/2023 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhidham. | 22/05/2023 | 21/08/2024 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work in progress |
| 16 | Upgradation of Plots, Roads & SWD in 40 hectare area inside Cargo Jetty Area. | 39.36 | 31.48 | 19.84% below | HW/WK/2456/579A dated 31/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd. | 22/10/2022 | 21/04/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 17 | Widening of Road from Junction of WG 1 & 2 to 12th Berth | 38.50 | 32.24 | 2.99% below | LOA No. EG/WK/8120/ 66 dated21/04/2023. | M/s. Dhanji K. Patel, Anjar. | - | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 18 | Raising & Upgradation of Plots inside Cargo Jetty Area | 38.24 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Rajesh Meghani, XEN(C-I) | Technical bid under scrutiny. |
| 19 | Construction of Dome shaped Storage Sheds inside C.J. Area - Phase-II | 30.63 | 24.24 | 20.86% | HW/WK/2567/335 dated 26/06/2023 | M/s. Patel Construction J/V M/s. Neelkanth Infrastructure P. Ltd. | 05/07/2023 | 04/01/2025 | Shri Mahesh Makhijani, XEN(H) | Work order issued. |
| 20 | Upgradation of Kutchha Plot C1 to C6 of 66 Hectares and SWD Network inside Cargo Jetty area. | 22.84 | 21.23 | 7.06% below | HW/WK/2545 202A dated 01/11/2022 | M/s. K.K. Sorathia J/v Hari Om Earthmovers and Transport | 15/11/2022 | 14/11/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 21 | Construction of Kendriya Vidyalaya Building at Port Colony Gopalpuri, Gandhidham | 21.64 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar, XEN(TD) | Price Bid opened on 08.05.2023 & sent for approval of L1 bidder |
| 22 | Development of area adjacent to Tuna-GIM track by earthwork in embankment from 4.00 Km to take-off point for doubling of line to facilitate upcoming new projects at Tekra | 19.62 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Rajesh Meghani, XEN(C-I) | Preliminary bid opened on 13/06/2023. Tender under scrutiny. |
| 23 | Up-gradation and Strengthening of Existing Oil Jetty No 3 | 19.27 | 15.78 | 13.38% Below | LOA No. EG/WK/9132/95 dated 26/05/2023 | M/s Patel Construction Co., Gandhidham | - | 29/09/2024 8 months | Shri B. Rajendra Prasad, SE (P) | Work Order issued on 22/06/2023. |
| 24 | Construction of A,B, C and D type quarters at Gopalpuri | 18.94 | 13.78 | 27.16% below | TW/WK/7775/ 299 dtd. 07/06/2021 | M/s. VC Project & Infra Pvt. Ltd. | 05/06/2021 | 04/06/2023 | Shri Hemant Bhaskar XEN(TD) | Work in progress. Extension requested upto Sept., 2023. |
| 25 | Development of Parking yards for trucks/vehicles for pre checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 | 14.59 | 12.87% below | HW/WK/2446/463 dated 26.06.2021 | M/s. Indian Construction Co., | 08/07/2021 | 07/07/2022 12 months work and 24 months maintenance Extension granted upto Sept.,2023. | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 26 | Providing Road network & SWD to newly added custom bonded area ( 25 Ha area) | 14.50 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Preliminary bid opened on 06/06/2023. |
| 27 | Retrofitting of the Bunder Basin Structures | 10.00 | 7.11 | 11.10% below | LOA No. EG/WK/8114/51 dated 25/02/2022 | M/s. Chetan Construction Co., Mehsana | 21/03/2022 | 15 months | Shri Rajesh Meghani XEN (C-I) | Work in progress. |
| 28 | Annual Maintenance contract for roads at Kandla for two years | 8.31 | 5.97 | 28.23% below | RW/WK/7810-I/239 dated 05/01/2023 | M/s. Dhanjibhai K. Patel, Anjar. | 05/01/2023 | 04/01/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 29 | Construction of E & D type quarters at Gopalpuri (Stage-1, D type ) | 8.23 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar , XEN(TD) | Technical Bid opened on 09.05.2023 & under process |
| 30 | Construction of Ring Road (Periphery road ) from NH-8A (From KASEZ) to Adipur | 8.20 | 6.33 | 22.83% below | TW/WK/7804-I/418 dated 04/11/2022 | M/s. Shree Ganesh Construction, Anjar | 10/11/2022 | 09/10/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 31 | Upgradation of internal road network from West gate I to Kutch Salt Junction LC 236 | 8.10 | 7.86 | 2.92% below | HW/WK/2555/806 dated 08/05/2023 | M/s. Dhanjibhai K. Patel, Anjar | 15/05/2023 | 14/12/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 32 | Resurfacing of Plots, Roads & SWD in 40 Hectare area inside Cargo Jetty area. | 8.09 | 7.95 | 1.68% below | HW/WK/2523/616 dated 09/12/2022 | M/s. Shree Ganesh Construction, Anjar. | 24/12/2022 | 23/07/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 33 | Extension of Custom Bounded area in Backup of 13th & 16th Berth | 8.02 | 5.28 | 34.24% below | LOA No. EG/WK/8115/264 dt. 22/06/2022 | M/s Mohit Enterprise, Rajkot | 08/08/2022 | 13 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 34 | Special Repairs of plot no 8 & 9 at bunder basin (5 hectares) | 7.99 | 7.17 | 10.33% below | HW/WK/2556 dated 30/05/2023. | M/s. Balaji Infra, Anjar. | 06/06/2023 | 05/06/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 35 | Construction of Storage Shed Over Existing Floor of Godown No. 3 & 4 inside C. J. Area | 7.81 | 6.05 | 11.10% below | N.A. | M/s. Neelkanth Infratech Pvt. Ltd. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | LOA issued on 07/07/2023. |
| 36 | Improving / Upgradation of Custom Fencing Wall of Cargo jetty and Bunder Area | 7.68 | 5.38 | 29.95 % below | HW/WK/2507-I/73 dated 15/02/2022 | M/s. Deosi Govindji Parmar (Lead Partner) J/v M/s. Shree Balaji Construction Co. | 28/02/2022 | 27/02/2023 12 months Extended upto 28/08/2023. | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 37 | Construction of garage and repair workshop building for mobile cargo handling equipments inside cargo jetty area | 7.61 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | XEN (H) | Preliminary bid opened on 08/06/2023. Tender under scrutiny |
| 38 | Strengthening to Residential & Non - Residential Building at New Port Colony, New Kandla | 7.56 | 4.99 | 34.05% below | RW/WK/7819-I/363 dated 18/05/2023 | M/s. Patel Construction Co., Gandhidham. | 22/05/2023 | 21/05/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 39 | Providing RCC and asphalt roads inside and outside of oil jetty area at Old Kandla | 7.12 | 4.79 | 32.76% Below | PL/WK/8490-I/189 dated 27/02/2023 | M/s. Mepabhai Mandan and Co., Adipur | 27/02/2023 | 11 months | Shri Rajendra Prasad B., S E (PL) | Work in progress. |
| 40 | S/R to quarters / building at FCI & KDLB Colony | 6.87 | 4.66 | 32.18% below | TW/WK/7788 -I/203 dated 27/06/2022 | M/s. Ankita Construction, Adipur | 01/07/2022 | 30/09/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 41 | Removal of old abandoned RCC jetty structure in between Oil Jetty No. 2 & 3 at Old Kandla. | 6.75 | 6.46 | 6.39% below | PL/WK/8424-I/562 dated 15/06/2023 | M/s. Goyal Iron and Steel Traders. | June, 2023 | 05 Months | Shri Rajendra Prasad B., S E (PL) | Work in progress. |
| 42 | Appointment of Project Management Consultant (PMC) for Capital and Maintenance Dredging works of Deendayal Port Trust from firms/ consortiums Empanelled Consultants for dredging works (Class-A, Category-A) by Indian Port Association, New Delhi. | 6.36 | Rs. 5.33 | 15.32% Below | LOA No.EG/WK/6112/ 333 dated 15.11.2019 | M/s AECOM INDIA PVT LTD, GURGAON | 25/11/2019 | 36 months Extension grated upto November, 2023 48 months. | Shri K. Srinivasa Rao, XEN (H &D) | Work in progress |
| 43 | S/R to A.O. Building at Gandhidham. | 5.73 | 4.55 | 20.70% below | - | M/s. K.K. Sorathia, | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Price Bid opened on 16.05.2023 & called for justification from L1 Bidder |
| 44 | Appointment of technical, legal and financial experts from the firms of Transaction Advisor for "providing legal, technical and financial transactions for all ongoing and future proposals of DPA on PP / Captive Mode for the period of two years and further extendable for one year. | 5.46 | 3.60 | 34.06% below | -- | M/s. Infrastructure Development (Karnataka) Corporation Ltd (Ideck) | 14/10/2022 | 2 years and further extendable for 1 year | Shri K.J. Todarmal, SE(D) | Work is in Progress. |
| 45 | Preparing and monitoring of Environmental Management Plan for DPA at Kandla. | 5.01 | 4.87 | 38.17 % below Estimated Cost | EG/WK/EMC/11023/2011/III/239 dated 15.02.2023 on nomination based | M/s. GEMI Gujarat Environment management Institute.r | 14.04.2023 | 36 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 46 | Improving & up-gradation of gardens and land scrapping at Gopalpuri (Renovation of Nehru Part and rain water harvesting by strengthening of SWD network near recharging pond at Gopalpuri | 4.79 | 2.40 | 49.81% below | TW/WK/7802-I/404 dtd.16.07.2021 | M/s. Rainbow Infrastructure, Rajkot | 03.07.2021 | 02.07.2022 (main work) 02/07.2024 (maintenance) | Shri Hemant Kumar Bhaskar XEN(TD) | Main Work completed. Maintenance work is in progress |
| 47 | Upgradation of Sewage treatment plant at Gopalpuri | 4.27 | 4.14 | 3.0363% below | TW/WK/7736-I/254 dated 21/07/2021 | M/s. Rajkamal Buildings, Infrastructure (P) Ltd., | 01/08/2022 | 31/01/2026 | Shri Hemant Kumar Bhaskar XEN(TD) | Main work completed. Maintenance work is in progress. Extension grated for two months. |
| 48 | Preparing and monitoring of Environmental Management Plan for Deendayal Port Authority at Kandla. | 4.07 | 2.52 | 38.17 % below | EG/WK/EMC/11023/2011/IV dtd. 05/12/2019 | M/s Detox Corporation Pvt. Ltd. | 16/12/2019 | 36 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work assigned to Detox Corporation is expired on 15/12/2022, same has been assigned to M/s. GEMI Work order dated 15/02/2023 on nomination basis. |
| 49 | Construction of Fire Brigade Station Opposite Jetty Office in CKD Yard inside Cargo Jetty Area | 3.48 | 2.94 | 15.62% below | HW/WK/2540/770 dated 24/04/2023 | M/s. Murlidhar Projects | 01/05/2023 | 31/07/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 50 | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 | 2.43 | 35.73% Below | W.O. No. HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd., Gurgaon - 122015 Haryana- India | 02/11/2021 | 36 months Extension grated upto November, 2023 | Shri K. Srinivasa Rao, XEN (H&D) | Work in progress |
| 51 | S/R to CISF complex building & Structure at New Kandla | 3.24 | 2.40 | 26.04% below | RW/WK/ 7817-I/307 dated 27/03/2023 | M/s. Acer Infra Trade, Gandhidham | 03/10/2023 | 02/10/2024 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work in progress. |
| 52 | Maintenance of PH & UG drainage at Gopalpuri Port Colony & KDLB Colony for the period of two years. | 3.15 | 1.56 | 50.51% below | TW/WK/7813-I/ dated 05/07/2022 | M/s. Patel Construction, Gandhidham. | 05/07/2022 | 04/07/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 53 | Annual Maintenance Contract for residential and non-residential building a Port Colony, Gopalpuri for two years. | 3.05 | 1.71 | 44.12% below | TW/WK/7806-I/126 dated 30/04/2022 | M/s. Dhanjibhai K. Patel, Anjar | 02/05/2022 | 01/05/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 54 | Construction of watch tower inside cargo jetty area | 3.04 | 2.84 | 6.22% below | HW/WK/2470/ 407 dated 09/04/2021 | M/s. Viyuha Infrabuild | 24/05/2021 | 8 months Extension granted upto 22/06/2022 | Shri Mahesh Makhijani, XEN(H) | Work in progress. Extension granted for 6 months from the date of handing over the site. |
| 55 | Special repairs to RFID cum data centre building adjoining to Seva Sadan III at New Kandla | 3.01 | 2.49 | 17.22% below | HW/WK/2582/ 284 dated 31/01/2023 | M/s. Vihat Construction, Gandhidham. | 03/02/2023 | 02/08/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 56 | Deployment of equipment for cleaning of all toilet blocks inside Port area and to maintain high standard of hygienic and to avoid pollution. | 2.99 | 2.23 | 25.40% below | HW/WK/2551/202 dated 31/10/2022 | M/s. Shree Ganesh Construction, Anjar - Kutch | 01/11/2022 | 30/10/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 57 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2022-24 | 2.78 | 1.68 | 39.35% below | TW/WK/7825-I/670 dated 24/03/2023 | M/s. Acer Infra Trade, Gandhidham | 27/03/2023 | 26/03/2025 24 months | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 58 | R/m of Maintenance Jetty - Repairs and Maintenance of Pontoons and Walkways of SNA Jetty and Flotilla Jetty | 2.77 | 3.37 | 10.51% above | HW/WK/2494/462 dated 25.06.2021 | M/s Patel Construction. Gandhidham | 08/07/2021 | 07/07/2023 24 months | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 59 | Maintenance Contract for Godown inside Cargo Jetty area for two years 2022-23 & 2023-24) | 2.70 | 2.08 | 23.77% Below | HW/WK/2531/324 dated 05.06.2023 | M/s. Sanjay k. Sorathiya & Co., Gandhidham. | 05/06/2023 | 04/06/2026 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 60 | Annual Maintenance Contract for AO Building at Gandhidham for 02 years | 2.67 | 1.95 | 27.00% below | TW/WK/7820/654 dated 13/03/2023 | M/s. Acer Infra Trade, Gandhidham | 15/03/2023 | 14/03/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 61 | Special Repairs to ATM office, Marine Bhavan, Immigration Centre Inside Cargo Jetty Area | 2.63 | 2.12 | 18.52% below | HW/WK/2536/297 dated 21/04/2023 | M/s. Murlidhar Projects | 28/04/2023 | 27/04/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 62 | Two years contract for supply and maintenance of railway tracks inside and outside cargo jetty area (for 02 years | 2.59 | 2.03 | 21.40 % below | HW/WK/2487/359 dated 20/02/2021 | M/s. Laxyo Entergy Ltd. | 06/03/2021 | 05/03/2023 24 months Extension granted upto 31/07/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 63 | Resurfacing of road from KK road junction to Mithirohar GIDC at Kandla | 2.52 | 2.56 | 1.68% above | RW/WK/ 7804-I/307 dated 16/03/2023 | M/s. Ravji Manji Sorathia & Co., Adipur. | 20/03/2021 | 19/12/2023 | Shri Hemant Bhaskar, XEN(R) | Work in progress. |
| 64 | Two Years Contract for supply and maintenance of railway tracks inside and outside cargo jetty area (For Years 2023-25) | 2.23 | 1.77 | 21.06% below | N.A. | M/s. Dharti Construction | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Price bid opened on 12/06/2023 |
| 65 | S/R to AO Building at Gandhidham - Renovation of toilet blocks, recreation room, old board room. | 2.20 | 1.32 | 40.13% below | TW/WK/7795-I/ 111 dt. 21/04/2022 | M/s. Ankita Construction, Adipur | 25/04/2022 | 24/04/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Main work completed. Maintenance work is in progress. |
| 66 | House Keeping & Cleaning of Building of Office building and surrounding outside Cargo Jetty Area for the year 2021-23. | 1.97 | 1.07 | 45.36 % below | HW/WK/2538/68 dated 07/02/2022 | M/s. Rajput Infrastructure Co. , Gandhidham | 22/02/2022 | 21/02/2024 24 months | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 67 | Maintenance Contract of Fenders inside Cargo Jetty Area for two year 2022-23 & 2023-24) | 1.97 | 2.14 | 12.17% above | N.A. | M/s. Patel Construction Co., Gandhidham | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Tender is discharged and re-invitation is under process for approval. |
| 68 | Two years maintenance contract for office buildings outside Port area (Civil work) | 1.63 | -- | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Preliminary bid opened on 07/06/2023. Tender under scrutiny |
| 69 | Providing Labour amenities centre at various locations inside Cargo Jetty Area. | 1.53 | 1.18 | 22.85 % below | HW/WK/2461/60 dated 25/01/2022 | M/s. Rajput Infrastructure Co. | 08/02/2022 | 07/02/2023 12 Months (Extension granted upto 07/08/2023) | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 70 | Providing RCC drinking water tank. | 1.52 | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad B., SE (PL) | Technical bid under evaluation. |
| 71 | AMC for White Washing, Distempering, Painting to Res. & Non-resi. Bldg. at G’puri, KDLB, G’dham & Adipur for the year 2022-23 | 1.45 | 0.74 | 48.60% below | - | M/s. Paras Enterpricse. | - | - | Shri Hemant Kumar Bhaskar, XEN(TD) | Price bids opened on 13/03/2023. Submitted the proposal to discharge tender. |
| 72 | Appointment of Independent Engineer for the work of “Development of Marine Liquid Terminal Facilities consisting of SPM and Two Product Jetties in KPT waters at OOT, Vadinar for Handling Crude and Petroleum Products on Captive Use Basis”. | 1.44 | 1.18232 | 17.89% below | Work Order No.EG/WK/4823(IE)/109 dated 22/10/2019 | M/s RINA Services s.p.A,Mumbai | 01/11/2019 | 42 months | Shri K.J. Todarmal, SE(D) | As concessionaire has not started construction activity, the work order issued to M/s. RINA has been kept in abeyance. |
| 73 | Third Party Inspection and Quality Inspection and Quality Assurance for the works costing more than Rs. 1.00 Cr. of Civil Engineering Department of Deendayal Port Authority. | 1.358 | 1.17 | 14.05% below | Work Order No.EG/WK/5212/53 dtd.16/10/2021 | M/s. VCS Quality Services pvt. Ltd., Mumbai | 25/10/2021 | 24/10/2023 | Shri Sunil Soren, XEN(D) | Work in Progress. |
| 74 | Maintenance Contract for Non-residential buildings inside Harbour area (Civil Work) | 1.31 | 0.95 | 27.55% below | HW/WK/2526/122 dated 20/04/2022 | M/s. Mepabhai Mandan & Co., Adipur | 05/05/2022 | 04/05/2024 24 months | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 75 | Strengthening of existing environmental management cell at DPT Appointment of environ-ment experts for two years and further extendable for one year | 1.232 | 1.20 | 2.60% below | EG/WK/ 4783/V/131 dtd.05/02/21 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15/02/2021 | 14/02/2023 24 months Extension granted upto 15/02/2024 | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 76 | Maintenance contract for cleaning & house keeping work of DPA hospital & isolation ward at gopalpuri & kandla & Adipur dispensary for the period of two years | 1.22 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Technical Bid opened & under process |
| 77 | Two years maintenance contract for Railway track leading to Tuna from 0 to 11 Km KPT Line (Take off Point at 2.573 Km at GIM Yard to 13.54 Km including LC-1, LC-2) | 1.19 | 0.908 | 23.77% below | HW/WK/2515/432 DATED 31/05/2021 | M/s Patel Construction. Gandhidham | 14/06/2021 | 13/06/2023 24 Months Extension grated upto 30/11/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 78 | Maintenance contract for sports complex for the period of two years at Gopalpuri. | 1.19 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar, XEN(TD) | Technical Bid opened on 25.05.2023 & under process. |
| 79 | Dismantling of existing godown no.19 to 23 inside cargo jetty area | Part A 0.26 and PART ‘B’ 0.93 (Credit item) | Part A 0.085 and PART ‘B’ 2.20 (Credit item) | 216.51% Above. | NA | M/s. Avance Infratect. I. P. Ltd. Delhi | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Tender discharged and re-invited. Preliminary bid opened on 27/06/2023 |
| 80 | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years | 1.13 | 0.82 | 27.27% below | PL/WK/8461-I/25 dated 09/02/2022 | M/s. Sanjay K Sorathiya & Co. | 09/02/2022 | 24 Months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in Progress |
| 81 | Repairs and maintenance of pontoons and walk ways of passenger jetty No: 1 & 2 inside cargo jetty area at New Kandla. -HD-07/19 | 1.12 | 1.20 | 7.21% above | HW/WK/2379-III/332 dated 05/12/2019 | M/s. Patel Construction Co. | 18/12/2019 | 12 months 1st Extension upto 17/12/2021. 2nd extension upto 17/06/2022 | Shri Mahesh Makhijani, XEN(H) | Work in progress. Proposal for extension upto 17/06/2023 submitted for approval. |
| 82 | Maintenance contract for quay and transit area inside cargo jetty area for two years | 1.04 | 0.87 | 16.77% | HW/WK/2617/12 dated 24/09/2021 | M/s. Sanjay K Sorathiya & Co. | 10/10/2021 | 09/10/2023 24 Months | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 83 | Maintenance Contract for Tree Plantation near offices, other buildings, along roads, islands, gates, etc. inside/outside cargo jetty area for two years | 0.97 | 0.62 | 35.82% below | HW/WK/ 2582/284 dated 17/03/2023 | M/s. Vihat Construction, Gandhidham | 25/03/2023 | 24/03/2025 24 months. | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 84 | Maintenance Contract for Residential & Non - Residential Building at New Port Colony at New Kandla for two years. | 0.97 | 0.62 | 36.20% below | RW/WK/7816-I/242 dtd. 17/10/2022 | M/s. Murlidhar Projects | 17/10/2022 | 16/10/2024 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work in progress. |
| 85 | Dismantling of Residential and Non - Residential buildings at New Kandla | 0.96 | 1.58 | 64.42% above | RW/WK/7706-I/19 dtd.08.12.2021 | M/s. Symcom Exim (P) Ltd., Mumbai | 16.12.2021 | 15.08.2022 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work is under dispute and the matter is referred to court |
| 86 | Two Years Contract for House Keeping & Cleaning of Gate office buildings and Non-residential buildings inside cargo jetty area | 0.96 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Price bid opened on 26/06/2023 |
| 87 | Maintenance Contract for sanitation of New Port Colony, New Kandla for period of 2 years | 0.95 | 0.56 | 41.00% below | RW/WK/7820-I/375 dated 02/06/2023 | M/s. Acer Infra Trade, Gandhidham | 05/06/2023 | 04/06/2025 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work in progress. |
| 88 | Running & housekeeping of Guest house, A-9 bungalow & bachelor accommodation / bungalow at Port colony, Gopalpuri, Gandhidham for 03 years | 0.90 | 0.83 | 7.76% below | - | M/s. Bansal Enterprise | - | - | Shri Hemant Kumar Bhaskar XEN(Road) | Price bid opened and L1 is under process. |
| 89 | Providing firefighting pipeline at 34 hectares inside cargo jetty area (A) Appointment of Technical Advisor for the work of Upgradation of firefighting system & associated facilities inside cargo jetty area. DPA | 0.86 | 0.80 | 6.39% below | PL/WK/8476-I/21 dated 21.12.2022 | M/s. S.R. Engineers | 26.12.2022 | 18 months | Shri Rajendra Prasad B., Superintending Engineer (PL) | Work in progress |
| 90 | Two years contract for cleaning of storm water drain inside cargo jetty area | 0.78 | 0.49 | 37.18% below | N.A. | M/s. Narayan Construction Co. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | LOA issued 08/06/2023. |
| 91 | White washing, painting & distempering to residential and non-residential buildings & CISF complex at New Port Colony, New Kandla (for 2 years) | 0.67 | 0.38 | 43.20% | RW/WK/7790-I/ dated 05/2022 | M/s. Rajput Infrastructure Co., Gandhidham. | 01/06/2022 | 31/05/2024 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress. |
| 92 | House keeping & cleaning of office building inside cargo jetty area (for 2 years) HD-10/19 | 0.54 | 0.4128 | 23.43% below | HW/WK/2422-I/367 dated 20/02/2021 | M/s. Shree Ganesh Construction, Anjar | 06/03/2021 | 05/03/2023 Extension granted upto 02/07/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 93 | Housekeeping of liaison office cum rest house for DPA at Ahmedabad port for 3 years | 0.54 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(Road) | Price Bid opened & under process |
| 94 | Maintenance Contract of 1.5 MLS Sewage treatment plant at New Port Colony, New Kandla for 2 years | 0.52 | 0.29 | 45.13% below | RW/WK | M/s. Gadhvi Construction Co., | 21/06/2022 | 20/06/2024 | Shri Manoj Gohel XEN(Road), | Work in progress. |

MEGA INFRASTRUCTURE PROJECTS

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 95 | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT basis under PPP mode | 4243.64 | NA | NA | Tender No. CE/13 | M/S Hindustan Infralog Private Limited | LOA Awarded Dated 28/01/2023 | 36 months from the date of award of concession | Shri K. J Todarmal S.E (Design) | RFP opened on 27.01.2023, M/S Hindustan Infralog Private Limited was declared as successful Bidder. Subsequently, LOA was issued on 28.01.2023 and the same was acknowledged and accepted by M/s. Hindustan Infralog Private Limited on 31.01.2023. From time to time, on the Request of M/s. Hindustan Infralog Private Limited, the time for signing the Concession Agreement was extended. On 25.04.2023, on the request of M/s. Hindustan Infralog Private Limited, the time period for execution of Concession Agreement between the Authority and SPV was further extended up to 20.06.2023 and the same was intimated to M/s. Hindustan Infralog Private Limited. |
| 96 | Development of multipurpose cargo (other than container/ liquid) berth off Tuna Tekra outside Kandla Creek at Kandla on BOT basis | 1719.22 | NA | NA | Tender No. CE/14 | NA | under Bidding stage | 30 months from the date of award of concession | Shri K. J Todarmal S.E (Design) | Due to NO response from the Pre-Qualified Bidders RFP was discharged and same has been intimated to the Pre-Qualified Bidders .Based on the approval of Authority, RFQ (2nd Attempt ) floated on 30.06.2023 |
| 97 | Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis | 448.00 | NA | NA | Tender No. 05/SE(D) Dated 16.11.2013 | M/s Nayara Energy Limited (formerly Essar Oil Limited) | Work not yet started | 36 months from date of award of concession (Revised : 42 months from date of award of concession) ( six months extension granted by DPT due to COVID 19 Force Majeure) | Shri K. J Todarmal S.E (Design) | Total LD levied on M/s CETL (period of delay 16/2/2021 to 31/03/2023) is Rs. 17,33,76,000. However, payment of LD is awaited from M/s CETL. * Note: PRESENT STATUS: The Scheduled construction Period (revised) 42 months have elapsed on 15/02/2023 but M/s CETL not initiated project Implementation. |
| 98 | Development of Oil Jetty to handle liquid cargo and ship bunkering terminal at Old Kandla on BOT basis | 343.00 | NA | NA | Tender No. 026/XEN (Design) Dated 16.04.2015 | M/s IMC Limited | 11.12.2020 | 24 months from date of award of concession | Shri K. J Todarmal S.E (Design) | The Scheduled construction period is completed on 10.12.2022.. Interim Milestones no 2nd, 3rd, 4th & 5th have been delayed. LD imposed. On 23.05.2023, M/s KOTPL deposits Rs 5,91,00,800 towards LD upto 30.04.2023.The Demand Note of LD amounting to Rs 36,20,800/- for the period 1.05.2023 to 31.05.2023 issued to KOTPL for not achieving the milestone. |

Ro-Ro / Ro-Pax Ferry Service Cell

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 99 | Maintenance Dredging at Underneath/Periphery of Landing Pontoon of Ro-Pax facility at Dahej Terminal for 12 Months. | 2.43 | 2.22 | 8.5926% (Below) | CN/WK/1600/DAHEJ/17-A DATED – 11/05/2021 | M/s. Divine Shipping Services, Ahmedabad | 12-05-2021 | 12 Months Extension granted upto 10/01/2023 | Shri Rajendra Prasad Bethi, SE(P) | 1st extension from 11.05.22 to 10.09.22, 2nd extension from 11.09.2022 to 10.01.23, 3rd extension from 11/01/2023 to 31/03/2023 and 4th extension from 01/04/2023 to 10/05/2023 has been approved by Competent authority. |
| 100 | Construction of RORO/ROPAX facility at Muldwarka, Gujarat. | 84.74 | 76.69 | 9.5% (Below) | LOA No.CN/WK/1600-Const/Muldwarka/7 dated 14/01/2022 | M/s. BMS Projects – Marymatha JV | 10-05-2022 | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | Interim W/O for fabrication of Pontoon and Linkspan at Hazira, awarded on 10/05/2022. Final W/O shall be awarded after receipt of EC & CRZ. |
| 101 | Dredging in Approach channel Turning Circle, Berth pockets and surroundings of landing pontoon etc at Ghogha Ro-Ro Terminal Gujarat. | 28.63 | 45.81 | 60% (Above) | CN/WK/1600- GHOGHA (7BCD)/51 Dated – 25/04/2022 | M/s. Rock & Reef Dredging Pvt Ltd., Navi Mumbai | 25-04-2022 | 4 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. 4 months extension from 23.08.2022 to 15.12.2022 and 2nd extension from 16/12/2022 to 31/03/2023 and 3rd extension upto 30/06/2023 has been granted by competent authority. 4th extension from 01/07/2023 to 29/12/2023 is under process. |
| 102 | Monitoring for smooth functioning of Ro-Ro Facility services located at Hazira, Dahej and Ghogha. | 1.95 | 1.67 | 14.36% (Below) | CN/WK/1600/ 38 dated 29/03/2022 | M/s. Dhanjibhai K Patel | 01-04-2022 | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in progress. |
| 103 | Construction of Ro – Ro / Ro-Pax On – Shore facility at Muldwarka – Gujarat, EPC mode. | 30.81 | 33.88 | 9.97% (Above) | CN/WK/1600/Onshore Muldwarka/137 dated 15.07.2022 | M/s. MMC Projects (India) Pvt Ltd., Gandhidham | 25-07-2022 | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | Work Order issued. Work is stopped due to local people's interference. EC is awaited. |
| 104 | Annual Maintenance contract of Linkspan Pontoon and Terminal facilities of Dahej & Ghogha Ro-Pax ferry terminal | 3.90 | 3.90 | - | Supplementary Work Order No. CN/WK/1600/55 Dated – 09/07/2021 | M/s. Vishwakarma Mechanical works, Porbandar | 08-03-2019 | 07-03-2021 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Proposal for extension of work from 07/09/2021 to 06/07/2023 (22 months) and Anticipated variation statement No.2 with extra items for net excess of Rs.3,94,36,435.00 i.e. 101.11% excess on the tendered cost of Rs.390.04 lakhs approved by the Board in its meeting on 03/02/2023. |
| 105 | Construction & Maintenance of Ro-Pax facility at Hazira-Gujarat on EPC mode | 66.35 | 69.06 | 4.09% above | CN/WK/1600/Pre-bid/10 dated 15.04.2021 | M/s. BMS Projects-Marymatha JV | 21/04/2021 | 14 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. 1st Extension upto 20.09.2022 and 2nd extension upto 20.10.2022 has been granted by the competent authority. Anticipated Variation Statement No.1 for net excess of Rs.7.91 Crores is under approval. |
| 106 | Construction of Ro-Ro/Ro-Pax On-shore facility at Pipavav-Gujarat on EPC mode | 36.53 | - | - | - | - | - | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | The tender has been discharged as per approval of competent authority dated 22.11.2022. |
| 107 | Annual Maintenance Contract of Navigational Channel Marking System (Buoys) at Ghogha Ro-Pax | 0.86 | 0.94 | 8.93% above. | - | M/s. Somnath Metal Cast, Bhavnagar. | - | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Work Order issued. Work in progress. |
| 108 | Annual Maintenance Contract of Navigation Channel Marking System (Buoys) at Dahej & Ghogha – Ro Pax Online Tender ID 383191 | 0.48 | 0.48 |  | Supplementary Work Order No. CN/WK/1600/49 Dated – 29/06/2021 | M/s. Sai Sagar Dredging & Marine Services Pvt. Ltd., Bharuch | 03-03-2020 | 02-03-2021 Extension granted upto 01/07/2023 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Anticipation Variation Statement No.2 for net excess of Rs.75,69,087/- i.e. 156.26% excess on the tendered cost of Rs.48,43,830/- approved by the Board in its meeting on 03/02/2023. |
| 109 | Annual Maintenance Contract for Link spans, Pontoons and Terminal facilities at Ghogha | 2.99 | - | - | - | - | - | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Price Bid opened on 07/06/2023 and L1 is processed for approval. |
| 110 | Annual Maintenance Contract for Link Spans, Pontoons and Terminal facilities at Dahej | 3.00 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | Technical bids under scrutiny. |
| 111 | Annual Maintenance contract for Navigational Channel marking system (Buoys) at Dahej - Ro- Pax | 3.69 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | IInd stage of preliminary bids done on 16.05.2023. Technical evaluation of bids is done. Approval of TCM for technical qualification of bidder done on 20.06.2023, wherein both bidders were disqualified as not qualifying Min. criteria. |
| 112 | Maintenance Dredging at Periphery of landing pontoon of Ro-Pax facility at Dahej Terminal for 12 months | 2.22 | 1.99 | 9.99% below | - | M/s. BSP Hydro Dredging Works Pvt. Ltd., AP. | - | 12 months | Shri Rajendra Prasad Bethi, SE(P) | Work Order issued. |
| 113 | Engagement of Security agency for providing watch & ward security supervisor & security guard without arms for Dahej terminal of DPA for 2 years | 0.81 | 0.7 | 13.41% below | CN/WK/1600/Security/132 dt. 04.05.2023 | M/s. Shakti Protection Force Pvt. Ltd. | 08/05/2023 | 24 months | Shri Rajendra Prasad Bethi, SE(P) | W.O. issued on 04.05.2023. Anticipated variation statement for Net excess of Rs. 10,69,566.80 i.e. 15.18% has been in-principle approved and submitted to Variation committee. |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No | Name of work & location | Reserve price Per sq. mtr./year | Premium received over and above reserve price during e-auction (per sq. mtr. / per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 114 | E-Tender cum E-Auction for the allotment of Various size of plots for Salt manufacturing and salt related activities in between Village Veera to Village Jhungi on 30 years lease on as is where is basis. | Rs. 25923.30 (per acre/per annum) | Plot No.1-Rs.200 Plot No.2- Rs.400 Plot No.3 Rs.500 Plot No. 5 Rs.200 Plot No. 6 Rs.200 Plot No.07 Rs.300 Plot No.08 Rs.4200 Plot No. 09 Rs.4100 Plot No.10 Rs.700 | Plot No.01 LW/PL/3507-I/605 DATED 14.06.2022 Plot No.02 LW/PL/3507-I/607 DATED 14.06.2022 Plot No.03 LW/PL/3507-I/603 DATED 14.06.2022 Plot No.05 LW/PL/3507-I/604 DATED 14.06.2022 Plot No.06 LW/PL/3507-I/601 DATED 14.06.2022 Plot No.07 LW/PL/3507-I/602 DATED 14.06.2022 Plot No.08 LW/PL/3507-I/609 DATED 14.06.2022 Plot No.09 LW/PL/3507-I/606 DATED 14.06.2022 Plot No.10 LW/PL/3507-I/608DATED 14.06.2022 | Plot No.1 - M/s. Priya Salt & Chemicals Pvt. Ltd. Plot No.2 - M/s. Shri Pingleshwar Salt Industries. Plot No.03 - M/s. Lakshmiwadi Mines & Minerals Pvt. Ltd. Plot No. 5 - M/s Patel Salt & Alied Industries Plot No.06 - Aashwat Salt and chemicals Pvt. Ltd. Plot No.07 - M/s Daivya Salt & Chemicals pvt. Ltd. Plot No. 8 - M/s Patel Salt & Allied Industries Plot No. 09 & 10 - M/s. Shamji Kangad & Co. | 30 years from date of Possession | Shri Sunil Soren XEN(KL) | Online Price Bids opened on 03.03.2022. E-Auction of plots was carried out on 06.06.2022 to 10.06.2022. Pre acceptance letter issued on 13.06.2022. Allotment letter issued on 14.06.2022 & Possession was given on 15.06.2022. Lease Deed is under execution. |
| 115 | E-Tender cum E-Auction for the allotment of plot Admg. 4000 Sq/Mtrs situated opposite to VTMS towers and behind boundary of DPT (East of dry dock) for the purpose of Barge Repairing/Beaching on 5 years lease basis on as where is basis. | Rs. 277.12 | Rs. 20 | LW/PL/3493/633 DATED 15.06.2022 | M/s. Amrut Dredging & Shipping Ltd. | 30 years from date of Possession | Shri Sunil Soren XEN(KL) | The tender has been re-invited and price bid opened on 27.04.2022. E-auction was carried on 05.05.2022. Board vide Resolution No.25 dated 27/05/2022 approved the proposed for allotment of Land to M/s. Amrut Dredging And Shipping Ltd. Accordingly, Pre-Acceptance Letter was issued on 08/06/2022. Allotment letter was issued on 15.06.2022 & Possession of Land given on 01.07.2022. Lease Deed is under execution. |
| 116 | E-tender cum E-auction for allotment of 06 Nos. of plots (with structure) situated at old/new Kandla for the purpose of liquid storage tanks (products permitted in the earlier Lease Deed/ Allotment Letter) on 30 years lease on as is where is basis(Phase-I). | Rs. 1060.56 | Rs.30 (Area 14250) Rs.10 (Area 13770) Rs.10 (Area 25000) | …. | M/s Samayak Steel Company (14250) M/s M.R. Shah Logistic Ltd. (13770) M/s CRL Terminals Private Limited (25000) | …. | Shri Sunil Soren XEN(KL) | NIT published on 27/04/2022,pre-bid meeting held on 04/05/2022. Technical bid OPENED on 11.10.2022 .price bid opened on 28.12.2022. E-Auction was carried out on 16-01-2023 to 17.01.2023. In auction single bid received on Sr No. 01,03, & 06. Re-invite the E-tender cum E-auction for 03 nos. of plots in which single bid are recieved on same terms and conditions as approved by the Board vide resolution No.44 except submission of the Solvancy Certificates which is deleted as per the Finance dept. Note No. FA/WA/Tendering/1475 dated 04.01.22, keeping the reserve price of Rs.1081.77 (G1 category). Allotment letter issued to Parties. |
| 117 | E-tender cum E-auction for allotment of 04 Nos. of plots (with structure) situated at old/new Kandla for the purpose of liquid storage tenks (products permitted in the earlier Lease Deed/ Allotment Letter) on 30 years lease on as is where is basis(Phase-II). | Rs. 1060.56 | …. | …. | …. | …. | Shri Sunil Soren XEN(KL) | NIT published on 27/04/2022,pre-bid meeting held on 04/05/2022.Date of opening of tender extended up to 13.07.2023 |
| 118 | E-Tender-cum-e-auction for allotment of 04 Nos. of plots for the purpose of Liquid Storage Tanks situated at Kandla on 30 years Lease on as is where is basis. | Rs. 1060.56 | …… | ….. | …… | ….. | Shri Sunil Soren XEN(KL) | NIT published on 04/01/2023,pre-bid meeting held on 16/01/2023. Technical bid opened on 24.03.2023. Price bid opened on 27/03/2023. E-auction carried out on 26/06/2023 & 27/06/2023. |
| 119 | E-Tender-cum-e-auction for allotment of 06 Nos. of Plots for the purpose of Godown / Warehouse situated at Kandla on 30 years Lease on as is where is basis. | Rs.231.86 | …… | ….. | …… | ….. | Shri Sunil Soren XEN(KL) | NIT published on 03/01/2023,pre-bid meeting held on 16/01/2023. Technical bid opened on 28.02.2023. E-auction will be carried out on 02.05.2023 to 04.05.2023. pre-acceptance letter issued on 26.06.2023 to the successful tenderer. |
| 120 | E-Tender cum e-auction for allotment of 3 Nos. of Plots (with structure) situated at Old / New Kandla for the purpose of Liquid Storage Tanks (Products permitted in the earlier Lease Deed / Allotment letter) on 30 years Lease basis on as is where is basis. | 1081.77 | …… | ….. | …… | ….. | Shri Sunil Soren XEN(KL) | NIT published on 28/02/2023,pre-bid meeting held on 10/03/2023. Technical bid opened on 13.04.2023. E-auction will be carried out soon. |
| 121 | E-Tender for appointment of Land Valuer for valuation of land rates in the Port Estate of Kandla from Village Veera to Village Jungi which includes Kandla, Tuna, Kharirohar and Bhachau, excluding Salt Lands & SIPC land for the year 2024-2028. | …… | …… | ….. | …… | ….. | Shri Sunil Soren XEN(KL) | NIT published on 18.05.2023, date od downloading tender 13.06.2023, last date of online submission 13.06.2023, bid open & preliminary bid under evaluation |
| 122 | E-Tender for Empanelment of Valuer for carrying out the Valuation of Assets lying in the Plots allotted to respective parties. | …… | …… | ….. | …… | ….. | Shri Sunil Soren XEN(KL) | NIT published on 18.05.2023, date od downloading tender 30.05.2023, last date of online submission 30.06.2023, pre-bid meeting held on 09.06.203, online opening of Technical bid extended upto 10.07.2023 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

4 .	MARINE DEPARTMENT							                                                                                      AS ON 30.06.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring or 2 Nos. of Tugs on Charter / Rate per year for the period of 10 years, extendable for one year. | 214.87Cr. | 209.87 Cr. | 0.86% below | Executed on 15/03/2023 | M/s. Ocean Sparkle Ltd. Hyderabad | Yet not commenced | 10 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 19/04/2022 |
| 2. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | - | Executed on 09/03/2022 | M/s. Electronics Corporation of India Ltd., Hyderabad | 25/11/2021 | 24 months for supply, installation and commissioning AMC 10 years after installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Supply & Installation work completed on 25/11/2020. AMC work in progress. |
| 3. | Hiring or 2 Nos. of Steel Hull Mooring Launches and Moorings Gangs at Deendayal Port, Kandla for a period of 5 years. | 14.60 Cr. | 10.76 Cr. | 26.24% below | Executed on 27/11/2022 | M/s. Pacific Shipping Services, Mumbai | Yet not commenced | 5 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 28/09/2022 Work Order issued on 02/11/2022 |
| 4 | Hiring of 04 Nos. of 50/60 Ton Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below. 20.08% below | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator | W.O. has been issued on 03/10/2016 & 22/09/2016. |
| 5 | Hiring of 165 Nos. of Manpower in the cadre at Firefighters for Port services at DPA, Kandla on Contractual basis for a period of 3 years. | 6.58 Cr. | 6.38 Cr. | 12.93% below | Executed on 27/04/2023 | M/s. Krishna Industrial Security & Fire Services Pacific Shipping Services , Anand Gujarat. | Yet not commenced | 3 years | Capt. Pradeep Mohanty,, Deputy Conservator | LOA issued on 13/02/2023. |
| 6 | Appointment of Agency for providing manning services /VTS operations at Kandla & Vadinar Port monitoring stations - VTS for the period of 3 years. | 5.41 Cr. | 5.93 Cr. | 9.69% above | Executed on 19/04/2023. | M/s. Admiral Marine Services P, Ltd., Chennai | Yet commenced. | 3 years | Capt. Pradeep Mohanty,, Deputy Conservator | LOA issued on 20/02/2023 Work Order issued on 20/03/2023. |
| 7 | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | 26/04/2021 | 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 13/10/2020. Work Order issued on 05/01/2021. |
| 8 | Renewal of Steel Plates & painting of various crafts / Tugs of DPT | 2.09 Cr. | 1.80 Cr. | 14.19% below | Executed on 16/06/2021 | M/s. Patel Engineering Works, Gandhidham. | 06/08/2021 | 2 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 21/05/2021. Work Order issued on 13/07/2021. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 30.06.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of brand new make of 64 Nos. of vehicles Model-2023) EV/Diesel / Petrol, on monthly hired basis and hiring of vehicles not earlier than 2022 on äs and when required basis "for a period of 3 years. | 19.33 Cr. | 16.02 Cr. | 16.97% below | Executed. Work Order No. GA/GN/5400/2023-25/815 dated 10/03/2023 | M/s. Rishabh Enterprises, Gandhidham. | 01/04/2023 | 31/03/2026 | Shri Deepak Rane, Dy. Secretary | Work in progress. |
| 2. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |
| 3. | Engagement of Security Agency for providing Watch & Ward Security Supervisors & Security Guards without arms for various Departments of DPA for the period of 02 years. | 5.92 Cr. | 5.13 Cr. | 13.34% blow | Executed Work Order No. ES/SR/2443/ Security/1 dated 26.03.2021 ES/SR/2443/ Security/2 dated 26.03.2021 ES/SR/2443/ Security/3 dated 26.03.2021 | M/s. Shakti Secuirty, Surat. M/s. Panther Surveillance, Ahmedabad. M/s. Rajput Security Services, Ahmedabad. | 26/03/2021 | 25/03/2023 Extended upto 30/09/2023 | Shri Omprakash Dadlani, TP & PRO & Nodal Officer, (Security) | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6.	MEDICAL DEPARTMENT										                                            AS ON 30.06.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |
| 2 | Outsourcing of Vadinar Hospital for treatment of employees of DPA, CISF Personnel and CISF employees engaged by DPA and IOCL and their family members as well as other persons as decided by DPA at Vadinar | 2.88 Cr. | 2.07 Cr. | 26.80% below | MH/SP/85/ 2020-21 | M/s. Shree Samarpan Wellness Pvt. Ltd., Rajkot | 16/05/2022 | 3 years. | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	TRAFFIC DEPARTMENT											                	AS ON 30.06.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Engagement of manpower service provider for providing various categories of outsourced staff to carry out railway operation inside Cargo Jetty area for a period of 3 years. | 3.88 Cr. | 2.87 Cr. | 26.00% below | Executed on dated 26/07/2021 | M/s. Dhanjibhai K. Patel, Anjar. | 01/05/2021 | 30/04/2024 | Shri T.D. Maheshwari, ATM (Railway), | Work in progress. |
| 2. | Outsourcing of Establishing and operating of occupational health services at Deendayal Port Authority, New Kandla for the period for 5 years. | 3.54 Cr. | 2.98 Cr. | 16.59% below | Executed on dated 15/12/2021 | M/s. Accord Multispecialty Hospital, Bhuj | 15/05/2021 | 5 years from the date of commencement | Safety Officer | Work in progress. |
| 3. | Engagement of Consultant to authenticate / validate the reports submitted by the PPP Operator for three (3) years | 2.56 Cr. | 2.77 Cr. | 9.99% Above | Executed on dated 10/10/2022 | M/s. Aarvee Associates Architects Engineering & Consultant Pvt. Ltd., Hyderabad | 17/10/2022 | 16/10/2025 | Asstt. Traffic Manager (PPP) | Work in progress. |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	FINANCE DEPARTMENT										                                     AS ON 30.06.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |

*****