DEENDAYAL PORT AUTHORITY

TENDERS / CONTRACTS UNDER INTEGRITY PACT

1.	MECHANICAL ENGINEERING DEPARTMENT													AS ON 30.09.2023

| Sr. No. | Name of work and location | Estimated cost (Rs.) in Crores | Tendered Cost (Rs.) in Crores | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 1 | Global Tender for Engineering, procurement and construction for development of mechanized fertilizer and other clean cargo handling facility at Berth No.14 in DPA, Kandla. | 290.85 | -- | --- | --- | --- | --- | --- | --- | Bid opening date 06.10.2023 |
| 2 | Procurement of 04 Nos. of 100 M.T. & above capacity Tyre mounted Electric and Diesel driven (Duo) HMC’s with Five Years Operation & comprehensive AMC (CAMC) after free CAMC of Two years. | 210.95 | -- | --- | --- | --- | --- | --- | --- | Bid opening date 04.10.2023 |
| 3 | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 155.70 | 144.46 96.86 towards capital cost & 47.60 towards O&M Charges. | 7.22 Below | EL/WK/2491/1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri D.K.Hazra, XEN (E) | Comprehensive A.M.C. work in progress. |
| 4 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 120.94 | 122.33 | 0.9% above | LoA issued vide MS/WK/4025-II/GIM-265 dtd. 31.03.2017 | M/s. RISHI Shipping, Gandhidham | 31/03/2017 | 10/07/2026 | Shri Aman Imran B. AXEN(M) | LoA issued on 31.03.2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect upto10/07/2026. |
| 5 | Design, Manufacture, Supply Erection, Testing, Commissioning & Operation of 02 Nos .of 100 Ton or above capacity of Mobile Harbour Crane at Dry Cargo Berths, including Comprehensive AMC with Operation for a period of 05 years. | 91.82 | Euro 79.31 Lakhs + customs Duty (Supply) Rs.20.10 crore (for CAMC) Total INR amount of Rs.93.15 crore (While evaluation of bid) | 0.73% below | EL/WK/2504/531 dated 21/07/2017 | M/s. Italgru, s.r.l. Italy | w.e.f. date of opening of letter of Credit(LC) i.e., 10/08/2017 & CAMC Work commence from 07/05/2018 | 07/11/2023 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | CAMC work in progress. |
| 6 | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 81.82 | 63.60 | 22.27 Below | EL/WK/2472/480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Comm’ned on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri D.K. Hazra, XEN(E) | Comprehensive A.M.C. work in progress. |
| 7 | Design, Supply, Installation, Testing & Commissioning of Firefighting system and associated facilities including Operation & Maintenance for a period of five years as per OISD-156 at Oil Jetty No. 08, Kandla, of Deendayal Port Authority ( EPC Contact) | 63.62 | 69.98 | 10% Above | W.O. No. MS/WK/4054/AOB/29 dated 08/05/2023 | M/s. Jay Project, Vadodara | 08.05.2023 | 07/01/2024 for SITC work & 07/01/2029 for O & M Work | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
| 8 | Revamping and upgradation of Firefighting system and associated facilities at Oil jetty area- Task-I: SITC of water pump / water pumping system including AMC of 5 years. | 33.77 (37.02 with credit item of 3.25 ) | Net Rs. 38.64[i.e. Part A (EPC(SITC) Rs. 39.56 [i.e. Rs. 39.67- (minus) Rs. 0.11 discount offered in negotiation] (plus) AMC of 5 years Rs. 1.00 (minus) Part B : Credit item : Rs. 1.92] | 14.41 % Above | W.O. ML/WK/4052(Re-tender)/ 343 dated 29/08/2022 | M/s. Jay Project, Vadodara | 29/08/2022 | 24/02/2024 for SITC work & 24/02/2029 for AMC Work | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
|  | Task-II: SITC Firefighting system & associated facilities alongwith Pipeline, civil structure etc. including AMC for a period of 5 Years. | 49.55 | 45.00 | 9.17% Below | W.O. ML/WK/4058/ 350 dated 01/09/2022 | M/s. Patel Construction Co., Gandhidham | 01.9.2022 | 28/02/2024 for SITC work & 31/08/2029 for AMC Work | Shri Mani Pushpak Sethi SE(M) | Work in Progress |
| 9 | Supply, installation, testing & commissioning of Sprinkling System for coal dust suppression in 34-hectare coal yard with five Years Operation & Comprehensive Maintenance contract. | 28.11 | 24.48 | 12.92% Below | MS/WK/4046-I/GIM/592 dated 18/02/2022 | M/s Omkar Enterprise, Ahmedabad | 18/02/2022 | 03/04/2028 | Shri Mani Pushpak Sethi SE(M) | O & M Work in progress. |
| 10 | Design, Supply, installation, testing & commissioning along with Comprehensive Operation & Maintenance for a period of Five Years of 02 Nos Column Type Vessel access telescopic gangway system at Oil Jetty No. 07 and 08 of DPA. | 22.83 | 18.97 | 16.90% Below | MS/WK/4056-I/AOB-30 dt. 08/05/2023 | M/s. Woodfield Systems International Pvt Ltd, Mumbai | 08.05.2023 | 07/02/2024 for SITC work & 07/02/2029 for O&M Work. | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
| 11 | Operation and maintenance of 66 K.v. Substation and overhead / underground 66 K.v. Transmission Line, AMC of H.T. /L.T. Electrical Installation of Residential & Non- Residential Buildings with-in Kandla premises including Tuna Port & engagement of service operator and advisory services distribution business metering and billing for a period of Three Years. | 16.18 | 16.97 | 4.88% Above | LOI EL/WK/2799-Est./462 29.08.2023. | PTC India New Delhi. | ---- | ---- | Shri D.K. Hazra, XEN( E) | LOI issued on 29.08.2023. |
|  | Design, Supply, Installation, Testing, Commissioning of Firefighting facilities as per OISD–156 including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT. | 15.34 | 16.84 | 9.76% above | Work Order: MS/WK/4052/Gim-94 Dated 30.08.2022 | M/s. Sterling And Wilson Pvt. Lltd. | 30/08/2022 | 30/11/2023 for SITC work & 30/11/2028 for O&M Work. | Shri Aman Imran B. AXEN(M) | SITC work under is progress under extension period. (95 % work completed) |
| 12 | Operation and maintenance contract of 02 Nos. Italguru make HMC of 120 Ton capacity along-with grabs inside C.J. area for period of two years. | 11.02 | - | - | - | - | - | - | - | Bid opening date 03.10.2023 |
| 13 | Comprehensive AMC for Port owned two nos. of Pilot Launches & four nos. of Mooring Launches and complete O&M for one Pilot Launch & one Survey Launch for a period of three years. | 8.94 | 7.92 | 11.36% Below | LOA No. ML/WK/4068/692 dt. 15/05/2023 | M/s. Hoger Offshore and Marine Pvt. Ltd. Mumbai | 18.05.2023 (After 3 Days from LOA) | 17.05.2026 | Shri Rajdeo Marine Engineer Gr.I | Work in Progress |
| 14 | Outsourcing of 02 Nos. each Truck Mounted Mist Cannon system, and, Truck Mounted Road Sweeper system, along with comprehensive operation & maintenance, for the period of three years at DPT. | 8.93 | 10.19 | 14.12% above | MS/WK/4047/GIM-542 Dated 21/12/2021 | M/s Sambhav Corporation, Ahmedabad | 23/12/2021 | 22/12/2024 | Shri Dana Manohar, XEN(M) | Work in Progress |
| 15 | Operation and Maintenance contract of industrial light at cargo handling area, open plots, jetty area, godowns, street lighting connecting to port gates including maintenance of 11/0.433 KV substation inside cargo jetty area from zero panel to berth no. 10 and 13th to 16th berth. | 8.51 | 5.29 | 37.84% Below | Work Order No. EL/AC/2709/2092 dated 05.7.2022 | M/s. Daxraj Electricals | 05/07/2022 | 04/07/2024 | Shri D. K. Hazra XEN (E) | AMC in progress |
| 16 | Operation & Maintenance Contract of 2 Nos. Liebherr make LHM 550 model Harbour Mobile Cranes along with 03 nos. Grabs inside cargo jetty area for a period of Two years. | 8.20 | 6.92 | 15.60% Below | W. O. No. EL/WK/2028 17/02/2023 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 20.02.2023 | 19.02.2025 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | Work in progress. |
| 17 | Maintenance contract of 03 nos. 25T and 02 nos. 16 T capacity MBE crane wharf cranes, alongwith grabs for a period of 2 years at inside cargo jetty area. | 7.42 | Rs. 7.05 | 5.00% below | LOI No. EL/WK/2691/947 dated 25.02.2022 | M/s. R. S. Electricals, Gandhidham | 16/02/2022 | 15/02/2024 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | AMC in progress. |
| 18 | Supply, installation, testing & commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) unit, integral capstan and remote control type including Operation & Maintenance for five years at Oil Jetty No 08 of DPA. | 6.89 | 6.43 | 6.68% below | W. O. No. MS/WK/4058/AOB-05 dated 15.02.2023 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 15.02.2023 | 14/06/2023 for SITC work & 14/06/2028 for O&M Work. | Shri Dana Manohar, XEN(M) | Civil Work in progress and QRMH Work will commence after completion of Civil work. |
| 19 | Special Repairs to Steel Floating Dry Dock – Self docking and repairs of Pontoon No. 5 & 6. | 6.60 | 5.41 | 18% Below | Work Order No. DD/WK/3070/41 dated 23.08.2023 | M/s. Patel Engineering Works, Gandhidham | 07.09.2023 | 06.04.2024 | Shri Himmat Makwana, AXEN(M) | Work in progress after 15 days from the date of issue of work order. |
| 20 | Outsourcing of Technical Manpower & staffs for attending various technical projects & works of the department for the period of five years. | 6.41 | 5.41 | 15.62 Below | MS/WK/4059/AOB/40 Dated 01.06.2023 | M/s. B M SORATHIA, MADHAPAR | 01.06.2023 | 31.05.2028 | Shri Mani Pushpak Sethi SE(M) | Work in progress. |
| 21 | Supply, installation, testing and commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) units, integral capstan and remote control type including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT. | 6.21 | 5.50 | 11.51% Below | MS/WK/4051/Gim-64 dated 04/07/2022 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 04/07/2022 | 31/01/2028 | Shri Dana Manohar, XEN(M) | O & M work is under progress since 01.02.2023. |
| 22 | Supply, Installation, Erection, Testing and Commissioning of S/C Overhead / Underground 66KV Line for providing power supply to IOCL, Kandla. | 6.11 | 6.09 | 0.3 % below | EL/WK/2757 LOI No. EL/AC/2757/1104 | M/s. Devangi Power Private limited, | 03.02.2023 (i.e. 11th day from issuance of LOI) | 26/08/2023 (150 days (i.e from 11th day from issue of LOI) With Extension Period. | Shri D.K. Hazra, XEN (E) & PTC | Work in progress. Extension up to 24.12.2023 |
| 23 | Annual Rate Contract for 11 KV distribution network at license area of DPA at Kandla. | 5.95 | 4.18 | 29.74% below | Work Oder No. EL/WK/2708/1340 dated 30/03/2023 | M/s. NK Industrial Services, Gandhidham | 01.04.2023 | 31.03.2025 | Shri D.K. Hazra, XEN (E) | AMC in progress |
| 24 | Maintenance contract of 2 Nos. ITALGRU make Harbour Mobile Crane of 63T capacity along with 6 nos. of grabs and comprehensive maintenance of Hydraulic (suspension and winch) pumps inside cargo jetty area for period of two years. | 5.70 | 4.32 | 24.21% | LOI No. EL/AC/2702/650dated 05-01-2022 | M/s. Italguru India Pvt. Ltd., New Delhi | 01/01/2023 | 31/12/2023 | Shri Aman Imran B. AXEN(M) & Shri Anil Rautiya, AXEN(E) | AMC in progress |
| 25 | ARC for supply & Laying of HT/LT/UG Cable, HT/LT/UG Cable fault finding inside & Outside Cargo Jetty area. | 5.39 | --- | --- | --- | --- | --- | --- | --- | Price bid opened & proposal under process. |
| 26 | Providing Power Supply & Illumination to oil Jetty No 08 at DPA, Kandla. | 4.97 | 4.37 | 12.136% below | EL/WK/2768/44 23.08.2023. | M/s. N.K. Industrial Service | --- | --- | Shri D.K. Hazra, XEN( E) | LOI issued on 23.08.2023 |
| 27 | Annual maintenance contract works at A.O. Building and Gopalpuri colony for a period of two years. | 4.96 | 3.48 | 29.84% below | W.O. No El/WK/2699/1219 dated 23/02/2023 | M/s N.K. Industrial Services | 01/03/2023 | 28/02/2025 | Shri D.K. Hazra, XEN (E) | AMC in progress |
| 28 | Providing of 11 Kv H.T. Power plug point on wharf side for operation of MHC from Berth No 6 to 10 & 13 to 16. | 4.74 | --- | --- | --- | --- | --- | --- | --- | Technical Bid opened on 01.09.23 & Under scrutiny. |
| 29 | Supply, Installation, Erection, Testing and Commissioning of Mast Tower 34 hectares area | 4.68 | 3.46 | 26.075 % below | LOI No. EL/AC/2723 Dtd 27.02.2023 & Work order No.EL/WK/2723 03/4/2023 | M/s. N. K. Industrial Services, Gandhidham | 27/02/2023 | 26.12.2023 | Shri Anil Runtia AXEN (E) | Work in progress. |
| 30 | Comprehensive AMC of Mech works and equipment. | 4.31 | 4.12 | 4.59% Below | MS/WK/4048 Dated 14/01/2022 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 15/01/2022 | 14/01/2027 | Shri Dana Manohar, XEN(M) | Work in progress. |
| 31 | Maintenance contract of 3 Nos. 25T capacity 4 rope TIL make ELL cranes along with Grabs at Berth No. 10 at Inside Cargo Jetty area for a period of 2 years. | 4.13 | 2.88 | 30.26% Below | W.O. No El/WK/2049/1247 dated 01/03/2023 | M/s. R. S. Electricals, Gandhidham | 05/02/2023 | 04/02/2025 | Shri Anil Rautiya, AXEN (E) | Work in progress. |
| 32 | Comprehensive Annual Maintenance Contract for Channel Marking, Dumping and Mooring Buoys in the Kandla Channel along with operation & Maintenance of Heave up Barge Bhimsen for a period of three years. | 4.00 | 3.68 | 8.17% Below | W.O. ML/WK/4040/ 336 dated 01/08/2022 | M/s. Seacrafts Industries (P) Ltd., | 06.8.2022 | 05.08.2025 | Shri Rajdeo Kumar, Marine Engineer Gr.I | Work in progress. |
| 33 | Upgradation of 66/11 KV GIS substation by replacement of the existing HT panel & control relay panels including civil building. | 3.40 | 3.08 | 9.35% below | EL/AC/2725/ TP/1065 Dtd: 12/01/2023. Work order No. EL/WK/2725/1187. 15/02/2023 | Shree Vallabh Electricals, Anand | 12/01/2023 | 08.12.2024 (330 Days) | Shir Anil R, AXEN (E) | Work in progress. |
| 34 | Construction of 16th berth for multipurpose cargo (other than Liquid/Container Cargo) – Supply, installation, testing and commissioning of High Mast Lighting Towers at Berth No. 16. | 3.16 | 2.72 | 13.88% below | EL/WK/2715/3554 Dtd. 14.11.22. | M/s. N.K. Industrial Service | 14.11.2022 | 31.10.2023 | Shri D.K. Hazra, XEN ( E) | Work in progress under extension period and to be completed on Oct-2023. |
| 35 | Refurbishing of Power supply of A.O.B. | 2.83 |  | - | - | - | - | - | - | Technical Bid opened on 14.08.23 & Under scrutiny. |
| 36 | Construction of Dome Shaped Storage sheds inside cargo jetty area- Electrification work. | 1.86 | 2.26 | 22.50% Above | EL/WK/2650-II, LOI No EL/AC/2650-II/3433, dated 06.10.2022 | M/s. Vishal Electricals, Ghaziabad (UP) | 09.12.2022 | 08.10.2023 | Shri D.K. Hazra, XEN(E) | Work in progress & Provisional Extension upto 08.10.2023 . |
| 37 | Major Repair Work of Heave Up Barge Bhimsen. | 1.67 | 1.56 | 6.41% below | ML/WK/4020-I(d)/156 dated 01/06/2022 | M/s. Patel Construction Co., Gandhidham | 01/06/2022 | 31/10/2023 | Shri Rajdeo, Marine Engineer Gr.I | Work in progress in under Extension period. |
| 38 | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhi-dham Area for period of three years. | 1.55 | 1.39 | 10.14% Below | DD/WK/4309/338 dated 04.08.2021 | M/s. Inspection & Engineering Services, Ahmedabad | 04/08/2021 | 03/08/2024 | Shri Himmat Makwana AXEN(M) | Work in Progress. |
| 39 | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weighbridges (15 Kmph speed) of 140Mt capacities including compre-hendsive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 1.51 | 1.48 | 2.07% below | W.O. No.ML/WK/3916-II/738 Dtd. 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., Chennai | 05/01/2019 | 17/12/2028 | Shri Aman Imran B. AXEN (M) | Work Completed on 18/12/2021. The weighbridges installed are under guarantee period of two years under CAMC |
| 40 | Electrical work for 66 KV feeder bay GETCO Substation and for feeder bay Extension. | 0.87 | 0.82 | 5.03 % below | LOI No. EL/AC/2575/ feederbay/ 3534, dated 02.11.2022 | M/s OM Power Transmission Ahmedabad | 12.11.2022 | 10.08.2023 | Shri Kumthekar, AE (E) & PTC | Work completed on 10.08.2023 |
| 41 | Re-wiring of 160 Nos. of FCI & DLB Colony Qtr. For allotment and shifting CISF family Qtrs. –Kandla to FCI & DLB Colony (Phase-II.) | 0.55 | -- | - | - | - | - | - | - | Price bid opened & proposal under process. |
| 42 | Up gradation of Power Supply Including Lighting Arrangement at Periphery at Tuna Port. | 0.54 | -- | - | - | - | - | - | - | Technical Bid Opened on 18/07/2023 & under scrutiny. |
| 43 | Design, Supply & Installation of control room fabrication with its associated works at pump house room at OJ-07 Kandla of DPA. | .54 | .47 | 12.73 % Below | LOI NO. MS/WK/4052/CR/253 Dated 08/09/2023 | M/s. Jyoti Engineering Works, Gandhidham | - | - | Shri Aman Imran B. AXEN (M) | LOI Issued. |
| 44 | Supply, installation, testing and commissioning of essential & integral components for the installed 02 nos. PSA oxygen units of 1000 LPM capacity each at Sir T Hospital Bhavnagar” donated by Deendayal Port Authority (DPA), under CSR scheme. | .50 | .48 | 5.57% Below | LOI No. MS/WK/4049-pt.1/Gim-PC/257 Dated 19.09.2023 | M/s. Air Shuddhi Engineers, Ahmedabad | - | - | Shri Aman Imran B. AXEN (M) | LOI Issued |
| 45 | Sell of renewable power generated from DPT’s 14.7MW wind power plant on Medium Term Open Access basis through tariff based competi-tive bidding through auction. | Rs. 4.26 per unit | Rs. 4.27 per unit | - | LOI No. EL/C/2688/1158, dated 10.11.2021 | M/s. UPL Ltd. GIDC Jhagadia- Bharuch | 29/12/2021 | 29/12/2022 Extension till 31/12/2023 | Shri D.K.Hazra, XEN(E) | MTOA has been extended with GETCO on 29/12/2021 and valid upto 31/12/2023. |
| 46 | Operation and maintenance for operation and main-tenance of 66 KV substation. | Not Applicable | 1.00 Per Year | Not Applicable | EL/WK/2736/3043 dated 14/07/2022 | M/s. PTC India Ltd., New Delhi | 12/08/2022 | 11/08/2024 | Shri D.K. Hazra XEN (E) | Work in progress. |
| 47 | Build, Operate and Maintain of 10 nos. of 120 T capacity each Automated road weighbridges on Revenue Sharing basis at DPA for a period of 10 years and buy–back of 10 nos. of existing Road weighbridges of DPA. | Tender is based on revenue sharing | Rs. 1.89 per Ton | Not Applicable | ML/WK/4013-II Dated 06.03.2023 | M/s. Serwell Cargo India Pvt Ltd, Mumbai | 10.04.2023 | 09.04.2033 | Shri Aman Imran B. AXEN (M) | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 30.09.2023

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Construction of Jetty for Indian Coast Guard at Vadinar. Estimate: Rs. 52,82,20,953/- | 52.82 Cr. | 49.32 Cr. | 6.62% below | No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. | M/s. Parsh Construction and Foundations Pvt. Ltd., Mumbai | 26/03/2021 | 18 months Extended Upto 30/06/2023 | Shri Rajesh Meghani, XEN (C) | Work Order issued vide No. OOT/C-WK/CG/(Jetty)/293 dated 26/03/2020. Extended vide O.O. No. OOT/C-WK/CG/7041 (Jetty)/190 dated 08/06/2022. Further Extended Upto 31/12/2023. |
| 2. | Hiring of 2 Nos. Steel Hull Mooring Launches with Crew and Mooring Gang at OOT, Vadinar for the period of Five (05) years. Estimate: Rs. 12,53,49,780/- | 12.53 Cr. | 9.12 Cr. | 27.21 % below | OOT/ME/WK/8017/484 dated 21/05/2021. | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | 14/12/2021 | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. OOT/ME/WK/8017/484 dated 21/05/2021. |
| 3. | Hiring of Service Boat for OOT, Vadinar for the period of 5 (five) years. Estimate: Rs.8,76,00,000/- | 8.76 Cr. | 9.59 Cr. | 9.49% above. | MR/WK/ 1397/66 dated 28/03/2022 | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | 05/05/2023 | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. MR/WK/1397/66 dated 28/03/2022. |
| 4. | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | No. OOT/ME/WK/3009-I/576 dated 26/12/2018. | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. |
| 5. | Strengthening of Road from colony to Jetty at OOT, Vadinar (Special Repairs) | 5.96 Cr. | 7.83 Cr. | 31.41% above | OOT-WK/NPS/4126/141 dated 26/05/2023 | M/s. A & T Infracon Pvt. Ltd. Bhuj. | 01/06/2023 | 4 months | Shri Rajesh Meghani, XEN (C) | Work Order issued vide No. OOT-WK/NPS/4126/141 dated 26/05/2023 Work in progress. Proposal for extension of time limit for three months i.e., 31/12/2023 is under process. |
| 6 | Engagement of Security Agency for providing watch and ward security supervisor and security guard at OOT, Vadinar. | 2.88 Cr. | 2.90 Cr. | 0.77% above | GEMC-511687725619008 dated 26.04.2023 | M/s. Kutch Security Services, Ahmedabad | 14.05.2023 | 04 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide:GEMC-511687725619008 dated 26.04.2023 |
| 7. | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 Cr. | 5.01 % above | OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/1666 dated 10/01/2020. |
| 8. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.44 Cr. | 2.83% above | OOT/ME-WK/RM/6004/239 dated 04/03/2021. | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. |
| 9. | Maitnenance of beacons, leading lights & channel marking bouys in DPA waters at OOT-Vadinar | 1.26 Cr. | 0.84 Cr. | 33.33% below | GEMC-5111687713333838 dated 28/07/2023 | M/s. Seaflesh Diving and Engineering Services | 04/08/2023 | 3 years | Shri Narendra Naik, ME (Gr. I) | Work Order issued vide GEMC-5111687713333838 dated 28/07/2023 |
| 10. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | OOT/ME-WK/RM/ 6018/329 dated 26/03/2021. | M/s. Pariya Electricals, Vadinar. | 01/04/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2021. |
| 11. | Running and Maintenance of Guest House and Staff Canteen at OOT, Vadinar Estimate Rs. 55,66,811/- | 0.56 Cr. | 0.53 Cr. | 5.61 % below | OOT/C-WK/RM4026/114 dated 29/04/2022 | M/s. Mahakal Enterprise, Jamnagar. | 01/05/2022 | 03 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide: OOT/C-WK/RM/4026/114 dated 29/04/2022 |
| 12. | Maintenance Contract of the Residential Building and Non Residential Building in Port Colony and Jetty at Vadinar. | 0.53 Cr. | 0.47 Cr. | 9.51% below | OOT/C-WK/ RM/4050-II/328 dated 29/07/2022 | M/s. G N Enterprise, Vadinar | 01/08/2022 | 02 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide: OOT/C-WK/RM/4050-II/328 Dt.29.07.2022 |
| 13 | Providing, Operating and Maintaining of (1) 01 Air Conditioned SUV Hyundai Creta or equivalent on 12 hours basis for COM, (2) 01 Air Conditioned 7 seater SUV Mahindra Bolero or equivalent on 24 hours basis for Multi-Purpose, (3) 01 Air Conditioned Sedan car Honda Amaze or equivalent on 12 hours basis for Officers and (4) 01 Air Conditioned Sedan Car Honda Amaze or equivalent on 24 hours basis for Pilots for a period of Three years at OOT, Vadinar through GeM. | 0.62 Cr. | 0.76 Cr. | 22.74% above | GEMC-511687761383207 Dt.18.05.2023 | M/s. Swarit E-Commerce Private Limited, Jamnagar | 02/06/2023 | 03 years | Shri M A Jadhav, Executive Engineer(Civil) (I/c). | Work Order Issued Vide:GEMC-511687725619008 Dt.26.04.2023 |
| 14 | Monthly Ambulance Service Type B Patient Transport Vehicle Single Stretcher Premium Van, Tata Winger Ambulance 3400 Force Traveller Ambulance, SML Isuzu Ambulance, 2000 km | 0.67 Cr. | 0.72 Cr. | 5.59% | GEMC-511687783908259 Dt.15.05.2023 | M/s. P.S.Funeral and Ambulance Services Pvt. Ltd., | 01-07-2023 | 3 years | Shri SuryaKant Kesari, XEN (E&M), | Work Order Issued Vide:GEMC-511687783908259 Dt.15.05.2023 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 30.09.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dredging in the Navigational Channel & Alongside Cargo Berths/Oil Jetties at Deendayal Port Trust for year 2020-23”. Location At Kandla | 393.80 | 310.04 | 21.27 % Below | LOA No. EG/WK/6116/182 dated 10.03.2021 | M/s Adani Ports and Special Economic Zone Ltd., Ahmedabad | 04/09/2021 | 36 months | Shri K. Srinivasa Rao, XEN (H & D) | Work in progress |
| 2 | Augmentation of liquid cargo handling capacity by revamping of existing pipeline network at Oil Jetty are, Deendayal Port Trust, Kandla | 130.49 | 126.49 | 3.05% below | PL/WK/8306 NIT-PQ/08 dated 31/08/2021 | M/s. Patel Corrrtech JV, Gandhidham | 30/09/2021 | 24 months | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 3 | Construction of Oil Jetty No.8 at Old Kandla. | 105.51 | 99.08 | 6.09% below | No.CN/WK/1571/work/243 dtd. 03/02/2021 | M/s Kargwal KM Joint Venture, Mumbai | 17/02/2021 | 18 months Extension granted upto Oct., 2023. | Shri B. Rajendra Prasad, SE (P) | Work in progress. Approval of revised estimated cost is awaited from Ministry. |
| 4 | Development of land from Junction of WG 1 & 2 to LC 236B at Kandla (Phase-1) | 81.99 | 67.67 | 27.69% below | CN1/WK/3014/Work/87 Dated 11.08.2023 | M/s. Shree Ram Infrastructure | 18.08.2023 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work order issued on 11.08.2023 |
| 5 | Development of backup area of oil Jetty No.8 to 11 (Phase-I) | 80.97 | 66.58 | 17.77% below | LOA No. EG/WK/9129/374 dated 19/10/2022. | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 21/12/2022 | 12 Months | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 6 | Development of area from Junction of West gate-I to west gate-II now renamed as "development of land west side of road in between junction of west gate 1&2 and railway line to 12th berth - Phase -I | 80.31 | 55.73 | 30.60% below | LOA No. EG/WK/8117/373 dated 17/10/2022 | M/s. Digvijay Construction Pvt. Ltd., Gandhinagar. | 07/11/2022 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 7 | Up - gradation of tuna road from two lane to four land (Phase-I) | 71.57 | 57.43 | 19.74% below | LOA No. EG/WK/8116/349 dated 03/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 10/11/2022 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 9 | Upgradation of Plots & S.W.D. in 66 Hectare area inside cargo jetty area | 65.80 | 59.55 | 9.51% below | HW/WK/2488/704 dated 11/01/2023 | M/s. Baldaniya Construction, Anjar. | 17/04/2023 | 16/10/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 10 | Development of four lane road common corridor from LC236B to 16th CB along railway line (Phase-I) | 55.28 | 38.47 | 30.41% below | CN1/WK/3012/Works | M/s. Hariom Earthmovers & Transport | 10.04.2023 | 18 Months | Shri Rajesh Meghani, XEN(C-I) | Work in progress |
| 11 | Construction of new godowns in place of existing godown no. 19 to 21 & 25 inside C. J. Area | 53.20 | 42.94 | 19.27% below | HW/WK/2580/705 dated 11/04/2023 | M/s. Patel Construction Co. Gandhidham. | 17/04/2023 | 16/10/2024 18 months | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 12 | Raising & upgrading the RCC Plots adjoining to track no. 10,11&12 inside Cargo Jetty Area | 53.13 | 43.27 | 18.56% below | HW/WK/2561/339 dated 07/07/2023 | M/s. Radhe Associated, Mehsana | 22/07/2023 | 21/07/2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 13 | Up gradation of roads & SWD outside cargo jetty area at New Kandla (Cement Concrete Pavement) | 40.35 | 24.65 | 38.88% | RW/WK/7821-I/362 dated 18/05/2023 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhidham. | 22/05/2023 | 21/08/2024 | Shri H.V. Gohel XEN(Road) | Work in progress |
| 14 | Upgradation of Plots, Roads & SWD in 40 hectare area inside Cargo Jetty Area. | 39.36 | 31.48 | 19.84% below | HW/WK/2456/579A dated 31/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd. | 22/10/2022 | 21/04/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 15 | Widening of Road from Junction of WG 1 & 2 to 12th Berth | 38.50 | 32.24 | 2.99% below | CN1/WK/3013/work/44 Dated 24.05.2023 | M/s. Dhanji K. Patel, Anjar. | 01.06.2023 | 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 16 | Construction of Dome shaped Storage Sheds inside C.J. Area - Phase-II | 30.63 | 24.24 | 20.86% | HW/WK/2567/335 dated 26/06/2023 | M/s. Patel Construction J/V M/s. Neelkanth Infrastructure P. Ltd. | 05/07/2023 | 04/01/2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 17 | Upgradation of Kutchha Plot C1 to C6 of 66 Hectares and SWD Network inside Cargo Jetty area. | 22.84 | 21.23 | 7.06% below | HW/WK/2545 202A dated 01/11/2022 | M/s. K.K. Sorathia J/v Hari Om Earthmovers and Transport | 15/11/2022 | 14/11/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 18 | Providing RCC Cable Trench for Electric Cables inside Cargo Jetty Area | 22.49 | NA | NA | NA | NA | NA | NA | Shri Mahesh Makhijani, XEN(H) | Preliminary bid schedule to be open on 30/10/2023 |
| 19 | Construction of Kendriya Vidyalaya Building at Port Colony Gopalpuri, Gandhidham | 21.64 | 20.24 | 6.00% below | TD/WK/7848/1059 dated 31/07/2023. | M/s. Dipesh Construction Co., Anjar | 04/08/2023 | 03/08/2024 | Shri H.K Bhaskar, XEN(TD) | Work Order issued. |
| 20 | Development of area adjacent to Tuna-GIM track by earthwork in embankment from 4.00 Km to take-off point for doubling of line to facilitate upcoming new projects at Tekra | 19.62 | 13.23 | 32.57% below | N.A. | M/s. Hariom Earthmovers & Transport, Adipur, Kachchh, 370205 | N.A. | N.A. | Shri Rajesh Meghani, XEN(C-I) | Price bid opened on 20/09/2023. TCM held on 29/09/2023 |
| 21 | Up-gradation and Strengthening of Existing Oil Jetty No 3 | 19.27 | 15.78 | 13.38% Below | CN/WK/608/FF&EMD/155 daed 22/06/2023 | M/s Patel Construction Co., Gandhidham | 01/07/2023 | 29/09/2024 8 months | Shri B. Rajendra Prasad, SE (P) | Work Order issued on 22/06/2023. |
| 22 | Construction of A, B, C and D type quarters at Gopalpuri | 18.94 | 13.78 | 27.16% below | TW/WK/7775/ 299 dtd. 07/06/2021 | M/s. VC Project & Infra Pvt. Ltd. | 05/06/2021 | 04/06/2023 | Shri Hemant Bhaskar XEN(TD) | Work Completed |
| 23 | Development of Parking yards for trucks/vehicles for pre-checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 | 14.59 | 12.87% below | HW/WK/2446/463 dated 26.06.2021 | M/s. Indian Construction Co., | 08/07/2021 | 07/07/2022 12 months work and 24 months maintenance Extension granted upto 07.03.2024. | Shri Mahesh Makhijani, XEN(H) | Work in progress. Extension proposal recommended upto 07.03.2024 approved by committee and forwarded to competent authority |
| 24 | Providing Road network & SWD to newly added custom bonded area (25 Ha area) | 14.50 | 13.49 | 7.18% below | N.A. | M/s. Neelkanth Infratech Pvt. Ltd., “NEELKANTH” BBZ S- 60, Zanda Chowk, Gandhidham Kutch 370201 | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Price bid opened on 22/09/2023. Under process |
| 25 | Retrofitting of the Bunder Basin Structures | 10.00 | 7.11 | 11.10% below | CN-1/WK/3008/Works (11.03.20220 | M/s. Chetan Construction Co., Mehsana | 21/03/2022 Extension granted upto Dec.,2023. | 15 months | Shri Rajesh Meghani XEN (C-I) | Work in progress. |
| 26 | Annual Maintenance contract for roads at Kandla for two years | 8.31 | 5.97 | 28.23% below | RW/WK/7810-I/239 dated 05/01/2023 | M/s. Dhanjibhai K. Patel, Anjar. | 05/01/2023 | 04/01/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 27 | Construction of E & D type quarters at Gopalpuri (Stage-1, D type ) | 8.23 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Technical Bid opened on 09.05.2023, tender scrutiny done ,price bid to be opened |
| 28 | Construction of Ring Road (Periphery road ) from NH-8A (From KASEZ) to Adipur | 8.20 | 6.33 | 22.83% below | TW/WK/7804-I/418 dated 04/11/2022 | M/s. Shree Ganesh Construction, Anjar | 10/11/2022 | 09/10/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 29 | Upgradation of internal road network from West gate I to QUAT LC 236 | 8.10 | 7.86 | 2.92% below | HW/WK/2555/806 dated 08/05/2023 | M/s. Dhanjibhai K. Patel, Anjar | 15/05/2023 | 14/12/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 30 | Resurfacing of road network inside cargo jetty area – Asphalt paving | 8.09 | 7.95 | 1.68% below | HW/WK/2523/616 dated 09/12/2022 | M/s. Shree Ganesh Construction, Anjar. | 24/12/2022 | 23/07/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress., Extension requested for 6 Months i.e. 24.07.2023 to 23.02.2024 |
| 31 | Extension of Custom Bounded area in Backup of 13th & 16th Berth | 8.02 | 5.28 | 34.24% below | LOA No. EG/WK/8115/264 dt. 22/06/2022 | M/s Mohit Enterprise, Rajkot | 08/08/2022 | 13 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 32 | Special Repairs of plot no 8 & 9 at bunder basin (5 hectares) | 7.99 | 7.17 | 10.33% below | HW/WK/2556 dated 30/05/2023. | M/s. Balaji Infra, Anjar. | 06/06/2023 | 05/06/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 33 | Construction of Storage Shed Over Existing Floor of Godown No. 3 & 4 inside C. J. Area | 7.81 | 6.05 | 11.10% below | HW/WK/2570/765 Dated 11.08.2023 | M/s. Neelkanth Infratech Pvt. Ltd. | 26.08.2023 | 27.07.2024 | Shri Mahesh Makhijani, XEN(H) | Work Order issued |
| 34 | Improving / Upgradation of Custom Fencing Wall of Cargo jetty and Bunder Area | 7.68 | 5.38 | 29.95 % below | HW/WK/2507-I/73 dated 15/02/2022 | M/s. Deosi Govindji Parmar (Lead Partner) J/v M/s. Shree Balaji Construction Co. | 28/02/2022 | 27/02/2023 12 months Extended upto 28/08/2023. | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 35 | Construction of garage and repair workshop building for mobile cargo handling equip-ments inside cargo jetty area | 7.61 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Preliminary bid opened on 08/06/2023. Tender under scrutiny |
| 36 | Strengthening to Residential & Non - Residential Building at New Port Colony, New Kandla | 7.56 | 4.99 | 34.05% below | RW/WK/7819-I/363 dated 18/05/2023 | M/s. Patel Construction Co., Gandhidham. | 22/05/2023 | 21/05/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 37 | Providing RCC and asphalt roads inside and outside of oil jetty area at Old Kandla | 7.12 | 4.79 | 32.76% Below | PL/WK/8490-I/189 dated 27/02/2023 | M/s. Mepabhai Mandan and Co., Adipur | 27/02/2023 | 11 months | Shri Rajendra Prasad B., S E (PL) | Work in progress. |
| 38 | S/R to quarters / building at FCI & KDLB Colony | 6.87 | 4.66 | 32.18% below | TW/WK/7788 -I/203 dated 27/06/2022 | M/s. Ankita Construction, Adipur | 01/07/2022 | 30/09/2023 | Shri Hemant K. Bhaskar XEN(TD) | Work in progress. |
| 39 | Removal of old abandoned RCC jetty structure in between Oil Jetty No. 2 & 3 at Old Kandla. | 6.75 | 6.46 | 6.39% below | PL/WK/8424-I/562 dated 15/06/2023 | M/s. Goyal Iron and Steel Traders. | June, 2023 | 05 Months | Shri Rajendra Prasad B., S E (PL) | Work in progress. |
| 40 | Appointment of Project Management Consultant (PMC) for Capital and Maintenance Dredging works of Deendayal Port Trust from firms/ consortiums Empanelled Consultants for dredging works (Class-A, Category-A) by Indian Port Association, New Delhi. | 6.36 | Rs. 5.33 | 15.32% Below | LOA No.EG/WK/6112/ 333 dated 15.11.2019 | M/s AECOM INDIA PVT LTD, GURGAON | 25/11/2019 | 36 months Extension grated upto November, 2023 48 months. | Shri K. Srinivasa Rao, XEN (H &D) | Work in progress |
| 41 | S/R to A.O. Building at Gandhidham. | 5.73 | 4.55 | 20.70% below | TW/WK/7797-I/1271 dated 21.09.2023 | M/s. Mepa bhai Mandan & Co. JV K.K. Sorathia, | 25.09.2023 | 24.08.2024 | Shri Hemant Kumar Bhaskar XEN(TD) | Work order issued w.e.f. 25.09.2023, work in progress |
| 42 | Appointment of technical, legal and financial experts from the firms of Transaction Advisor for "providing legal, technical and financial transactions for all ongoing and future proposals of DPA on PP / Captive Mode for the period of two years and further extendable for one year. | 5.46 | 3.61 | 33.88% below | EG/WK/4759/TA-IV dated 11/10/2022 | M/s. Infrastructure Development (Karnataka) Corporation Ltd (Ideck) | 14/10/2022 | 13/01/2024 2 years and further extendable for 1 year | Shri K.J. Todarmal, SE(D) | Work is in Progress. |
| 43 | Preparing and monitoring of Environmental Management Plan for DPA at Kandla. | 5.01 | 4.87 | 38.17 % below Estimated Cost | EG/WK/EMC/11023/2011/III/239 dated 15.02.2023 | M/s. GEMI Gujarat Environment management Institute. | 14.04.2023 | 36 months | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 44 | Improving & up-gradation of gardens and land scrapping at Gopalpuri (Renovation of Nehru Park and rain water harvesting by strengthening of SWD network near recharging pond at Gopalpuri | 4.79 | 2.40 | 49.81% below | TW/WK/7802-I/404 dtd.16.07.2021 | M/s. Rainbow Infrastructure, Rajkot | 03.07.2021 | 02.07.2022 (main work) 02/07.2024 (maintenance) | Shri Hemant Kumar Bhaskar XEN(TD) | Main Work completed. Maintenance work is in progress |
| 45 | Painting to Port structure and its allied structure at Oil Jetty area at Old Kandla (Phaze-I) (R/M of Oil Jetty at Old Kandla. | 4.18 | 4.59 | 17.52% Above | PL/WK/8475-I/789 Dated 31.08.2023 | M/S.ACER INFRA TRADE-GANDHIDHAM | 11.09.2023 | 10.09.2024 | Shri Rajendra Prasad SE(PL) | Work order issued on 31.08.2023 |
| 46 | Special Repair to existing storm water drain network inside Cargo Jetty area. | 8.33 | 5.91 | 28.21% Below | HW/WK/2568/762 dated 11.08.2023. | M/S.SHILPVIEW CONSTRUCTION-SANJAY.K.SORATHIA AND CO (JV) | 18.08.2023 | 17.11.2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 47 | Upgradation of Sewage treatment plant at Gopalpuri | 4.27 | 4.14 | 3.0363% below | TW/WK/7736-I/254 dated 21/07/2021 | M/s. Rajkamal Buildings, Infrastructure (P) Ltd., | 01/08/2022 | 31/01/2026 | Shri Hemant Kumar Bhaskar XEN(TD) | Main work completed. Maintenance work is in progress. Extension granted for two months. |
| 48 | Construction of Fire Brigade Station Opposite Jetty Office in CKD Yard inside Cargo Jetty Area | 3.48 | 2.94 | 15.62% below | HW/WK/2540/770 dated 24/04/2023 | M/s. Murlidhar Projects | 01/05/2023 | 31/07/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 49 | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 | 2.43 | 35.73% Below | W.O. No. HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd., Gurgaon - 122015 Haryana- India | 02/11/2021 | 36 months Extension grated upto Nov., 2023 | Shri K. Srinivasa Rao, XEN (H&D) | Work in progress |
| 50 | S/R to CISF complex building & Structure at New Kandla | 3.24 | 2.40 | 26.04% below | RW/WK/ 7817-I/307 dated 27/03/2023 | M/s. Acer Infra Trade, Gandhidham | 03/10/2023 | 02/10/2024 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work in progress. |
| 51 | Maintenance of PH & UG drainage at Gopalpuri Port Colony & KDLB Colony for the period of two years. | 3.15 | 1.56 | 50.51% below | TW/WK/7813-I/ dated 05/07/2022 | M/s. Patel Construction, Gandhidham. | 05/07/2022 | 04/07/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 52 | Annual Maintenance Contract for residential and non-residential building a Port Colony, Gopalpuri for two years. | 3.05 | 1.71 | 44.12% below | TW/WK/7806-I/126 dated 30/04/2022 | M/s. Dhanjibhai K. Patel, Anjar | 02/05/2022 | 01/05/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 53 | Construction of watch tower inside cargo jetty area | 3.04 | 2.84 | 6.22% below | HW/WK/2470/ 407 dated 09/04/2021 | M/s. Viyuha Infrabuild | 24/05/2021 | 8 months Extension granted upto 22/06/2022 | Shri Mahesh Makhijani, XEN(H) | Work in progress. Extension granted for 6 months from the date of handing over the site. |
| 54 | Special repairs to RFID cum data centre building adjoining to Seva Sadan III at New Kandla | 3.01 | 2.49 | 17.22% below | HW/WK/2582/ 284 dated 31/01/2023 | M/s. Vihat Construction, Gandhidham. | 03/02/2023 | 02/08/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress. Extension upto 02.11.2023 under approval |
| 55 | Deployment of equipment for cleaning of all toilet blocks inside Port area and to maintain high standard of hygienic and to avoid pollution. | 2.99 | 2.23 | 25.40% below | HW/WK/2551/202 dated 31/10/2022 | M/s. Shree Ganesh Construction, Anjar - Kutch | 01/11/2022 | 30/10/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 56 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2022-24 | 2.78 | 1.68 | 39.35% below | TW/WK/7825-I/670 dated 24/03/2023 | M/s. Acer Infra Trade, Gandhidham | 27/03/2023 | 26/03/2025 24 months | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 57 | R/m of Maintenance Jetty - Repairs and Maintenance of Pontoons and Walkways of SNA Jetty and Flotilla Jetty | 2.77 | 3.37 | 10.51% above | HW/WK/2494/462 dated 25.06.2021 | M/s Patel Construction. Gandhidham | 08/07/2021 | 07/07/2023 24 months | Shri Mahesh Makhijani, XEN(H) | Work Completed |
| 58 | Maintenance Contract for Godown inside Cargo Jetty area for two years 2022-23 & 2023-24) | 2.70 | 2.08 | 23.77% Below | HW/WK/2531/324 dated 05.06.2023 | M/s. Sanjay k. Sorathiya & Co., Gandhidham. | 05/06/2023 | 04/06/2026 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 59 | Annual Maintenance Contract for AO Building at Gandhidham for 02 years | 2.67 | 1.95 | 27.00% below | TW/WK/7820/654 dated 13/03/2023 | M/s. Acer Infra Trade, Gandhidham | 15/03/2023 | 14/03/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 60 | Special Repairs to ATM office, Marine Bhavan, Immigration Centre Inside Cargo Jetty Area | 2.63 | 2.12 | 18.52% below | HW/WK/2536/297 dated 21/04/2023 | M/s. Murlidhar Projects | 28/04/2023 | 27/04/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 61 | Two years contract for supply and maintenance of railway tracks inside and outside cargo jetty area (for 02 years | 2.59 | 2.03 | 21.40 % below | HW/WK/2487/359 dated 20/02/2021 | M/s. Laxyo Entergy Ltd. | 06/03/2021 | 05/03/2023 24 months Extn. granted upto 31/07/2023 | Shri Mahesh Makhijani, XEN(H) | Work completed |
| 62 | Resurfacing of road from KK road junction to Mithirohar GIDC at Kandla | 2.52 | 2.56 | 1.68% above | RW/WK/ 7804-I/307 dated 16/03/2023 | M/s. Ravji Manji Sorathia & Co., Adipur. | 20/03/2021 | 19/12/2023 | Shri Hemant Bhaskar, XEN(R) | Work in progress. |
| 63 | Two Years Contract for supply and maintenance of railway tracks inside and outside cargo jetty area (For Years 2023-25) | 2.23 | 1.77 | 21.06% below | HW/WK/2584/772 Dated 31.08.2023 | M/s. Dharti Construction | 07.09.2023 | 06.09.2025 | Shri Mahesh Makhijani, XEN(H) | Work order issued |
| 64 | S/R to AO Building at Gandhidham - Renovation of toilet blocks, recreation room, old board room. | 2.20 | 1.32 | 40.13% below | TW/WK/7795-I/ 111 dt. 21/04/2022 | M/s. Ankita Construction, Adipur | 25/04/2022 | 24/04/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Main work completed. Maintenance work is in progress. |
| 65 | House Keeping & Cleaning of Building of Office building and surrounding outside Cargo Jetty Area for the year 2021-23. | 1.97 | 1.07 | 45.36 % below | HW/WK/2538/68 dated 07/02/2022 | M/s. Rajput Infrastructure Co. , Gandhidham | 22/02/2022 | 21/02/2024 24 months | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 66 | Annual maintenance contract for buildings, walkways, trestles, firefighting pipelines, fenders and garden isnide & outside oil jetty area at Old Kandla | 1.67 | Part A - 1.35 and Part B - 2.82 | 21.0847% below | PL/WK/8486-I/596-A dated 01.07.2023 | M/s. Vihat Construction Co. | 08.07.2023 | 07.07.2025 | Shri Rajendra Prasad B., SE (PL) | Work in progress |
| 67 | Two years maintenance contract for office buildings outside Port area (Civil work) | 1.63 | -- | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Preliminary bid opened on 07/06/2023. Tender under scrutiny |
| 68 | S/R to emergency response centre at Old Kandla. | 1.62 | 1.14 | 29.63% below | EG/WK/6144/133 | M/s. Vihat Construction Co. | - | - | Shri Rajendra Prasad B.,SE (PL) | LOA to be issued. |
| 69 | Annual maintenance contract for firefighting pipeline and water supply line and Misc. civil works for overhead and underground water tank inside and outside cargo jetty at Kandla. | 1.62 | 1.08 | 33.30% below | EG/WK/6146/135 17/07/2021 | M/S.Sanjay K. Sorthiya Co. | - | - | Shri Rajendra Prasad B., SE (PL) | LOA issued. |
| 70 | Providing Labour amenities centre at various locations inside Cargo Jetty Area. | 1.53 | 1.18 | 22.85 % below | HW/WK/2461/60 dated 25/01/2022 | M/s. Rajput Infrastructure Co. | 08/02/2022 | 07/02/2023 12 Months (Extension granted upto 07/08/2023) | Shri Mahesh Makhijani, XEN(H) | Work in progress., 2 Months extension requested i.e. upto 07.10.2023 |
| 71 | Providing RCC drinking water tank. | 1.52 | -- | -- | -- | -- | -- | -- | Shri Rajendra Prasad B., SE (PL) | Tender processed for discharge |
| 72 | Two years’ maintenance contract for railway tract leading to Tuna from0 to 11 Km KPLT line (Take off at 2.573 Km at Gandhidham Yard to 13.54 Km) including LC-1, LC-2 | 1.46 | NA | NA | NA | NA | NA | NA | Shri Mahesh Makhijani, XEN(H) | Proposal for discharge due to abnormally low rated , will be reinvited |
| 72 | Maintenance contract for quay and transit area inside Cargo Jetty Area for two years. | 1.46 | NA | NA | NA | NA | NA | NA | Shri Mahesh Makhijani, XEN(H) | Preliminary bid schedule to be open on 04/10/2023 |
| 74 | AMC for White Washing, Distempering, Painting to Res. & Non-resi. Bldg. at G’puri, KDLB, G’dham & Adipur for the year 2022-23 | 1.45 | 0.74 | 48.60% below | - | M/s. Paras Enterpricse. | - | - | Shri Hemant Kumar Bhaskar, XEN(TD) | Price bids opened on 13/03/2023. Submitted the proposal to discharge tender. |
| 75 | Appointment of Independent Engineer for the work of “Development of Marine Liquid Terminal Facilities consisting of SPM and Two Product Jetties in KPT waters at OOT, Vadinar for Handling Crude and Petroleum Products on Captive Use Basis”. | 1.44 | 1.18232 | 17.89% below | Work Order No.EG/WK/4823(IE)/109 dated 22/10/2019 | M/s RINA Services s.p.A,Mumbai | 01/11/2019 | 42 months | Shri K.J. Todarmal, SE(D) | As concessionaire has not started construction activity, the work order issued to M/s. RINA has been kept in abeyance. |
| 76 | Third Party Inspection and Quality Inspection and Quality Assurance for the works costing more than Rs. 1.00 Cr. of Civil Engineering Department of Deendayal Port Authority. | 1.358 | 1.17 | 14.05% below | Work Order No.EG/WK/5212/53 dtd.16/10/2021 | M/s. VCS Quality Services pvt. Ltd., Mumbai | 25/10/2021 | 24/10/2023 | Shri Sunil Soren, XEN(D) | Work in Progress. |
| 77 | Maintenance Contract for Non-residential buildings inside Harbour area (Civil Work) | 1.31 | 0.95 | 27.55% below | HW/WK/2526/122 dated 20/04/2022 | M/s. Mepabhai Mandan & Co., Adipur | 05/05/2022 | 04/05/2024 24 months | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 78 | Strengthening of existing environmental management cell at DPT Appointment of environ-ment experts for two years and further extendable for one year | 1.232 | 1.20 | 2.60% below | EG/WK/ 4783/V/131 dtd.05/02/21 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15/02/2021 | 14/02/2023 24 months Extension granted upto 15/02/2024 | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 79 | Maintenance contract for cleaning&house keeping work of DPA hospital & isolation ward at gopalpuri & kandla & Adipur dis-pensary for the period of 2 years | 1.22 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Technical Bid opened & under process |
| 80 | Two years maintenance contract for Railway track leading to Tuna from 0 to 11 Km KPT Line (Take off Point at 2.573 Km at GIM Yard to 13.54 Km including LC-1, LC-2) | 1.19 | 0.908 | 23.77% below | HW/WK/2515/432 DATED 31/05/2021 | M/s Patel Construction. Gandhidham | 14/06/2021 | 13/06/2023 24 Months Extension grated upto 30/11/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 81 | Maintenance contract for sports complex for the period of two years at Gopalpuri. | 1.19 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar, XEN(TD) | Proposal sent for L1 Acceptance |
| 82 | Dismantling of existing godown no.19 to 23 inside cargo jetty area | Part A 0.26 and PART ‘B’ 0.93 (Credit item) | -- | -- | -- | -- | -- | -- | Shri Mahesh Makhijani, XEN(H) | Tender scrutiny under process. |
| 83 | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years | 1.13 | 0.82 | 27.27% below | PL/WK/8461-I/25 dated 09/02/2022 | M/s. Sanjay K Sorathiya & Co. | 09/02/2022 | 24 Months | Shri Rajendra Prasad B., SE (PL) | Work in Progress |
| 84 | Maintenance contract for quay and transit area inside cargo jetty area for two years | 1.04 | 0.87 | 16.77% | HW/WK/2617/12 dated 24/09/2021 | M/s. Sanjay K Sorathiya & Co. | 10/10/2021 | 09/10/2023 24 Months | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 85 | Maintenance Contract for Tree Plantation near offices, other buildings, along roads, islands, gates, etc. inside/outside cargo jetty area for two years | 0.97 | 0.62 | 35.82% below | HW/WK/ 2582/284 dated 17/03/2023 | M/s. Vihat Construction, Gandhidham | 25/03/2023 | 24/03/2025 24 months. | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 86 | Maintenance Contract for Residential & Non - Residential Building at New Port Colony at New Kandla for two years. | 0.97 | 0.62 | 36.20% below | RW/WK/7816-I/242 dtd. 17/10/2022 | M/s. Murlidhar Projects | 17/10/2022 | 16/10/2024 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work in progress. |
| 87 | Two Years Contract for House Keeping & Cleaning of Gate office buildings and Non-residential buildings inside cargo jetty area | 0.96 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Tender proposed for discharged and reinvitation |
| 88 | Maintenance Contract for sanitation of New Port Colony, New Kandla for period of 2 years | 0.95 | 0.56 | 41.00% below | RW/WK/7820-I/375 dated 02/06/2023 | M/s. Acer Infra Trade, Gandhidham | 05/06/2023 | 04/06/2025 | Shri Hemant Kumar Bhaskar, XEN(Road) | Work in progress. |
| 89 | Providing firefighting pipeline at 34 hectares inside cargo jetty area (A) Appointment of Technical Advisor for the work of Upgradation of firefighting system & associated facilities inside cargo jetty area. DPA | 0.86 | 0.80 | 6.39% below | PL/WK/8476-I/21 dated 21.12.2022 | M/s. S.R. Engineers | 26.12.2022 | 18 months | Shri Rajendra Prasad B., SE (PL) | Work in progress |
| 90 | Two years contract for cleaning of storm water drain inside cargo jetty area | 0.78 | 0.49 | 37.18% below | HW/WK/2562/342 dated18/07/2023 | M/s. Narayan Construction Co. | 25/07/2023 | 24/07/2025 | Shri Mahesh Makhijani, XEN(H) | Work order issued. |
| 91 | White washing, painting & distempering to residential and non-residential buildings & CISF complex at New Port Colony, New Kandla (for 2 years) | 0.67 | 0.38 | 43.20% | RW/WK/7790-I/ dated 05/2022 | M/s. Rajput Infrastructure Co., Gandhidham. | 01/06/2022 | 31/05/2024 | Shri Hemant Kumar Bhaskar XEN(Road), | Work in progress. |
| 92 | Housekeeping & cleaning of office building inside cargo jetty area (for 2 years) HD-10/19 | 0.54 | 0.4128 | 23.43% below | HW/WK/2422-I/367 dated 20/02/2021 | M/s. Shree Ganesh Construction, Anjar | 06/03/2021 | 05/03/2023 Extension granted upto 02/07/2023 | Shri Mahesh Makhijani, XEN(H) | Work in progress, extension requested from 03.07.2023 to 02.01.2024 |
| 93 | Housekeeping of liaison office cum rest house for DPA at Ahmedabad port for 3 years | 0.53 | 0.53 | - | TW/WK/7816-I/9167 Dated 24.08.2023 | M/S N. Kumar Associates International Mumbai | 01.09.2023 | 31.08.2026 | Shri Hemant Kumar Bhaskar XEN(Road) | Work order issued |
| 94 | Maintenance Contract of 1.5 MLS Sewage treatment plant at New Port Colony, New Kandla for 2 years | 0.52 | 0.29 | 45.13% below | RW/WK | M/s. Gadhvi Construction Co., | 21/06/2022 | 20/06/2024 | Shri Manoj Gohel XEN(Road), | Work in progress. |

MEGA INFRASTRUCTURE PROJECTS

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 95 | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT basis under PPP mode | 4243.64 | NA | NA | Tender No. CE/13 | M/S Hindustan Infralog Private Limited | LOA Awarded Dated 28/01/2023 | 36 months from the date of award of concession | Shri Sunil Soren XEN (Design) | RFP opened on 27.01.2023, M/S Hindustan Infralog Private Limited was declared as successful Bidder. Subsequently, LOA was issued on 28.01.2023 and the same was acknowledged and accepted by M/s. Hindustan Infralog Private Limited on 31.01.2023. From time to time, on the Request of M/s. Hindustan Infralog Private Limited, the time for signing the Concession Agreement was extended. On 20.06.2023, on the request of M/s. Hindustan Infralog Private Limited, the time period for execution of Concession Agreement between the Authority and SPV was signed on 25.08.2023 and the same was intimated to M/s. Hindustan Infralog Private Limited. |
| 96 | Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis | 448.00 | NA | NA | Concession Agreement executed between DPA (erstwhile KPT) and M/s. Coviva Energy Terminals Ltd. (erstwhile VLTL) on 16/04/2015 | Name of the Concessionaire : M/s. Coviva Energy Terminals Ltd. Project is to be implemented by CETL | Award of Concession granted on 16/08/2019. However, CETL not initiated Project implementa-tion | Original: 36 months from date of award of concession i.e., 16/08/2019 to 15/08/2022 Revised : 42 months from date of award of concession (due to six months extension granted by DPA due to COVID 19 Force Majeure) | Shri Sunil Soren XEN (Design) | PRESENT STATUS: The construction period (revised) 42 months have elapsed on 15/02/2023 but, CETL asked extension of time limit for completion of construction utp 31/08/2026 by citing main reason of delay in expansion of Nayara Energy Refinery. Action taken by DPA: As CETL has not started construction activity on project site, the Board of DPA in its meeting held on 10/01/2022 had resolved to approve to levy LD on CETL as per Article 6.9 of the CA. The total LD levied on CETL (for the period of delay 16/02/2021 to 31/08/2023) is Rs. 20,76,48,000/. However, the payment of LD is still awaited CETL. M/s. Nayara Energy Ltd. (parent company of CETL) vide communication dated 08/04/2022 had agreed to pay LD provided DPA grants extension of time limit upto 31/08/2026. Looking to the importance of capacity addition project (24.5 MMTPA) and also considering M/s. NEL’s above submission dated 08/04/2022, DPA requested MoPS&W, GoI, vide letter dated 29/12//2022 to give further advice / direction in the matter regarding extension sought by CETL upto August, 2026. Subsequently, MoPS&W asked certain clarification from DPA which were complied. However, advice / direction from MoPS&W, GoI is awaited. An Agenda Item is also submitted to DPA Board for the meeting scheduled to be held on 13/10/2023 for deliberation. |

Ro-Ro / Ro-Pax Ferry Service Cell

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 97 | Maintenance Dredging at Underneath/Periphery of Landing Pontoon of Ro-Pax facility at Dahej Terminal for 12 Months. | 2.43 | 2.22 | 8.5926% (Below) | CN/WK/1600/DAHEJ/17-A DATED – 11/05/2021 | M/s. Divine Shipping Services, Ahmedabad | 12-05-2021 | 12 Months Extension granted upto 10/05/2023 | Shri Rajendra Prasad Bethi, SE(P) | Work Completed |
| 98 | Construction of RORO/ROPAX facility at Muldwarka, Gujarat. | 84.74 | 76.69 | 9.5% (Below) | LOA No.CN/WK/1600-Const/Muldwarka/7 dated 14/01/2022 | M/s. BMS Projects – Marymatha JV | 10-05-2022 | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | Interim W/O for fabrication of Pontoon and Linkspan at Hazira, awarded on 10/05/2022. Final W/O shall be awarded after receipt of EC & CRZ. |
| 99 | Dredging in Approach channel Turning Circle, Berth pockets and surroundings of landing pontoon etc at Ghogha Ro-Ro Terminal Gujarat. | 28.63 | 45.81 | 60% (Above) | CN/WK/1600- GHOGHA (7BCD)/51 Dated – 25/04/2022 | M/s. Rock & Reef Dredging Pvt Ltd., Navi Mumbai | 25-04-2022 | 4 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. 4 months extension from 23.08.2022 to 15.12.2022 and 2nd extension from 16/12/2022 to 31/03/2023 and 3rd extension upto 30/06/2023 has been granted by competent authority. 4th extension from 01/07/2023 to 29/12/2023 is under process. |
| 100 | Monitoring for smooth functioning of Ro-Ro Facility services located at Hazira, Dahej and Ghogha. | 1.95 | 1.67 | 14.36% (Below) | CN/WK/1600/ 38 dated 29/03/2022 | M/s. Dhanjibhai K Patel | 01-04-2022 | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in progress. |
| 101 | Construction of Ro – Ro / Ro-Pax On – Shore facility at Muldwarka – Gujarat, EPC mode. | 30.81 | 33.88 | 9.97% (Above) | CN/WK/1600/Onshore Muldwarka/137 dated 15.07.2022 | M/s. MMC Projects (India) Pvt Ltd., Gandhidham | 25-07-2022 | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | Work Order issued. Work is stopped due to local people's interference. EC is awaited. |
| 102 | Annual Maintenance contract of Linkspan Pontoon and Terminal facilities of Dahej & Ghogha Ro-Pax ferry terminal | 3.90 | 3.90 | - | Supplementary Work Order No. CN/WK/1600/55 Dated – 09/07/2021 | M/s. Vishwakarma Mechanical works, Porbandar | 08-03-2019 | 07-03-2021 1st extension 06.07.2023 | Shri Rajendra Prasad Bethi, SE(P) | Work Completed. Proposal for extension of work from 07/09/2021 to 06/07/2023 (22 months) and Anticipated variation statement No.2 with extra items for net excess of Rs.3,94,36,435.00 i.e. 101.11% excess on the tendered cost of Rs.390.04 lakhs approved by the Board in its meeting on 03/02/2023. Further extension request up to 20.09.2023 which is under consideration |
| 103 | Annual Maintenance Contract of Navigational Channel Marking System (Buoys) at Ghogha Ro-Pax | 0.86 | 0.94 | 8.93% above. | CN/WK/1613/ ROPAX/ GHOGHA-III/PQ /124 dated 17/04/2023 | M/s. Somnath Metal Cast, Bhavnagar. | 17/04/2023 | 16/04/2025 | Shri Rajendra Prasad Bethi, SE(P) | Work Order issued. Work in progress. |
| 104 | Annual Maintenance Contract of Navigation Channel Marking System (Buoys) at Dahej & Ghogha – Ro Pax Online Tender ID 383191 | 0.48 | 0.48 |  | Supplementary Work Order No. CN/WK/1600/49 Dated – 29/06/2021 | M/s. Sai Sagar Dredging & Marine Services Pvt. Ltd., Bharuch | 03-03-2020 | 02-03-2021 Extension granted upto 01/07/2023 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Anticipation Variation Statement No.2 for net excess of Rs.75,69,087/- i.e. 156.26% excess on the tendered cost of Rs.48,43,830/- approved by the Board in its meeting on 03/02/2023. Further time extension of 6 Months is seeked upto 01.01.2024 |
| 105 | Annual Maintenance Contract for Link Spans, Pontoons and Terminal facilities at Dahej | 2.95 | 3.3 | 11.86% above | CN/WK/1612/ROPAX/DAHEJ/207 Dated 13.09.2023 | M/S. VISHWAKARMA MECHANICAL WORKS-PORBANDAR | 21.09.2023 | 20.09.2025 | Shri Rajendra Prasad Bethi, SE(P) | Work order issued |
| 106 | Annual Maintenance contract for Navigational Channel marking system (Buoys) at Dahej - Ro- Pax | 3.69 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | Tender to be reinvited ,with modifications in estimates |
| 107 | Maintenance Dredging at Periphery of landing pontoon of Ro-Pax facility at Dahej Terminal for 12 months | 2.22 | 1.99 | 9.99% below | CN/WK/1600/DHEJ-2022-23/PONT Main Dredg./18 dated 04/05/2023 | M/s. BSP Hydro Dredging Works Pvt. Ltd., AP. | - | 12 months | Shri Rajendra Prasad Bethi, SE(P) | Work Order issued. |
| 108 | Engagement of Security agency for providing watch & ward security supervisor & security guard without arms for Dahej terminal of DPA for 2 years | 0.81 | 0.7 | 13.41% below | CN/WK/1600/Security/132 dt. 04.05.2023 | M/s. Shakti Protection Force Pvt. Ltd. | 08/05/2023 | 24 months | Shri Rajendra Prasad Bethi, SE(P) | W.O. issued on 04.05.2023. Anticipated variation statement for Net excess of Rs. 10,69,566.80 i.e. 15.18% has been in-principle approved and submitted to Variation committee. |
| 109 | Annual maintenance contract for link spans, pontoons and terminal facilities at Ghogha. | 2.94 | 3.19 | 8.57% above | CN/WK/1611/ROPAX/DAHEJ/207 Dated 16.08.2023 | M/S. VISHWAKARMA MECHANICAL WORKS-PORBANDAR | 23.08.2023 | 22.08.2025 | Shri Rajesh Meghani, XEN(C-I) | Work order issued |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No. | Name of work & location | Reserve price Per sq. mtr./year | Premium received over nd above reserve price during e-auction (per sq. mtr./per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 110 | E-tender cum E-auction for allotment of 04 Nos of plots (with structure) situated at old/new Kandla for the purpose of liquid storage tanks (products permitted in the earlier Lease Deed/ Allotment Letter) on 30 years lease on as is where is basis(Phase-II). | Rs. 1060.56 | …. | …. | …. | …. | Shri S.K. Rao. SE (KL) | NIT published on 27/04/2022,pre-bid meeting held on 04/05/2022.Date of opening of tender extended up to 13.07.2023. Bid submission date extended upto 27/10/2023. |
| 111 | e-tender for appointment of land valuer for valuation of land rates in the port etate of kandla from village veera to village jungi which includes kandla, tuna, kharirohar and bhachau excluding salt lands & sipc land for the year 2024-2028 | …… | …… | ….. | …… | ….. | Shri Sunil Soren XEN(KL) | NIT published on 18.05.2023, date od downloading tender 13.06.2023, last date of online submission 13.06.2023, bid open & preliminary bid under evaluation |
| 112 | e-tender for empanelment of valuer for carrying out the valuation of assets lying in the plots allotted to respective parties. | …… | …… | ….. | …… | ….. | Shri Sunil Soren XEN(KL) | NIT published on 18.05.2023, date od downloading tender 30.05.2023, last date of online submission 30.06.2023, pre-bid meeting held on 09.06.203, online opening of Technical bid opened on 10.07.2023. |
| 113 | e-tender cum e-auction for the allotment of 03 nos. of plots for the purpose of edible oil storage tanks (products permitted in the earlier lease deed/allotment letter) on 30 years lease on as is where is basis. | …… | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 13.07.2023, date of downloading tender 13.07.2023, last date of online submission 28.08.2023, pre-bid meeting held on 24.07.2023. Bid submission date extended upto 27/10/2023. |
| 114 | e-tender cum e-auction for the allotment of 03 nos. of plots (with structure) situated at old kandla for the purpose of liquid storage tanks (products permitted in the earlier lease deed/allotment letter) on 30 years lease on as is where is basis. | …… | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 14.07.2023, date of downloading tender 14.07.2023, last date of online submission 28.08.2023, pre-bid meeting held on 24.07.2023. The bids opened on 05/10/2023. |
| 115 | e-tender cum e-auction for the allotment of 05 nos. of plots (with structure) situated at old kandla for the purpose of liquid storage tanks (products permitted in the earlier lease deed/allotment letter) on 30 years lease on as is where is basis. | …… | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 13.07.2023, date of downloading tender 13.07.2023, last date of online submission 28.08.2023, pre-bid meeting held on 24.07.2023. Bid submission date extended upto 27/10/2023. |
| 116 | e-tender cum e-auction for the allotment of 02 nos. of plots for the purpose of edible oil storage tanks on 30 years lease on as is where is basis. | …… | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 14.07.2023, date of downloading tender 14.07.2023, last date of online submission 28.08.2023, pre-bid meeting held on 24.07.2023. The bids opened on 05/10/2023. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

4 .	MARINE DEPARTMENT							                                                                                      AS ON 30.09.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Design, Construction and supply of 01 No. Speed Boat (Patrolling Boat) for waterfront security of Deendayal Port. | 948.11 Cr. | -- | -- | -- | -- | -- | 5 years | Capt. Pradeep Mohanty, Deputy Conservator | Technical Bid opened on 10/08/2023. |
| 2. | Hiring or 2 Nos. of Tugs on Charter / Rate per year for the period of 10 years, extendable for one year. | 214.87Cr. | 209.87 Cr. | 0.86% below | Executed on 15/03/2023 | M/s. Ocean Sparkle Ltd. Hyderabad | Tug 1: 9/5/23 Tug 2: 16/5/23 | 10 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 19/04/2022 |
| 3. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | - | Executed on 09/03/2022 | M/s. Electronics Corporation of India Ltd., Hyderabad | 25/11/2021 | 24 months for supply, installation and commissioning AMC 10 years after installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Supply & Installation work completed on 25/11/2020. AMC work in progress. |
| 4 | Hiring or 2 Nos. of Steel Hull Mooring Launches and Moorings Gangs at Deendayal Port, Kandla for a period of 5 years. | 14.60 Cr. | 10.76 Cr. | 26.24% below | Executed on 27/11/2022 | M/s. Pacific Shipping Services, Mumbai | Yet not commenced | 5 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 28/09/2022 Work Order issued on 02/11/2022 |
| 5 | Hiring of 04 Nos. of 50/60 Ton Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below. 20.08% below | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator | W.O. has been issued on 03/10/2016 & 22/09/2016. |
| 6 | Hiring of 165 Nos. of Manpower in the cadre at Firefighters for Port services at DPA, Kandla on Contractual basis for a period of 3 years. | 6.58 Cr. | 6.38 Cr. | 12.93% below | Executed on 27/04/2023 | M/s. Krishna Industrial Security & Fire Services Pacific Shipping Services , Anand Gujarat. | 14/04/2023 | 3 years | Capt. Pradeep Mohanty,, Deputy Conservator | LOA issued on 13/02/2023. |
| 7 | Appointment of Agency for providing manning services /VTS operations at Kandla & Vadinar Port monitoring stations - VTS for the period of 3 years. | 5.41 Cr. | 5.93 Cr. | 9.69% above | Executed on 19/04/2023. | M/s. Admiral Marine Services P, Ltd., Chennai | 01/04/2023 | 3 years | Capt. Pradeep Mohanty,, Deputy Conservator | LOA issued on 20/02/2023 Work Order issued on 20/03/2023. |
| 8 | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | 26/04/2021 | 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 13/10/2020. Work Order issued on 05/01/2021. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 30.09.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of brand new make of 64 Nos. of vehicles Model-2023) EV/Diesel / Petrol, on monthly hired basis and hiring of vehicles not earlier than 2022 on äs and when required basis "for a period of 3 years. | 19.33 Cr. | 16.02 Cr. | 16.97% below | Executed. Work Order No. GA/GN/5400/2023-25/815 dated 10/03/2023 | M/s. Rishabh Enterprises, Gandhidham. | 01/04/2023 | 31/03/2026 | Shri Deepak Rane, Dy. Secretary | Work in progress. |
| 2. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |
| 3. | Engagement of Security Agency for providing Watch & Ward Security Supervisors & Security Guards without arms for various Departments of DPA for the period of 02 years. | 5.92 Cr. | 5.13 Cr. | 13.34% blow | Executed Work Order No. ES/SR/2443/ Security/1 dated 26.03.2021 ES/SR/2443/ Security/2 dated 26.03.2021 ES/SR/2443/ Security/3 dated 26.03.2021 | M/s. Shakti Secuirty, Surat. M/s. Panther Surveillance, Ahmedabad. M/s. Rajput Security Services, Ahmedabad. | 26/03/2021 | 25/03/2023 Extended upto 30/09/2023 | Shri Omprakash Dadlani, TP & PRO & Nodal Officer, (Security) | Work in progress. Proposal extension for further period of 6 months i.e. 31/03/2024 is submitted to the competent authority for approval. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6.	MEDICAL DEPARTMENT										                                            AS ON 30.09.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |
| 2 | Outsourcing of Vadinar Hospital for treatment of employees of DPA, CISF Personnel and CISF employees engaged by DPA and IOCL and their family members as well as other persons as decided by DPA at Vadinar | 2.88 Cr. | 2.07 Cr. | 26.80% below | MH/SP/85/ 2020-21 | M/s. Shree Samarpan Wellness Pvt. Ltd., Rajkot | 16/05/2022 | 3 years. | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	TRAFFIC DEPARTMENT											                	AS ON 30.09.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Engagement of manpower service provider for providing various categories of outsourced staff to carry out railway operation inside Cargo Jetty area for a period of 3 years. | 3.88 Cr. | 2.87 Cr. | 26.00% below | Executed on dated 26/07/2021 | M/s. Dhanjibhai K. Patel, Anjar. | 01/05/2021 | 30/04/2024 | Shri N.M. Parmar, ATM (Railway), | Work in progress. |
| 2. | Outsourcing of Establishing and operating of occupational health services at Deendayal Port Authority, New Kandla for the period for 5 years. | 3.54 Cr. | 2.98 Cr. | 16.59% below | Executed on dated 15/12/2021 | M/s. Accord Multispecialty Hospital, Bhuj | 15/05/2021 | 14/12/2026 | Shri Bavesh Mandvi, Safety Officer | Work in progress. |
| 3. | Engagement of Consultant to authenticate / validate the reports submitted by the PPP Operator for three (3) years | 2.56 Cr. | 2.77 Cr. | 9.99% Above | Executed on dated 10/10/2022 | M/s. Aarvee Associates Architects Engineering & Consultant Pvt. Ltd., Hyderabad | 17/10/2022 | 16/10/2025 | Shri Thushar Patel, Asstt. Traffic Manager (PPP) | Work in progress. |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	FINANCE DEPARTMENT										                                     AS ON 30.09.2023

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |  |  |  |  |  |  |  |  |  |  |

*****