SAP PS USER MANUAL

1) Login to SAP with your USER ID and Password

SAP Easy Access Screen will display :

Enter CJ20N (in TCode Box) – to go to Project Builder

2) To Create New Project

Click on Icon Create

3) Select on Project 4) Enter Project Definition 5) Enter Project Definition : P-DP-C-C-21-01 Click on Find Search for New Open Number of Project System shows you the Open Number : P-DP-C-C-21-45….. Click on Continue [ _/ ] 6) Enter Short Description (allows only 40 characteristics) : SIC 14 MW Wind Power Project Click on Intermediate Save Tab Note : Intermediate Save - will save instantly and active in Project Builder Save – will save and comes out of the Project Builder 7) Select Project Profile from the drop down : New Capital Project Profile-DPT Click on Intermediate Save Tab 8) Enter Start Date and Finish Date Enter Profit Center of DPT : 1201 Click on Save 9) Project is being created : P-DP-C-C-21-45 10) Create Level 1 WBS Element Right Click on the Project Number Select Create Click on WBS Element 11) Enter WBS Element Code : P-DP-C-C-21-45 Note: Should be similar as Project Code (it’s a basic rule in SAP) Enter Short Description : SIC 14 MW Wind Power Project Level 1 WBS Under Operative Indicators - Check [_/] Planning Elements 12) Create Level 2 WBS Element Right Click on the Level 1 WBS Element Select Create Click on WBS Element 13) Level 2 WBS Element is assigned by System Automatically : P-DP-C-C-21-45-01 Enter Short Text : Construction, Erection & Commissioning 14) Create Network : Right Click on Level 1 WBS Element Select Create Click on Network 15) Enter Short Text : SIC 14 MW WP Network Click on Intermediate Save 16) Enter Scheduling Type from the drop down Menu 17) Click on Save Network Created : 401000955 Click on Exit 18) Enter ZPS_MEASURE (Screen with display)

19) Select Version[ 1] under Measurement Sheet Version Box Select Version [ 1 ] To Create Block Estimate in ZPS_MEASURE Click on Measurement Sheet Entries 21) Select N (for Services) under item Category 22) Enter Cost Element Number : 41400008 Enter Service Item No. Ex. 8300001679 under Material/ Service Box Click on Enter 23) Click on Input Measurements Tab (in the Middle) 24) Enter Description and Number.. Number… Each…. Remarks in the last Click on Save & Exit 25) Click on Save Input Database 26) Click on YES to Save the Measurement Sheet Entries in the DB 27) Click on Measurement Sheet Entries 28) Click on Transfer to Abstract (CJ40) 29) Click on YES to Process with CJ40 30) Workflow Released for Approval will trigger for Version [ 1 ] Click on Exit 31) Enter CJ40 Click on Enter 32) Change Cost Planning Initial Screen will display 33) Select Planned Total Column Right Click on Planned Total…. Select Total Up 34) Click on [ _/ ] 35) Cost Planning of Version [ 1 ] completed Click on Save without Check 36) Check Notification.. Data was Saved in the bottom Click on Exit 37) Enter CJ20N Click on Enter 38) Select the Current Project User Status showing BEPR – Block Estimate Prepared 39) Change the User Status to BEAP Double Click on BEAP – Block Estimate Approved by CA Click on Exit 40) Click on Save Click on Exit 41) Enter ZPS_MEASURE Click on Enter 42) Select Version[ 2 ] under Measurement Sheet Version Box Select Version [ 2 ] To Create Detailed Estimate in ZPS_MEASURE 43) Select [ _/ ] Copy Measurement Sheet Elements from Version 1 Click on Measurement Sheet Entries Click on Enter 44) Click on Save Input Database Tab Measurement Sheet Version [ 2 ] 45) Click on Save Confirm YES to Save the Measurement Sheet Entries in the DB 46) Click on Measurement Sheet Entries 47) Click on Transfer to Abstract (CJ40) 48) Confirm YES to Process with CJ40 49) Workflow Released for Approval for Version [ 2 ] Click on [ _/ ] Click on Exit 50) Enter CJ40 Click on Enter 51) Select Planned Total Column Right Click on Total Up 52) Click on [ _/ ] Continue Click on Save Click on Exit 53) Enter CJ20N Click on Enter 54) Select the Current Project User Status showing DEPR – Detailed Estimate Prepared 55) Double Click on DEAP – Detailed Estimate Approved Click on Exit 56) Enter ZPS_TRANSFER (To Transfer Services) Click Enter 57) Enter Project Definition – P-DP-C-C-21-45 Select Service Activity Group One Service Activity – One Service ID Click on Execute 58) Network Changed – Update CJ20N Activity Services Values from CJ40 Click on Exit Click on Exit 59) Enter ZPS_TRANSMAT (To Transfer Materials – If Applicable only Use) Click Enter 60) Enter Current Project Definition : P-DP-C-C-21-45 Click on Execute 61) Network Changed – Update CJ20N Activity Services Values from CJ40 Click on Exit…… Click on Exit…. 62) Enter CJ20N Click on Enter Select the Current Project 63) Expand the Project Structure 64) Click on the Service Network – Land Development ID : 401000955/10 65) Enter Purchase Group – 302 MEED (Respective Division have to take) – Land Development Similarly Click Civil Works and Enter Purchase Group – 302 MEED 66) Enter Material Group : 81000000 – Land Development Similarly Enter Material Group : 81000000 to Civil Works 67) Double Click on Administrative Approval (for Purchase Requisition) Change User Status to ADMN – Administrative Approval 68) Double Click on Technical Sanctioned Received Click on Exit 69) Enter CJ30 – for Budget Allocation Click on Enter 70) Click on Enter (on View of this Screen) 71) Select total Rows Right on Budget Column Select Copy View 72) Select 05 – Planned Total from the Menu and double click Click Enter 73) Select Add and [ _/ ] Continue Click on Save Click on Exit 74) Enter CJ20N Click on Enter 75) Select Project Definition Go to More Select Project…. Edit… Status…. Release Click on Intermediate Save 76) Click on Services (or) Materials Purchase Requisition Number Generates