DEENDAYAL PORT AUTHORITY

TENDERS / CONTRACTS UNDER INTEGRITY PACT

- MECHANICAL ENGINEERING DEPARTMENT

AS ON 31.03.2024

| Sr. No. | Name of work and location | Estimated cost (Rs.) in Crores | Tendered Cost (Rs.) in Crores | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 1 | Global tender for “Engineering, procurement and construction for development of mechanized fertilizer and other clean cargo handling facility at berth no.14 in Deendayal Port, Kandla | 290.85 | -- | --- | --- | --- | --- | --- | Shri Dana Manohar, SE(M) | Technical Bid Opened on 12.01.2024 & submitted for Scrutiny |
| 2 | Procurement of 04 Nos. of 100 M.T. & above capacity Tyre mounted Electric and Diesel driven (Duo) HMC’s with Five Years Operation & comprehensive AMC (CAMC) after free CAMC of Two years. | 210.95 | 204.94 | 2.85 Below | LOI No. EL/AC/2779/ 1234 dated 15.12.2023 | M/s. Italgru s.r.l., Italy | Contract effective from the date Opening of LC. i.e. 15.02.2024 | 10 months for 2 Nos. MHCs with accessories i.e. 14.12.2024 and 15 months for remaining 2 HMCs with accessories i.e. 14.05.2025 | Shri D.K. Hazra, XEN( E) | - W.O. No. EL/WK/2779/1431 dated 05.02.2024 (10 months from the date of opening of LC) - W.O. No. EL/WK/2779/1430 dated 05.02.2024 (15 months from the date of opening of LC) |
| 3 | Supply, Installation & Commissioning of 14 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 155.70 | 144.46 96.86 towards capital cost & 47.60 towards O&M Charges. | 7.22 Below | EL/WK/2491/1816, 1817, 1818 & 1819 dated 19/04/2018 (04 Nos. of work orders) | M/s. Suzlon Energy Limited, New Delhi | 15/09/2017 | Project Comm’ned on 30/03/2019 CAMC work commenced on 30/03/2019 Scheduled date of Completion is 29/03/2039 | Shri D.K.Hazra, XEN (E) | Comprehensive A.M.C. work in progress. |
| 4 | Supply, Erection, Testing & Commissioning of mechanized bagging and wagon loading facility for handling of fertilizers at Godown No. 34 inside CJA including Comprehensive Maintenance for a period of 06 years after expiry of guarantee period of 02 years and operation of 08 yrs. from the commissioning of the project. | 120.94 | 122.33 | 0.9% above | LoA issued vide MS/WK/4025-II/GIM-265 dtd. 31.03.2017 | M/s. RISHI Shipping, Gandhidham | 31/03/2017 | 10/07/2026 | Shri Rajdeo Marine Engineer Gr.I | LoA issued on 31.03.2017. The facility has been put into commercial operation w.e.f. 11/07/2018. O&M contract is in effect upto10/07/2026. |
| 5 | Engineering, procurement and construction for phase-i development of mechanization of bulk cargo handling facility at berth nos. 8 & 9 in Deendayal Port, Kandla | 81.82 | -- | --- | --- | --- | --- | --- | Shri Dana Manohar, SE(M) | Technical Bid Opened on 09.01.2024 & submitted for Scrutiny |
| 6 | Supply, Installation & Commissioning of 6 ± 5% MW Wind Power Project in Gujarat on LSTK Basis with Comprehensive O&M | 81.82 | 63.60 | 22.27 Below | EL/WK/2472/480, 481, 482 & 483 dated 08/07/2016 (04 Nos. of work orders) | M/s. Inox Wind Limited, Noida. | 08/07/2016 | Project Comm’ned on 29/03/2017 CAMC work commenced on 27/05/2017 Scheduled date of Completion is 26/05/2037 | Shri D.K. Hazra, XEN(E) | Comprehensive A.M.C. work in progress. |
| 7 | Design, Supply, Installation, Testing & Commissioning of Firefighting system and associated facilities including Operation & Maintenance for a period of five years as per OISD-156 at Oil Jetty No. 08, Kandla, of Deendayal Port Authority (EPC Contact) | 63.62 | 69.98 | 10% Above | W.O. No. MS/WK/4054/AOB/29 dated 08/05/2023 | M/s. Jay Project, Vadodara | 08.05.2023 | 08/07/2024 for SITC work | Shri Rajdeo Marine Engineer Gr.I | Work in progress. |
| 8 | Revamping and upgradation of Firefighting system and associated facilities at Oil jetty area- Task-I: SITC of water pump / water pumping system including AMC of 5 years. | 33.77 (37.02 with credit item of 3.25) | Net Rs. 38.64[i.e. Part A (EPC (SITC) Rs. 39.56 [i.e. Rs. 39.67- (minus) Rs. 0.11 discount offered in negotiation] (plus) AMC of 5 years Rs. 1.00 (minus) Part B : Credit item : Rs. 1.92] | 14.41 % Above | W.O. ML/WK/4052(Re-tender)/ 343 dated 29/08/2022 | M/s. Jay Project, Vadodara | 29/08/2022 | 05/10/2024 for SITC work | Shri Rajdeo Marine Engineer Gr.I | Work in Progress under Provisional Extension up to 05.10.2024 |
|  | Task-II: SITC Firefighting system & associated facilities alongwith Pipeline, civil structure etc. including AMC for a period of 5 Years. | 49.55 | 45.00 | 9.17% Below | W.O. ML/WK/4058/ 350 dated 01/09/2022 | M/s. Patel Construction Co., Gandhidham | 01.9.2022 | 05/10/2024 for SITC work | Shri Rajdeo Marine Engineer Gr. I | Work in Progress under Provisional Extension up to 05.10.2024 |
| 9 | Supply, installation, testing & commissioning of Sprinkling System for coal dust suppression in 34-hectare coal yard with five Years Operation & Comprehensive Maintenance contract. | 28.11 | 24.48 | 12.92% Below | MS/WK/4046-I/GIM/592 dated 18/02/2022 | M/s Omkar Enterprise, Ahmedabad | 18/02/2022 | 03/04/2028 | Shri Dana Manohar, SE(M) | O & M Work in progress. |
| 10 | Design, Supply, installation, testing & commissioning along with Comprehensive Operation & Maintenance for a period of Five Years of 02 Nos Column Type Vessel access telescopic gangway system at Oil Jetty No. 07 and 08 of DPA. | 22.83 | 18.97 | 16.90% Below | MS/WK/4056-I/AOB-30 dt. 08/05/2023 | M/s. Woodfield Systems International Pvt Ltd, Mumbai | 08.05.2023 | 31/07/2024 for SITC work | Shri Rajdeo Marine Engineer Gr. I | Work in Progress under Provisional Extension up to 31.07.2024 |
| 11 | Operation and maintenance of 66 K.v. Substation and overhead / underground 66 K.v. Transmission Line, AMC of H.T. /L.T. Electrical Installation of Residential & Non- Residential Buildings with-in Kandla premises including Tuna Port & engagement of service operator and advisory services distribution business metering and billing for a period of Three Years. | 16.18 | 16.97 | 4.88% Above | W. O. EL/WK/2799/1287 Dated 01.01.2024. | PTC India New Delhi. | 01.01.2024 | 31.12.2026 | Shri D.K. Hazra, XEN( E) | Work in Progress. |
| 12 | Design, Supply, Installation, Testing, Commissioning of Firefighting facilities as per OISD–156 including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT. | 15.34 | 16.84 | 9.76% above | Work Order: MS/WK/4052/Gim-94 Dated 30.08.2022 | M/s. Sterling And Wilson Pvt. Lltd. | 30/08/2022 | 31/12/2028 | Shri Rajdeo Marine Engineer Gr. I | SITC work Completed. |
| 13 | Operation and maintenance contract of 02 Nos. Italguru make HMC of 120 Ton capacity along-with grabs inside C.J. area for period of two years. | 11.02 | 10.47 | 5% Below | LOI No. CME/Electrical/230/Estimate /2023/1098 dtd. 07.11.2023. | M/s. Italgru India Pvt. Ltd., New Delhi | 08.11.2023 | 07.11.2025 | Shir Anil R, AXEN (E) | Work in Progress. |
| 14 | Comprehensive AMC for Port owned two nos. of Pilot Launches & four nos. of Mooring Launches and complete O&M for one Pilot Launch & one Survey Launch for a period of three years. | 8.94 | 7.92 | 11.36% Below | LOA No. ML/WK/4068/692 dt. 15/05/2023 | M/s. Hoger Offshore and Marine Pvt. Ltd. Mumbai | 18.05.2023 (After 3 Days from LOA) | 17.05.2026 | Shri Rajdeo Marine Engineer Gr. I | Work in Progress |
| 15 | Outsourcing of 02 Nos. each Truck Mounted Mist Cannon system, and, Truck Mounted Road Sweeper system, along with comprehensive operation & maintenance, for the period of three years at DPT. | 8.93 | 10.19 | 14.12% above | MS/WK/4047/GIM-542 Dated 21/12/2021 | M/s Sambhav Corporation, Ahmedabad | 23/12/2021 | 22/12/2024 | Shri Rajdeo Marine Engineer Gr. I | Work in Progress |
| 16 | Operation and Maintenance contract of industrial light at cargo handling area, open plots, jetty area, godowns, street lighting connecting to port gates including maintenance of 11/0.433 KV substation inside cargo jetty area from zero panel to berth no. 10 and 13th to 16th berth. | 8.51 | 5.29 | 37.84% Below | Work Order No. EL/AC/2709/2092 dated 05.7.2022 | M/s. Daxraj Electricals | 05/07/2022 | 04/07/2024 | Shri D. K. Hazra XEN (E) | AMC in progress |
| 17 | Operation & Maintenance Contract of 2 Nos. Liebherr make LHM 550 model Harbour Mobile Cranes along with 03 nos. Grabs inside cargo jetty area for a period of Two years. | 8.20 | 6.92 | 15.60% Below | W. O. No. EL/WK/2028 17/02/2023 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 20.02.2023 | 19.02.2025 | Shri Anil Rautiya, AXEN(E) | Work in progress. |
| 18 | Maintenance contract of 03 nos. 25T and 02 nos. 16 T capacity MBE crane wharf cranes, alongwith grabs for a period of 2 years at inside cargo jetty area. | 7.42 | Rs. 7.05 | 5.00% below | LOI No. EL/WK/2691/947 dated 25.02.2022 | M/s. R. S. Electricals, Gandhidham | 16/02/2022 | 15/05/2024 | Shri Anil Rautiya, AXEN(E) | AMC in progress under extension period. |
| 19 | Maintenance contract of 03 nos. 25T and 02 nos. 16 T capacity MBE crane wharf cranes, alongwith grabs for a period of 2 years at inside cargo jetty area. | 7.42 |  |  |  |  |  |  | Shri Anil Rautiya, AXEN(E) | Technical Bid Opened on 05.04.2024 & submitted for Scrutiny |
| 20 | Supply, installation, testing & commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) unit, integral capstan and remote control type including Operation & Maintenance for five years at Oil Jetty No 08 of DPA. | 6.89 | 6.43 | 6.68% below | W. O. No. MS/WK/4058/AOB-05 dated 15.02.2023 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 15.02.2023 | 30/04/2024 for SITC Work. | Shri Rajdeo Marine Engineer Gr. I | Work in progress. |
| 21 | Special repairs to steel floating dry dock – self docking and repairs of pontoon no. - 5 & 6. | 6.60 | 5.41 | 18% Below | Work Order No. DD/WK/3070/41 dated 23.08.2023 | M/s. Patel Engineering Works, Gandhidham | 07.09.2023 | 31.08.2024 | Shri Dana Manohar, SE(M) | Work in progress(15 days from the date of issue of work order). |
| 22 | Outsourcing of Technical Manpower & staffs for attending various technical projects & works of the department for the period of five years. | 6.41 | 5.41 | 15.62 Below | MS/WK/4059/AOB/40 Dated 01.06.2023 | M/s. B M SORATHIA, MADHAPAR | 01.06.2023 | 31.05.2028 | Shri Rajdeo Marine Engineer Gr. I | Work in progress. |
| 23 | Supply, installation, testing and commissioning of 08 Nos. Quick Release Mooring Hook (QRMH) units, integral capstan and remote control type including Operation and Maintenance for five years at Oil Jetty No. 07 of DPT. | 6.21 | 5.50 | 11.51% Below | MS/WK/4051/Gim-64 dated 04/07/2022 | M/s. Hi Tech Elastomers Ltd, Ahmedabad | 04/07/2022 | 31/01/2028 | Shri Rajdeo Marine Engineer Gr. I | O & M work is under progress since 01.02.2023. |
| 24 | Annual Rate Contract for 11 KV distribution network at license area of DPA at Kandla. | 5.95 | 4.18 | 29.74% below | Work Oder No. EL/WK/2708/1340 dated 30/03/2023 | M/s. NK Industrial Services, Gandhidham | 01.04.2023 | 31.03.2025 | Shri D.K. Hazra, XEN (E) | AMC in progress |
| 25 | Maintenance contract of 2 Nos. ITALGRU make Harbour Mobile Crane of 63T capacity along with 6 nos. of grabs and comprehensive maintenance of Hydraulic (suspension and winch) pumps inside cargo jetty area for period of two years. | 5.70 | 4.32 | 24.21% below | LOI No. EL/AC/2702/650dated 05-01-2022 | M/s. Italguru India Pvt. Ltd., New Delhi | 01/01/2022 | 30/06/2024 | Shri Anil Rautiya, AXEN(E) | AMC in progress & Extension granted upto 30.06.2024 |
| 26 | ARC for supply & Laying of HT/LT/UG Cable, HT/LT/UG Cable fault finding inside & Outside Cargo Jetty area. | 5.39 | 3.11 | 41.40% below | LOI No. EL/AC/2766-Est/1359 Dated 17.01.2024 | M/s. N.K. Industrial Service | 23.02.2024 | 22.02.2026 | Shri Anil Rautiya, AXEN(E) | W.O. No. EL/WK/2766/1720 23.02.2024 |
| 27 | Providing Power Supply & Illumination to oil Jetty No 08 at DPA, Kandla. | 4.97 | 4.37 | 12.136% below | W. O. No. EL/WK/2768/1335 dated 08.12.2023. | M/s. N.K. Industrial Service | 08.12.2023 | 07.06.2024 | Shri D.K. Hazra, XEN( E) | Work in progress. |
| 28 | Annual maintenance contract works at A.O. Building and Gopalpuri colony for a period of two years. | 4.96 | 3.48 | 29.84% below | W.O. No El/WK/2699/1219 dated 23/02/2023 | M/s N.K. Industrial Services | 01/03/2023 | 28/02/2025 | Shri D.K. Hazra, XEN (E) | AMC in progress |
| 29 | Providing of 11 Kv H.T. Power plug point on wharf side for operation of MHC from Berth No 6 to 10 & 13 to 16. | 4.74 | --- | --- | --- | --- | --- | --- | --- | Price bid opened on 28.12.2023 & Approval of L1 offer under process. |
| 30 | Maintenance Contract of 2 Nos. Italgru make Mobile Harbour Cranes of 63T capacity along with 6 Nos. of Grabs and Comprehensive maintenance of Hydraulic (suspension and winch) pumps inside Cargo Jetty area for a period of two years | 4.70 | --- | --- | --- | --- | --- | --- | --- | Preliminary bid opening on 22.4.2024 |
| 31 | Supply, Installation, Erection, Testing and Commissioning of Mast Tower 34 hectares area | 4.68 | 3.46 | 26.75 % below | LOI No. EL/AC/2723 Dtd 27.02.2023 & Work order No.EL/WK/2723 03/4/2023 | M/s. N. K. Industrial Services, Gandhidham | 04.04.2023 | 03.04.2024 | Shri Anil Runtia AXEN (E) | Work in progress under Extension Period. |
| 32 | Comprehensive AMC of Mech works and equipment. | 4.31 | 4.12 | 4.59% Below | MS/WK/4048 Dated 14/01/2022 | M/s. Rukmani Engineering & Technical Solutions Gandhidham | 15/01/2022 | 14/01/2027 | Shri Dana Manohar, SE(M)) | Work in progress. |
| 33 | Maintenance contract of 3 Nos. 25T capacity 4 rope TIL make ELL cranes along with Grabs at Berth No. 10 at Inside Cargo Jetty area for a period of 2 years. | 4.13 | 2.88 | 30.26% Below | W.O. No El/WK/2049/1247 dated 01/03/2023 | M/s. R. S. Electricals, Gandhidham | 05/02/2023 | 04/02/2025 | Shri Anil Rautiya, AXEN (E) | Work in progress. |
| 34 | Comprehensive Annual Maintenance Contract for Channel Marking, Dumping and Mooring Buoys in the Kandla Channel along with operation & Maintenance of Heave up Barge Bhimsen for a period of three years. | 4.00 | 3.68 | 8.17% Below | W.O. ML/WK/4040/ 336 dated 01/08/2022 | M/s. Seacrafts Industries (P) Ltd., | 06.8.2022 | 05.08.2025 | Shri R.K. Sinha EIC(Tug) | Work in progress. |
| 35 | Upgradation of Substations outside Cargo Jetty area at DPA | 3.43 | --- | --- | --- | --- | --- | --- | --- | Preliminary bid opening on 19.4.2024 |
| 36 | Refurbishing of Power supply of A.O.B. | 2.83 | 2.18 | 22.57% Below | W. O. EL/WK/2039-II/1696 Dated 16.02.2024 | Shree Vallabh Electricals, Anand | 16.02.2024 | 15.08.2024 | Shri D.K. Hazra, XEN (E) | Work in Progress. |
| 37 | Maintenance contract for Air conditioners and Water coolers installed at various places at Kandla, Gopalpuri and Gandhidham Area for period of three years | 2.56 |  |  |  |  |  |  |  | Preliminary bid opened on 04.04.2024 |
| 38 | Major Repair Work of Heave Up Barge Bhimsen. | 1.67 | 1.56 | 6.41% below | ML/WK/4020-I(d)/156 dated 01/06/2022 | M/s. Patel Construction Co., Gandhidham | 01/06/2022 | 31/03/2024 | Shri R.K. Sinha EIC(Tug) | Work in progress in under Extension period. |
| 39 | Maintenance contract for Air conditioners and Water coolers installed at Various places at Kandla, Gopalpuri and Gandhi-dham Area for period of three years. | 1.55 | 1.39 | 10.14% Below | DD/WK/4309/338 dated 04.08.2021 | M/s. Inspection & Engineering Services, Ahmedabad | 04/08/2021 | 03/08/2024 | Shri R.K. Sinha EIC(Tug) | Work in Progress. |
| 40 | Supply, Installation, Testing & Commissioning of 04 Nos. Pit-less Type, Electronic in-motion Railway Weighbridges (15Kmph speed) of 140Mt capacities including comprehensive Maintenance contract for a period of 05 years after guarantee period of 02 years. | 1.51 | 1.48 | 2.07% below | W.O. No. ML/WK/3916-II/738 Dtd. 05/01/2019 | M/s. Merit BMH Engg. Pvt. Ltd., Chennai | 05/01/2019 | 17/12/2028 | Shri Dana Manohar, SE(M) | Work Completed on 18/12/2021. The weighbridges installed are under guarantee period of two years under CAMC |
| 41 | Special Repairs to ATM Office, Marine Bhavan, and Immigration Centre inside Cargo Jetty area – Electrification work therof. | .80 |  | - | - | - | - | - | - | Price bid opened on 11.03.2024. Lowest offer acceptance under process |
| 42 | Re-wiring of 160 Nos. of FCI & DLB Colony Qtr. For allotment and shifting CISF family Qtrs. –Kandla to FCI & DLB Colony (Phase-II.) | 0.55 | .36 | 34.55 below | W. O. No. EL/WK/2064/1147 Dated 28/11/2023 | M/s Power Tech Engineering | 28.11.2023 | 27.02.2024 | Shri D.K.Hazra, XEN(E) | Work in Progress. |
| 43 | Up gradation of Power Supply Including Lighting Arrangement at Periphery at Tuna Port. | 0.54 | -- | - | - | - | - | - | Shri D.K.Hazra, XEN(E) | Price bid opened on 15.12.2023. Lowest offer acceptance under process |
| 45 | Sell of renewable power generated from DPT’s 14.7MW wind power plant on Medium Term Open Access basis through tariff based competi-tive bidding through auction. | Rs. 4.26 per unit | Rs. 4.27 per unit | - | LOI No. EL/C/2688/1158, dated 10.11.2021 | M/s. UPL Ltd. GIDC Jhagadia- Bharuch | 29/12/2021 | 29/12/2022 Extension till 31/12/2024 | Shri D.K.Hazra, XEN(E) | MTOA has been extended with GETCO on 29/12/2021 and valid upto 31/12/2024. |
| 45 | Build, Operate and Maintain of 10 nos. of 120 T capacity each Automated road weighbridges on Revenue Sharing basis at DPA for a period of 10 years and buy–back of 10 nos. of existing Road weighbridges of DPA. | Tender is based on revenue sharing | Rs. 1.89 per Ton | Not Applicable | ML/WK/4013-II Dated 06.03.2023 | M/s. Serwell Cargo India Pvt Ltd, Mumbai | 10.04.2023 | 09.04.2033 | Shri Dana Manohar, SE(M) | Work in progress. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

2.	OFF-SHORE OIL TERMINAL DEPARTMENT, VADINAR 					                                                                                                        AS ON 31.03.2024

| Sr. No | Name of work & location | Estimated Cost (Rs.) in Crore/ lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of comm-ence-ment of work | Time of Comple-tion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of 2 Nos. Steel Hull Mooring Launches with Crew and Mooring Gang at OOT, Vadinar for the period of Five (05) years. Estimate: Rs. 12,53,49,780/- | 12.53 Cr. | 9.12 Cr. | 27.21 % below | OOT/ME/WK/8017/484 dated 21/05/2021. | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | 14/12/2021 | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. OT/ME/WK/8017/484 dated 21/05/2021. |
| 2. | Hiring of Service Boat for OOT, Vadinar for the period of 5 (five) years. Estimate: Rs.8,76,00,000/- | 8.76 Cr. | 9.59 Cr. | 9.49% above. | MR/WK/ 1397/66 dated 28/03/2022 | M/s. Knowledge Marine & Engineering Works Ltd., Mumbai | 05/05/2023 | 5 years | Shri Narendra Naik, ME Gr. I. | Work Order issued vide No. MR/WK/1397/66 dated 28/03/2022. |
| 3. | Operation & Maintenance of Oil Spill Response equipments for a period of five years at Kandla & OOT, Vadinar. Estimate: Rs. 7,97,20,000/- | 7.97 Cr. | 6.35 Cr | 20.32% below | No. OOT/ME/WK/3009-I/576 dated 26/12/2018. | M/s. Sadhav Shipping Ltd., Mumbai | 01/01/2019 | 5 years Extended for one year from 01/01/2024 to 31/12/2024 | Shri Narendra Naik, ME (Gr. I), | Work Order issued vide No. OOT/ME/WK/3009-I/576 dated 26/12/2018. Extended vide OO No. OOT/Civil/161/Oil spill/2023/446 dated 21/11/2023. |
| 4. | Engagement of Security Agency for providing watch and ward security supervisor and security guard at OOT, Vadinar. | 2.88 Cr. | 2.90 Cr. | 0.77% above | GEMC-511687725619008 dated 26.04.2023 | M/s. Kutch Security Services, Ahmedabad | 14.05.2023 | 04 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide:GEMC-511687725619008 dated 26.04.2023 |
| 5. | Restoration of 450 KLD Sewage Treatment Plant on Turnkey basis with 5 years AMC. Estimate: Rs. 1,54,52,800/- | 1.54 Cr. | 1.62 Cr. | 5.01 % above | OOT/C-NPS/GPCB/1234-I/666 dated 10/01/2020. | M/s. Shubham Inc., Ahmedabad. | 10/01/2020 | 5 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide No. OOT/C-NPS/GPCB/1234-I/1666 dated 10/01/2020. |
| 6. | Providing Operating and Maintaining of 2 Nos. of 32 seater bus and 1 No. 19 seater bus on hire basis for various activities at OOT, Vadinar for a period of 3 years. Estimate: Rs. 1,40,90,000/- | 1.41 Cr. | 1.44 Cr. | 2.83% above | OOT/ME-WK/RM/6004/239 dated 04/03/2021. | M/s. Safari Travels, Balasinor | 05/03/2021 | 3 years Extended upto 04/06/2024. | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6004/239 dated 04/03/2021. Extended for 3 months i.e., from 05.03.2024 to 04/06/2024 vide Order No. OOT/ME-WK/RM/6004/436 dated 27/02/2021. |
| 7. | Maintenance of beacons, leading lights & channel marking bouys in DPA waters at OOT-Vadinar | 1.26 Cr. | 0.84 Cr. | 33.33% below | GEMC-5111687713333838 dated 28/07/2023 | M/s. Seaflesh Diving and Engineering Services | 04/08/2023 | 5 years | Shri Narendra Naik, ME (Gr. I) | Work Order issued vide GEMC-5111687713333838 dated 28/07/2023 |
| 8. | Comprehensive AMC for electrical RM works at Colony and Jetty for a period of 3 years. Estimate: Rs. 1,03,32,000/- | 1.03 Cr. | 1.03 Cr. | 0.0015% above | OOT/ME-WK/RM/ 6018/329 dated 26/03/2021. | M/s. Pariya Electricals, Vadinar. | 01/04/2021 | 3 years | Shri Surya Kant Kesari, XEN (E&M), | Work Order issued vide No. OOT/ME-WK/RM/6018/329 dated 26/03/2021. |
| 9 | Monthly Ambulance Service Type B Patient Transport Vehicle Single Stretcher Premium Van, Tata Winger Ambulance 3400 Force Traveller Ambulance, SML Isuzu Ambulance, 2000 km | 0.67 Cr. | 0.72 Cr. | 5.59% | GEMC-511687783908259 Dt.15.05.2023 | M/s. P.S.Funeral and Ambulance Services Pvt. Ltd., | 01/07/2023 | 3 years | Shri SuryaKant Kesari, XEN (E&M), | Work Order Issued Vide:GEMC-511687783908259 Dt.15.05.2023 |
| 10 | Providing, Operating and Maintaining of (1) 01 Air Conditioned SUV Hyundai Creta or equivalent on 12 hours basis for COM, (2) 01 Air Conditioned 7 seater SUV Mahindra Bolero or equivalent on 24 hours basis for Multi-Purpose, (3) 01 Air Conditioned Sedan car Honda Amaze or equivalent on 12 hours basis for Officers and (4) 01 Air Conditioned Sedan Car Honda Amaze or equivalent on 24 hours basis for Pilots for a period of Three years at OOT, Vadinar through GeM. | 0.62 Cr. | 0.76 Cr. | 22.74% above | GEMC-511687761383207 Dt.18.05.2023 | M/s. Swarit E-Commerce Private Limited, Jamnagar | 02/06/2023 | 03 years | Shri M A Jadhav, Executive Engineer(Civil) (I/c). | Work Order Issued Vide:GEMC-511687725619008 dated 26.04.2023 |
| 11. | Running and Maintenance of Guest House and Staff Canteen at OOT, Vadinar Estimate: Rs. 55,66,811/- | 0.56 Cr. | 0.53 Cr. | 5.61 % below | OOT/C-WK/RM4026/114 dated 29/04/2022 | M/s. Mahakal Enterprise, Jamnagar. | 01/05/2022 | 03 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order issued vide: OOT/C-WK/RM/4026/114 dated 29/04/2022 |
| 12 | Maintenance Contract of the Residential Building and Non Residential Building in Port Colony and Jetty at Vadinar. | 0.53 Cr. | 0.47 Cr. | 9.51% below | OOT/C-WK/ RM/4050-II/328 dated 29/07/2022 | M/s. G N Enterprise, Vadinar | 01/08/2022 | 02 years | Shri M.A. Jadhav, XEN (Civil)(I/c), | Work Order Issued Vide: OOT/C-WK/RM/4050-II/328 Dt.29.07.2022 |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

3.	CIVIL ENGINEERING DEPARTMENT	                                                                                                                                       					AS ON 31.03.2024

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dredging in the Navigational Channel & Alongside Cargo Berths/Oil Jetties at Deendayal Port Trust for year 2020-23”. Location At Kandla | 393.80 | 310.04 | 21.27 % Below | EG/WK/1067/2020/Work/52 dated 05.04.2020 | M/s Adani Ports and Special Economic Zone Ltd., Ahmedabad | 09/04/2021 | 08/04/2024 36 months | Shri K. Srinivasa Rao, Dy CE (H &D) | Work in progress |
| 2 | Augmentation of liquid cargo handling capacity by revamping of existing pipeline network at Oil Jetty are, Deendayal Port Trust, Kandla | 130.49 | 126.49 | 3.05% below | PL/WK/8306 NIT-PQ/08 dated 31/08/2021 | M/s. Patel Corrrtech JV, Gandhidham | 30/09/2021 | 31.09.2024 | Shri B. Rajendra Prasad, SE (P) | Work in progress. |
| 3 | Construction of Oil Jetty No.8 at Old Kandla. | 105.51 | 99.08 | 6.09% below | No.CN/WK/1571/work/243 dtd. 03/02/2021 | M/s Kargwal KM Joint Venture, Mumbai | 17/02/2021 | 31.07.2024 | Shri Rajesh Meghani, XEN(C-I | Work in progress. |
| 4 | Development of land from Junction of WG 1 & 2 to LC 236B at Kandla (Phase-1) | 81.99 | 67.67 | 27.69% below | CN1/WK/3014/Work/87 Dated 11.08.2023 | M/s. Shree Ram Infrastructure | 18.08.2023 | 17.02.2025 | Shri Rajesh Meghani, XEN(C-I) | Work in progress |
| 5 | Development of backup area of oil Jetty No.8 to 11 (Phase-I) | 80.97 | 66.58 | 17.77% below | CN/WK/1582/Work/858(G) Dated 14/12/2022 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 21/12/2022 | 20.12.2023 Extension granted upto 20.03.2024 | Shri Rajesh Meghani, XEN(C-I | Work in progress. |
| 6 | Development of area from Junction of West gate-I to west gate-II now renamed as "development of land west side of road in between junction of west gate 1&2 and railway line to 12th berth - Phase -I | 80.31 | 55.73 | 30.60% below | CN-I/WK/2277/Work/881 Dated 28.10.2022 | M/s. Digvijay Construction Pvt. Ltd., Gandhinagar. | 07/11/2022 | 06/05/2024 | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 7 | Up - gradation of tuna road from two lane to four land (Phase-I) | 71.57 | 57.43 | 19.74% below | LOA No. EG/WK/8116/349 dated 03/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhinagar | 10/11/2022 | 09/11/2024 | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 8 | Upgradation of Plots & S.W.D. in 66 Hectare area inside cargo jetty area | 65.80 | 59.55 | 9.51% below | HW/WK/2488/704 dated 11/01/2023 | M/s. Baldaniya Construction, Anjar. | 17/04/2023 | 16/10/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 9 | Up-Gradation of Road From Junction Of Tuna Jetty Road To Take Off Point At Tuna Tekra | 62.86 | 51.89 | -26.26% | Work order issued on dated: 07/03/2024 | M/s Hariom Earth Movers & Transport | 18/03/2024 | 18 Months | Shri Rajesh Meghani, XEN(C-I) | Work in progress |
| 10 | Development of four lane road corridor from LC236B to 16th CB along railway line (Phase-I) | 55.28 | 38.47 | 30.41% below | CN1/WK/3012/Works | M/s. Hariom Earthmovers & Transport | 10.04.2023 | 09/11/2024 | Shri Rajesh Meghani, XEN(C-I) | Work in progress |
| 11 | Construction of new godowns in place of existing godown no. 19 to 21 & 25 inside C. J. Area | 53.20 | 42.94 | 19.27% below | HW/WK/2580/705 dated 11/04/2023 | M/s. Patel Construction Co. Gandhidham. | 17/04/2023 | 16/10/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 12 | Raising & upgrading the RCC Plots adjoining to track no. 10,11&12 inside Cargo Jetty Area | 53.13 | 43.27 | 18.56% below | HW/WK/2561/339 dated 07/07/2023 | M/s. Radhe Associated, Mehsana | 22/07/2023 | 21/07/2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 13 | Development of Container Terminal at Tuna-Tekra Common connectivity from Take off point upto back up area" | 40.80 | 26.84 | 34.31% Below | CN/WK/6015/75 Dated 11/10/2023 | M/S.K.K. Sorthya JV M/S. HARIOM EARTHMOVERS & TRANSPORT | 12/10/2023 | 11/09/2024 | Shri Chetan Kumar Jeniya XEN( C ) | Work in progress |
| 14 | Up gradation of roads & SWD outside cargo jetty area at New Kandla (Cement Concrete Pavement) | 40.35 | 24.65 | 38.88% | RW/WK/7821-I/362 dated 18/05/2023 | M/s. Neelkanth Infratech Pvt. Ltd., Gandhidham. | 22/05/2023 | 21/08/2024 | Shri MT Gohel XEN(Road) | Work in progress |
| 15 | Upgradation of Plots, Roads & SWD in 40 hectare area inside Cargo Jetty Area. | 39.36 | 31.48 | 19.84% below | HW/WK/2456/579A dated 31/10/2022 | M/s. Neelkanth Infratech Pvt. Ltd. | 22/10/2022 | 21/04/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 16 | Widening of Road from Junction of WG 1 & 2 to 12th Berth | 38.50 | 32.24 | 2.99% below | CN1/WK/3013/work/44 Dated 24.05.2023 | M/s. Dhanji K. Patel, Anjar. | 01.06.2023 | 30.11.2024 18 months | Shri Rajesh Meghani, XEN(C-I) | Work in progress. |
| 17 | Raising & Upgradation of Plots inside Cargo Jetty Area | 38.24 | N.A. | N.A. | N.A. | N.A. | N.A. | - | - | Price bid opened , LOA to be issued |
| 18 | Construction of Dome shaped Storage Sheds inside C.J. Area - Phase-II | 30.63 | 24.24 | 20.86% | HW/WK/2567/335 dated 26/06/2023 | M/s. Patel Construction J/V M/s. Neelkanth Infrastructure P. Ltd. | 05/07/2023 | 04/01/2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 19 | Providing RCC Cable Trench for Electric Cables inside Cargo Jetty Area | 22.49 | 16.28 | 27.6% | EG/WK/1209/54 Dated 15/03/2024 | M/s Mohit Enterprise,Rajkot | 8/04/2024 | 07/04/2026 | Shri Mahesh Makhijani, XEN(H) | LOA Issued |
| 20 | Construction of Vidyalaya Building at Port Colony Gopalpuri, Gandhidham | 21.64 | 20.24 | 6.00% below | TD/WK/7848/1059 dated 31/07/2023. | M/s. Dipesh Construction Co., Anjar | 04/08/2023 | 03/08/2024 | Shri H.K Bhaskar, XEN(TD) | Work in progress |
| 21 | Development of area adjacent to Tuna-RCC track by earthwork in embankment from 4.00 Km to take-off point for doubling of line to facilitate upcoming new projects at Tekra | 19.62 | 13.23 | 32.57% below | HW/WK/2583 dated 11/12/2023 | M/s. Hariom Earthmovers & Transport, | 27.12.2023 | 26.08.2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 22 | Up-gradation and Strengthening of Existing Oil Jetty No 3 | 19.27 | 15.78 | 13.38% Below | CN/WK/608/FF&EMD/155 daed 22/06/2023 | M/s Patel Construction Co., Gandhidham | 01/07/2023 | 29/02/2024 | Shri Muneeb Ansari , XEN (P) | Work in progress |
| 23 | Development of Parking yards for trucks/vehicles for pre-checking of documents before arrival at gates along with ancillary facility like Canteen, Toilet block, Garage, Rest shelter and High mast tower etc, on North of Road leading to W.G.-I & II outside CJA. | 16.76 | 14.59 | 12.87% below | HW/WK/2446/463 dated 26.06.2021 | M/s. Indian Construction Co., | 08/07/2021 | 07/07/2022 Extension granted upto 07.04.2024. | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 24 | Providing Road network & SWD to newly added custom bonded area (25 Ha area) | 14.50 | 13.49 | 7.18% below | HW/WK/2559/826 dated 15/01/2024 | M/S. NEELKANTH INFRATECH PVT.LTD | 29.01.2024 | 28.01.2025 | Shri Mahesh Makhijani, XEN(H) | Work order issued |
| 25 | Annual Maintenance contract for roads at Kandla for two years | 8.31 | 5.97 | 28.23% below | RW/WK/7810-I/239 dated 05/01/2023 | M/s. Dhanjibhai K. Patel, Anjar. | 05/01/2023 | 04/01/2025 | Shri MT Gohel , XEN XEN(TD) | Work in progress. |
| 26 | Construction of E & D type quarters at Gopalpuri (Stage-1, D type ) | 8.23 | 6.25 | 21.34 | TW/WK/7840-I/1505 Dated 26/12/23 | M/s Mepabhai mandan & Co. JV M/s KK Sarothia | 01.01.2024 | 31.12.2024 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 27 | Construction of Ring Road (Periphery road ) from NH-8A (From KASEZ) to Adipur | 8.20 | 6.33 | 22.83% below | TW/WK/7804-I/418 dated 04/11/2022 | M/s. Shree Ganesh Construction, Anjar | 10/11/2022 | 09/10/2023 Extension granted upto 09.07.2024 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 28 | Special Repairs of plot no 8 & 9 at bunder basin (5 hectares) | 7.99 | 7.17 | 10.33% below | HW/WK/2556 dated 30/05/2023. | M/s. Balaji Infra, Anjar. | 06/06/2023 | 05/06/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 29 | Construction of Storage Shed Over Existing Floor of Godown No. 3 & 4 inside C. J. Area | 7.81 | 6.05 | 11.10% below | HW/WK/2570/765 Dated 11.08.2023 | M/s. Neelkanth Infratech Pvt. Ltd. | 26.08.2023 | 27.07.2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 30 | Improving / Upgradation of Custom Fencing Wall of Cargo jetty and Bunder Area | 7.68 | 5.38 | 29.95 % below | HW/WK/2507-I/73 dated 15/02/2022 | M/s. Deosi Govindji Parmar (Lead Partner) J/v M/s. Shree Balaji Construction Co. | 28/02/2022 | 27/02/2023 Extension granted upto 30.04.2024 . | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 31 | Construction of garage and repair workshop building for mobile cargo handling equip-ments inside cargo jetty area | 7.61 | 5.89. | 22.6% Below | HW/WK/2577/818 11.12.2023 | M/s Viyuha infrabuild | 18/12/2023 | 17.12.2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 32 | Strengthening to Residential & Non - Residential Building at New Port Colony, New Kandla | 7.56 | 4.99 | 34.05% below | RW/WK/7819-I/363 dated 18/05/2023 | M/s. Patel Construction Co., Gandhidham. | 22/05/2023 | 21/05/2025 | Shri MT Gohel , XEN XEN(Road) | Work in progress. |
| 33 | Providing RCC and asphalt roads inside and outside of oil jetty area at Old Kandla | 7.12 | 4.79 | 32.76% Below | PL/WK/8490-I/189 dated 27/02/2023 | M/s. Mepabhai Mandan and Co., Adipur | 27/02/2023 | 26/01/2024 | Shri Rajendra Prasad B., S E (PL) | Work in progress. |
| 34 | Removal of old abandoned RCC jetty structure in between Oil Jetty No. 2 & 3 at Old Kandla. | 6.75 | 6.46 | 6.39% below | PL/WK/8424-I/562 dated 15/06/2023 | M/s. Goyal Iron and Steel Traders. | 15/06.2023 | 21/11/2023 , further extension granted upto 21.01.2024. | Shri Rajendra Prasad B., S E (PL) | Work in progress. extension sought upto 21.05.2024 which is under consideration |
| 35 | Appointment of Independent Engineer for the work of development of container terminal at Tuna Tekra, Deendayal Port on BOT basis under PPP mode for a concession period of 30 years. | 11.01 | 2.98 | 75.12 % Below | EG/WK/5371/223 Dated 15.11.2023 | M/S.RITES Ltd, HARYANA | - | - | Shri Sunil Soren (XEN D) | LOA Issued |
| 36 | Appointment of Project Management Consultant (PMC) for Capital and Maintenance Dredging works of Deendayal Port Authority | 4.96 | Rs. 5.46 | 9.85% Above | LOA No.EG/WK/6147/ 227 dated 22.11.2023 | M/s AECOM INDIA PVT LTD, GURGAON | 25/11/2023 | 24/11/2027 | Shri K. Srinivasa Rao, Dy CE (H &D) | Work in progress |
| 37 | S/R to A.O. Building at Gandhidham. | 5.73 | 4.55 | 20.70% below | TW/WK/7797-I/1271 dated 21.09.2023 | M/s. Mepa bhai Mandan & Co. JV K.K. Sorathia, | 25.09.2023 | 24.08.2024 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress |
| 38 | Appointment of technical, legal and financial experts from the firms of Transaction Advisor for "providing legal, technical and financial transactions for all ongoing and future proposals of DPA on PP / Captive Mode for the period of two years and further extendable for one year. | 5.46 | 3.61 | 33.88% below | EG/WK/4759/TA-IV dated 11/10/2022 | M/s. Infrastructure Development (Karnataka) Corporation Ltd (Ideck) | 14/10/2022 | 13/10/2024 2 years and further extendable for 1 year | Shri Sunil Soren (XEN D) | Work is in Progress. |
| 39 | Preparing and monitoring of Environmental Management Plan for DPA at Kandla. | 5.01 | 4.87 | 38.17 % below Estimated Cost | EG/WK/EMC/11023/2011/III/239 dated 15.02.2023 | M/s. GEMI Gujarat Environment management Institute. | 14.04.2023 | 13.04.2027 | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 40 | Improving & up-gradation of gardens and land scrapping at Gopalpuri (Renovation of Nehru Park and rain water harvesting by strengthening of SWD network near recharging pond at Gopalpuri | 4.79 | 2.40 | 49.81% below | TW/WK/7802-I/404 dtd.16.07.2021 | M/s. Rainbow Infrastructure, Rajkot | 03.07.2021 | 02.07.2022 (main work) 02/07.2024 (maintenance) | Shri Hemant Kumar Bhaskar XEN(TD) | Main Work completed. Maintenance work is in progress |
| 41 | Painting to Port structure and its allied structure at Oil Jetty area at Old Kandla (Phaze-I) (R/M of Oil Jetty at Old Kandla. | 4.18 | 4.59 | 17.52% Above | PL/WK/8475-I/789 Dated 31.08.2023 | M/S.ACER INFRA TRADE-GANDHIDHAM | 11.09.2023 | 10.09.2024 | Shri Rajendra Prasad SE(PL) | Work in progress |
| 42 | Special Repair to existing storm water drain network inside Cargo Jetty area. | 8.33 | 5.91 | 28.21% Below | HW/WK/2568/762 dated 11.08.2023. | M/S.SHILPVIEW CONSTRUCTION-SANJAY.K.SORATHIA AND CO (JV) | 18.08.2023 | 17.11.2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 43 | Upgradation of Sewage treatment plant at Gopalpuri | 4.27 | 4.14 | 3.0363% below | TW/WK/7736-I/254 dated 21/07/2021 | M/s. Rajkamal Buildings, Infrastructure (P) Ltd., | 01/08/2022 | 31/01/2026 | Shri Hemant Kumar Bhaskar XEN(TD) | Main work completed. Maintenance work is in progress.. |
| 44 | Construction of Fire Brigade Station Opposite Jetty Office in CKD Yard inside Cargo Jetty Area | 3.48 | 2.94 | 15.62% below | HW/WK/2540/770 dated 24/04/2023 | M/s. Murlidhar Projects | 01/05/2023 | 31/07/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 45 | Services of Third Party Government Survey Agency for the Dredging at Deendayal Port (2020-23) | 3.24 | 2.43 | 35.73% Below | W.O. No. HD/WK/1071/2020/Work dated 08/02/2021 | M/s. Wapcos Ltd., Gurgaon - 122015 Haryana- India | 11/02/2021 | 10/02/2024 36 months | Shri K. Srinivasa Rao, XEN (H&D) | Work in progress Further three months extension is under process |
| 46 | S/R to CISF complex building & Structure at New Kandla | 3.24 | 2.40 | 26.04% below | RW/WK/ 7817-I/307 dated 27/03/2023 | M/s. Acer Infra Trade, Gandhidham | 03/10/2023 | 02/10/2024 | Shri MT Gohel, XEN(Road) | Work in progress. |
| 47 | Maintenance of public health & underground drainage at Gopalpuri Port Colony & KDLB Colony for the period of two years. | 3.15 | 1.56 | 50.51% below | TW/WK/7813-I/ dated 05/07/2022 | M/s. Patel Construction, Gandhidham. | 05/07/2022 | 04/07/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 48 | Annual Maintenance Contract for residential and non-residential building a Port Colony, Gopalpuri for two years. | 3.05 | 1.71 | 44.12% below | TW/WK/7806-I/126 dated 30/04/2022 | M/s. Dhanjibhai K. Patel, Anjar | 02/05/2022 | 01/05/2024 | Shri Hemant Kumar Bhaskar XEN (TD) | Work in progress |
| 49 | Deployment of equipment for cleaning of all toilet blocks inside Port area and to maintain high standard of hygienic and to avoid pollution. | 2.99 | 2.23 | 25.40% below | HW/WK/2551/202 dated 31/10/2022 | M/s. Shree Ganesh Construction, Anjar - Kutch | 01/11/2022 | 30/10/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 50 | R/M of Arboriculture / Horticulture work in Public Building at Gopalpuri and KDLB Colony for the year 2022-24 | 2.78 | 1.68 | 39.35% below | TW/WK/7825-I/670 dated 24/03/2023 | M/s. Acer Infra Trade, Gandhidham | 27/03/2023 | 26/03/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 51 | Maintenance Contract for Godown inside Cargo Jetty area for two years 2022-23 & 2023-24) | 2.70 | 2.08 | 23.77% Below | HW/WK/2531/324 dated 05.06.2023 | M/s. Sanjay k. Sorathiya & Co., Gandhidham. | 05/06/2023 | 04/06/2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 52 | Annual Maintenance Contract for AO Building at Gandhidham for 02 years | 2.67 | 1.95 | 27.00% below | TW/WK/7820/654 dated 13/03/2023 | M/s. Acer Infra Trade, Gandhidham | 15/03/2023 | 14/03/2025 | Shri Hemant Kumar Bhaskar XEN(TD) | Work in progress. |
| 53 | Special Repairs to ATM office, Marine Bhavan, Immigration Centre Inside Cargo Jetty Area | 2.63 | 2.12 | 18.52% below | HW/WK/2536/297 dated 21/04/2023 | M/s. Murlidhar Projects | 28/04/2023 | 27/04/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 54 | Design, Construction, Procurement, Installation and Commissioning of 50 Tonne per day Semi-Automatic MRF plant at Deendayal port Gandhidham on EPC mode | 2.50 | 2.49 | 7.00 % above estimate cost | CE/Const-I/2304/wet wasteplant/2023 dated 15.03.2024 | M/s.JAINUM FOOD AND WASTE PROJECTSS PVT.LTD-INDORE | 15.03.2024 | 14.07.2024 | Shri Chetan Kumar Jeniya XEN (c ) | WORK IN PROGRESS |
| 55 | Two years contract for House Keeping & cleaning of office buildings outside Cargo Jetty area at New Kandla | 2.31 | NA | NA | N.A. | N.A. | N.A. | N.A. | XEN (H) | Preliminary Bid opened on 26/03/2024, tender under scrutiny |
| 56 | Two Years Contract for supply and maintenance of railway tracks inside and outside cargo jetty area (For Years 2023-25) | 2.23 | 1.77 | 21.06% below | HW/WK/2584/772 Dated 31.08.2023 | M/s. Dharti Construction | 07.09.2023 | 06.09.2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 57 | S/R to AO Building at Gandhidham - Renovation of toilet blocks, recreation room, old board room. | 2.20 | 1.32 | 40.13% below | TW/WK/7795-I/ 111 dt. 21/04/2022 | M/s. Ankita Construction, Adipur | 25/04/2022 | 24/04/2023 | Shri Hemant Kumar Bhaskar XEN(TD) | Work Completed |
| 58 | Providing PMC Services for preparation of Detailed Project Report and assist in Supervision during execution for the expansion of existing Railway siding for Tekra Port of Deendayal Port Authority to serve upcoming Projects at Tekra | 2.20 | NA | NA | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Submitted for dischrage and re-invite. |
| 59 | Maintenance contract of fenders inside cargo jetty area for two years | 1.97 | N.A | N.A | N.A | N.A | N.A | N.A | Shri Mahesh Makhijani, XEN(H) | Tender reinviation of tender under approval |
| 60 | House Keeping & Cleaning of Building of Office building and surrounding outside Cargo Jetty Area for the year 2021-23. | 1.97 | 1.07 | 45.36 % below | HW/WK/2538/68 dated 07/02/2022 | M/s. Rajput Infrastructure Co. , Gandhidham | 22/02/2022 | 21/02/2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress. Proposal for 3 month extension 07/05/2024 sent for approval |
| 61 | Annual maintenance contract for buildings, walkways, trestles, firefighting pipelines, fenders and garden isnide & outside oil jetty area at Old Kandla | 1.67 | Part A - 1.35 and Part B - 2.82 | 21.0847% below | PL/WK/8486-I/596-A dated 01.07.2023 | M/s. Vihat Construction Co. | 08.07.2023 | 07.07.2025 | Shri Rajendra Prasad B., SE (PL) | Work in progress |
| 62 | Two years maintenance contract for office buildings outside Port area (Civil work) | 1.63 | 1.11 | 32% below | HW/WK/2548/788 DATED 15.09.2023 | M/s. Rajput Infrastructure Company | 22.09.2023 | 21.09.2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 63 | S/R to emergency response centre at Old Kandla. | 1.62 | 1.14 | 29.63% below | PL/WK/8501-I/596A Dated 11.08.2023 | M/s. Vihat Construction Co. | 21.08.2023 | 20.07.2024 | Shri Rajendra Prasad B.,SE (PL) | Work in progress |
| 64 | Annual maintenance contract for firefighting pipeline and water supply line and Misc. civil works for overhead and underground water tank inside and outside cargo jetty at Kandla. | 1.62 | 1.08 | 33.30% below | PL/WK/8495-I/763 Dated 22.08.2023 | M/S.Sanjay K. Sorthiya Co. | 24.08.23 | 23.08.2024 | Shri Rajendra Prasad B., SE (PL) | Work is in progress |
| 65 | Two years’ maintenance contract for railway track leading to Tuna from0 to 11 Km KPLT line (Take off at 2.573 Km at Gandhidham Yard to 13.54 Km) including LC-1, LC-2 | 1.46 | NA | NA | NA | NA | NA | NA | Shri Mahesh Makhijani, XEN(H) | Submitted for opening of price bid |
| 66 | Maintenance contract for quay and transit area inside Cargo Jetty Area for two years. | 1.46 | 1.15 | 21.60% below | HW/WK/2597/857dated 04/03/2024 | M/s. Vihat Construction Co.,D-30, KPT Colony, Gopalpuri. | 11.03.2024 | 10.03.2026 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 67 | Appointment of Independent Engineer for the work of “Development of Marine Liquid Terminal Facilities consisting of SPM and Two Product Jetties in KPT waters at OOT, Vadinar for Handling Crude and Petroleum Products on Captive Use Basis”. | 1.44 | 1.18232 | 17.89% below | Work Order No.EG/WK/4823(IE)/109 dated 22/10/2019 | M/s RINA Services s.p.A,Mumbai | 01/11/2019 | 01/11/2019 to the date of expires of 6 months from the date of commercial operation or extension thereof 42 months | Shri Sunil Soren (XEN D) | As concessionaire has not started construction activity, the work order issued to M/s. RINA has been kept in abeyance. As the BG submitted by m/s RINA was expiring on 31.01.2023, DPA informed M/s RINA to extend the said BG submitted. However ,M/s RINA has not responded and BG has expired |
| 68 | Construction of electric substation near old unloader building to replace substation of 6th cargo berth and at plot no B2 of 34 hectare area | 1.39 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | L-1 Offer submitted for approval |
| 69 | Third Party Inspection and Quality Inspection and Quality Assurance for the works costing more than Rs. 1.00 Cr. of Civil Engineering Department of Deendayal Port Authority. | 1.358 | 1.17 | 14.05% below | Work Order No.EG/WK/5212/53 dtd.16/10/2021 | M/s. VCS Quality Services pvt. Ltd., Mumbai | 25/10/2021 | 24/10/2023 | Shri Sunil Soren, XEN(D) | Work in Progress. 6 Months extension granted . i.e. upto 23.04.2024 |
| 70 | Maintenance Contract for Non-residential buildings inside Harbour area (Civil Work) | 1.31 | 0.95 | 27.55% below | HW/WK/2526/122 dated 20/04/2022 | M/s. Mepabhai Mandan & Co., Adipur | 05/05/2022 | 04/05/2024 24 months | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 71 | Strengthening of existing environmental management cell at DPT Appointment of environ-ment experts for two years and further extendable for one year | 1.232 | 1.20 | 2.60% below | EG/WK/ 4783/V/131 dtd.05/02/21 | M/s. Precitech Laboratories Pvt. Ltd., Vapi | 15/02/2021 | 14/02/2023 Extension granted upto 15/02/2024 | Shri B. Rajendra, SE(PL) & EMC (I/C) | Work in progress |
| 72 | Maintenance contract for cleaning& house keeping work of DPA hospital & isolation ward at Gopalpuri & Kandla & Adipur dispensary for the period of 2 years | 1.22 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar XEN(TD) | Technical Bid opened and sent for process, thereafter price bid opened, Justification from bidder is sought. |
| 73 | Two years maintenance contract for Railway track leading to Tuna from 0 to 11 Km KPT Line (Take off Point at 2.573 Km at GIM Yard to 13.54 Km including LC-1, LC-2) | 1.19 | 0.908 | 23.77% below | HW/WK/2515/432 DATED 31/05/2021 | M/s Patel Construction. Gandhidham | 14/06/2021 | 13/06/2023 24 Months (Extension grated upto 30/11/2023) (Further extension granted upto Feb 2024) | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 74 | Maintenance contract for sports complex for the period of two years at Gopalpuri. | 1.19 | 0.70 | 41.17% Below | TW/WL/7826-I Dated 25.10.2023 | M/s Rajput Infrastructure Company | 23.10.2023 | 22.10.2025 | Shri Hemant Kumar Bhaskar, XEN(TD) | Work in progress |
| 75 | Dismantling of existing godown no.19 to 23 inside cargo jetty area | Part A = 0.26 Part B = 0.93 (credit item) | Part A= 0.42 Part B= 0.88 (Credit part) | 25.09% Above | EG/WK/1197/255 Dated 12.01.2024 | M/s Rajesh Traders | 06-02-2024 | 05-08-2024 | Shri Mahesh Makhijani, XEN(H) | Work in progress |
| 76 | Supply and transportation of water at Kandla, Tuna and Gandhidham for a period of two years | 1.13 | 0.82 | 27.27% below | PL/WK/8461-I/25 dated 09/02/2022 | M/s. Sanjay K Sorathiya & Co. | 09/02/2022 | 08.02.2024 | Shri Rajendra Prasad B., SE (PL) | Work in Progress |
| 77 | House Keeping and cleaning of office building and surrounding inside and outside oil jetty area at Kandla | 1.10 | 0.97 | 15.9% Below | PL/WK/8498-I/844 Dated 18.09.2023 | M/s. Sanjay K Sorathiya & Co. | 25.09.2023 | 24.09.2025 | Shri Rajendra Prasad B., SE (PL | Work in Progress |
| 78 | Maintenance Contract for Tree Plantation near offices, other buildings, along roads, islands, gates, etc. inside/outside cargo jetty area for two years | 0.97 | 0.62 | 35.82% below | HW/WK/ 2582/284 dated 17/03/2023 | M/s. Vihat Construction, Gandhidham | 25/03/2023 | 24/03/2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 79 | Maintenance Contract for Residential & Non - Residential Building at New Port Colony at New Kandla for two years. | 0.97 | 0.62 | 36.20% below | RW/WK/7816-I/242 dtd. 17/10/2022 | M/s. Murlidhar Projects | 17/10/2022 | 16/10/2024 | Shri MT Gohel , XEN (Road) | Work in progress. |
| 80 | Dismantling of Residential and Non - Residential buildings at New Kandla | 0.96 | 1.58 | 64.42% Above | RW/WK/7706-I/19 dtd.08.12.2021 | M/s. Symcom Exim (P) Ltd., Mumbai | 16.12.2021 | 15.08.2022 | Shri MT Gohel , XEN(Road) | Work under dispute and matter referred to court |
| 81 | Two Years Contract for House Keeping & Cleaning of Gate office buildings and Non-residential buildings inside cargo jetty area | 0.96 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | Shri Mahesh Makhijani, XEN(H) | Tender under scrutiny |
| 82 | Maintenance Contract for sanitation of New Port Colony, New Kandla for period of 2 years | 0.95 | 0.56 | 41.00% below | RW/WK/7820-I/375 dated 02/06/2023 | M/s. Acer Infra Trade, Gandhidham | 05/06/2023 | 04/06/2025 | Shri MT Gohel , XEN(Road) | Work in progress. |
| 83 | Running and house keeping of guest house , A-9 Bungalow & Bachelor accommodation / Bungalow at port colony, Gandhidham for 3 years | 0.90 | - | - | - | - | - | - | Shri Hemant Kumar Bhaskar , XEN (TD) | New tender prepared and processed for approval |
| 84 | Providing firefighting pipeline at 34 hectares inside cargo jetty area (A) Appointment of Technical Advisor for the work of Upgradation of firefighting system & associated facilities inside cargo jetty area. DPA | 0.86 | 0.80 | 6.39% below | PL/WK/8476-I/21 dated 21.12.2022 | M/s. S.R. Engineers | 26.12.2022 | 25.06.2024 | Shri Rajendra Prasad B., SE (PL) | Work in progress |
| 85 | Two years contract for cleaning of storm water drain inside cargo jetty area | 0.78 | 0.49 | 37.18% below | HW/WK/2562/342 dated18/07/2023 | M/s. Narayan Construction Co. | 25/07/2023 | 24/07/2025 | Shri Mahesh Makhijani, XEN(H) | Work in progress. |
| 86 | White washing, painting & distempering to residential and non-residential buildings & CISF complex at New Port Colony, New Kandla (for 2 years) | 0.67 | 0.38 | 43.20% | RW/WK/7790-I/ dated 05/2022 | M/s. Rajput Infrastructure Co., Gandhidham. | 01/06/2022 | 31/05/2024 | Shri MT Gohel , XEN (Road), | Work in progress. |
| 87 | Housekeeping of liaison office cum rest house for DPA at Ahmedabad port for 3 years | 0.53 | 0.53 | - | TW/WK/7816-I/9167 Dated 24.08.2023 | M/S N. Kumar Associates International Mumbai | 01.09.2023 | 31.08.2026 | Shri Manoj Gohel XEN(Road), | Work in progress |
| 88 | Maintenance Contract of 1.5 MLD Sewage treatment plant at New Port Colony, New Kandla for 2 years | 0.52 | 0.29 | 45.13% below | RW/WK | M/s. Gadhvi Construction Co., | 21/06/2022 | 20/06/2024 | Shri Manoj Gohel XEN(Road), | Work in progress. |

MEGA INFRASTRUCTURE PROJECTS

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore | Tendered Cost (Rs.) in Crore | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 89 | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT basis under PPP mode | 4243.64 | NA | NA | Tender No. CE/13 | M/S Hindustan Infralog Private Limited | LOA Awarded Dated 28/01/2023 | 36 months from the date of award of concession | Shri Sunil Soren XEN (Design) | RFP opened on 27.01.2023, M/S Hindustan Infralog Private Limited was declared as successful Bidder. Subsequently, LOA was issued on 28.01.2023 and the same was acknowledged and accepted by M/s. Hindustan Infralog Private Limited on 31.01.2023. On the request of M/s. Hindustan Infralog Private Limited, the time period for execution of Concession Agreement between the Authority and SPV was extended time to time up to 30.08.2023. On 25.08.2023 Signing of Concession Agreement between Deendayal Port Authority and M/s. Hindustan Gateway Container Terminal Kandla Private Limited was executed on 17.10.2023 Hon’ble Prime Minister virtually laid foundation stone for the Project. Presently, both Parties are fulfilling CP on their respective parts. On 19.01.2024, the Project Site has been jointly surveyed by Authorized representatives of the Parties. Schedule date of fulfillment of CPs is on 21.02.2024. However, on request of M/s HGCTKPL requesting extension of fulfilment of CP till 15.03.2024 and same has been extended upto 15.03.2024. Upon the fulfilment of the CPs on the part of both Parties, the Concession for the project awarded by DPA to M/s HGCTKPL on 14.03.2024 . |
| 90 | Development of Marine Liquid Terminal Facilities consisting of SPM and two product jetties in DPT waters at OOT, Vadinar for handling Crude and Petroleum Products on Captive Use Basis | 448.00 | NA | NA | Concession Agreement executed between DPA (erstwhile KPT) and M/s. Coviva Energy Terminals Ltd. (erstwhile VLTL) on 16/04/2015 | Name of the Concessionaire : M/s. Coviva Energy Terminals Ltd. Project is to be implemented by CETL | Award of Concession granted on 16/08/2019. However, CETL not initiated Project implementa-tion | Original: 36 months from date of award of concession i.e., 16/08/2019 to 15/08/2022 Revised : 42 months from date of award of concession (due to six months extension granted by DPA due to COVID 19 Force Majeure) | Shri Sunil Soren XEN (Design) | :1) Total LD levied on M/s CETL (period of delay 16/2/2021 to 12/11/2023) is 22,40,00,000.00 (specified limit of 5% of estimated project cost exhausted). • Note: PRESENT STATUS: The Scheduled construction Period (revised) 42 months have elapsed on 15/02/2023 but M/s CETL not initiated project Implementation. |
| 91 | Development of Oil Jetty to handle liquid cargo and ship bunkering terminal at Old Kandla on BOT basis | 343 |  |  | TenderNo. 026/XEN (Design) Dated 16.04.2015 | M/s IMC Limited | 11.12.2020 | 24 months from date of award of concession | Shri Sunil Soren E.E (Design) | The Scheduled construction period is completed on 10.12.2022.. Interim Milestones no 2nd, 3rd, 4th & 5th have been delayed. LD imposed. On time to time M/s KOTPL paid LD upto July 2023. Further DPA raised Demand note up to 30.04.2024 . Due date for the payment is 30.03.2024 On 23.09.2023, 30.09.2023, 30.10.2023, 30.11.2023, 04.01.2024 , 31.01.2024 & 7.03.2024 M/s KOTPL deposited Rs 71,24,800, Rs 36,20,800, Rs 35,04,000, Rs 36,20,800, Rs 36,20,800 & Rs 33,87,200 ,Rs36,20,800 towards LD under protest for the period from 01.08.2023 to 31.03.2024. Construction works at site was stopped from 05/02/2023 to 31.10.2023. |

Ro-Ro / Ro-Pax Ferry Service Cell

| Sr. No. | Name of work and location | Estimated cost (Rs.) in Crores | Tendered Cost (Rs.) in Crores | % Above/ Below Schedule of Rates | Agreement No. / Work Order No. | Agency | Date of commence-ment of work | Time of completion | Name & Address of the Engineer in Charge | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 92 | Construction of RORO/ROPAX facility at Muldwarka, Gujarat. (Offshore) | 84.74 | 76.69 | 9.5% (Below) | LOA No.CN/WK/1600-Const/Muldwarka/7 dated 14/01/2022 | M/s. BMS Projects – Marymatha JV | 10/05/2022 | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | Interim W/O for fabrication of Pontoon and Linkspan at Hazira, awarded on 10/05/2022. EC & CRZ received on 30.12.2023 and Final W/O shall be issued shortly. |
| 93 | Dredging in Approach channel Turning Circle, Berth pockets and surroundings of landing pontoon etc at Ghogha Ro-Ro Terminal Gujarat. | 28.63 | 45.81 | 60% (Above) | Work Order No. CN/WK/1600- GHOGHA (7BCD)/51 Dated – 25/04/2022 | M/s. Rock & Reef Dredging Pvt Ltd., Navi Mumbai | 25/04/2022 | 4 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. 1st extension for 4 months from 23.08.2022 to 15.12.2022, 2nd extension from 16.12.2022 to 31.03.2023 and 3rd extension for the period upto 30.06.2023 has been granted by competent authority subject to ratification of Board. Letter to MOSP&W to release balance 10% payment and to incur balance expenditure through internal resources.Show cause notice has been issued on 16.11.2023 as per recommendation of NTCPWC, IIT M. Work completed on 30.11.2023 |
| 94 | Monitoring for smooth functioning of Ro-Ro Facility services located at Hazira, Dahej and Ghogha. | 1.95 | 1.67 | 14.36% (Below) | Work Order No. CN/WK/1600/38 Dated – 29/03/2022 | M/s. Dhanjibhai K Patel | 01/04/2022 | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Proposal for extension of contract for 6 months and variation thereof processed for approval. |
| 95 | Construction of RoRo / Ropax facility at Pipavav – Gujarat. (Offshore) | 110.17 | - | - | - | - | - | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | The tender has been discharged as per approval of competent authority dated 22.11.2022. due to non-receipt of NOC |
| 96 | Construction of Ro – Ro / Ro-Pax On – Shore facility at Muldwarka – Gujarat, EPC mode. | 30.81 | 33.89 | 9.97% (Above) | Work Order No.CN/WK/1600/Onshore Muldwarka/137 dated 15.07.2022 | M/s. MMC Projects (India) Pvt Ltd., Gandhidham | 25/07/2022 | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | LOA issued on 03/06/2022. Work is stopped due to local people interference. EC & CRZ received on 30.12.2023 and order to resume work shall be issued shortly. |
| 97 | Annual Maintenance contract of Linkspan Pontoon and Terminal facilities of Dahej & GhoghaRo-Paxferry terminal | 3.90 | 3.90 | - | Supplementary Work Order No. CN/WK/1600/55 Dated – 09/07/2021 Extension Letter issued vide No.CN/WK/1600/Ro-Pax/55/35 dated 24.02.23 | M/s. Vishwakarma Mechanical works, Porbandar | 08/03/2019 | 07/03/2021 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Proposal for extension of work from 07/09/2021 to 06/07/2023 (22 months) and Anticipation Variation Statement No.2 with extra items for net excess of Rs.3,94,36,435/- i.e. 101.11% excess on the tendered cost of Rs.390.04 Lakhs has been approved by the Board in its meeting held on 03.02.2023 .Further in-principle extension for 3 months from 07.07.2023 to 20.09.2023 with net excess of 117.00% has been approved by competent authority. Final variation statement with Net excess of 116.81% is technically checked and is placed before the variation committee |
| 98 | Construction & Maintenance of Ro-Pax facility at Hazira-Gujarat on EPC mode | 66.35 | 69.06 | 4.09% above | W.O.No. CN/WK/1600/Pre-bid/10 dated 15.04.2021 | M/s. BMS Projects-Marymatha JV | 21/04/2021 | 14 Months | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. 1st Extension upto 20.09.2022 and 2nd extension upto 20.10.2022 has been granted by the competent authority. Anticipated Variation Statement No.1 for net excess of Rs.7.91 Crores is under approval. |
| 99 | Construction of Ro-Ro/Ro-Pax On-shore facility at Pipavav-Gujarat on EPC mode | 36.53 | - | - | - | - | - | 8 Months | Shri Rajendra Prasad Bethi, SE(P) | The tender has been discharged as per approval of competent authority dated 22.11.2022 due to non receipt of NOC. |
| 100 | Annual Maintenance Contract of Navigational Channel Marking System (Buoys) at Ghogha – Ro-Pax | 0.86 | 0.94 | 8.9339% above | WORK ORDER NO. CN/WK/1613/ROPAX/GHOGHA-III/PQ/124 DT. 17.04.2023 | M/s. Somnath Metal Cast, Bhavnagar | 24.04.2023 | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | LOA issued to on 28.03.2023 W.O. issued on 17.04.2023 Work in progress. Anticipated variation statement for Net excess of Rs27,37,595 i.e. 29.16% is approved by Variation committee. |
| 101 | Annual Maintenance Contract of Navigation Channel Marking System (Buoys) at Dahej & Ghogha – Ro Pax Online Tender ID 383191 | 0.48 | 0.48 |  | Supplementary Work Order No. CN/WK/1600/49 Dated – 29/06/2021 Extension Letter issued vide No.CN/WK/1600/Ro-Pax/49/36 dated 24.02.23 | M/s. Sai Sagar Dredging & Marine Services Pvt. Ltd., Bharuch | 03/03/2020 | 02/03/2021 | Shri Rajendra Prasad Bethi, SE(P) | Work in Progress. Proposal for extension of work from 02/09/2021 to 01/07/2023 (22 months) and Anticipation Variation Statement No.2 for net excess of Rs.75,69,087/- i.e. 156.26% excess (For Ghogha Rs. 59,28,200 i.e. 122.39% and Dahej Rs. 16,40887/- i.e. 33.88% on the tendered cost of Rs.48,43,830/-has been approved by the Board in its meeting held on 03.02.2023.Further 2nd extension for period of 6 months from 02.07.2023 to 01.01.2024 with Net excess of 239.06% is in principlally approved and same is placed before variation committee. |
| 102 | Annual Maintenance Contract for Link spans, Pontoons and Terminal facilities at Ghogha | 2.94 | 3.19 | 8.57% | LOA issued vide EG/WK/9134/137 DT. 24.07.2023 | M/s. Vishwakarma Mechanical works, Porbandar | 23.08.2023 | 24 Months | Shri Rajendra Prasad Bethi, SE(P) | LOA issued on 24.07.2023 Work order issued on 16.08.2023 Work is in progress. Variation statement for Net excess of 11.88% is under process. |
| 103 | Annual Maintenance Contract for Link Spans, Pontoons and Terminal facilities at Dahej | 2.95 | 3.30 | 11.67% ABOVE | LOA issued on 31.08.2023- | Vishwakarma Mechanical Work, Porbander | 21.09.2023 | 24 months | Shri Rajendra Prasad Bethi, SE(P) | .LOA issued on 31.08.2023. Work order issued on 13.09.2023 Work is in progress. |
| 104 | Annual Maintenance Contract of Navigational Channel Marking System (Buoys) at Dahej-Ro-Pax | 3.69 | - | - | - | - | - | 24 months | Shri Rajendra Prasad Bethi, SE(P) | Proposal for discharge of tender due to disqualification of both bidders & re-invitation of tender with modified estimate & DTPS has been approved. Estimate & DTPs is under process |
| 105 | Maintenance Dredging at Periphery of Landing Pontoon of Ro-Pax facility at Dahej Terminal for 12 months | 2.22 | 1.99 | 9.999% below | Work Order No. CN/WK/1600/Dahej-2022-23/Pont. Maint. Dredg./18 dt. 04.05.2023 | M/s. BSP Hydro Dredging Works Pvt. Ltd., Bhimavaram, Andhra Pradesh | 19.06.2023 | 12 Months | Shri Rajendra Prasad Bethi, SE(P) | W.O. issued on 04.05.2023. Site handed over on 23.06.2023 and work is in progress. |
| 106 | Engagement of Security agency for providing watch & ward security supervisor & security guard without arms for Dahej terminal of DPA for 2 years | 0.81 | 0.70 | 13.41% below | Work Order No. CN/WK/1600/Security/132 dt. 04.05.2023 | Shakti Protection Force Pvt. Ltd. | 08.05.2023 | 24 months | Shri Rajendra Prasad Bethi, SE(P) | W.O. issued on 04.05.2023. Anticipated variation statement for Net excess of Rs. 10,69,566.80 i.e. 15.18% has been in-principle approved and submitted to Variation committee. |

LAND CONTRACTS (C.E. DEPARTMENT)

| Sr. No. | Name of work & location | Reserve price Per sq. mtr./year | Premium received over nd above reserve price during e-auction (per sq. mtr./per year | Allotment letter No. & Date | Name of Agency | Time of completion | Name & address of the Engineer-in-charge. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 107 | E-tender for Empanelment of Valuer for carrying out the valuation of assets lying in the plots allotted to respective parties. | …… | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 18.05.2023, date od downloading tender 30.05.2023, last date of online submission 30.06.2023, pre-bid meeting held on 09.06.203, online opening of Technical bid opened on 10.07.2023. Work order issued on 21.02.2024 |
| 108 | E-tender cum e-auction for the allotment of 03 nos. of plots for the purpose of edible oil storage tanks (products permitted in the earlier lease deed/allotment letter) on 30 years lease on as is where is basis. | 1081.77 | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 13.07.2023, date of downloading tender 13.07.2023, last date of online submission 28.08.2023, pre-bid meeting held on 24.07.2023, Technical bid opened on 05.10.2023. price bid opened at 29.12.2023. E-auction was carried out on 14.03.2024 to 15.03.2024 |
| 109 | Ee-tender cum e-auction for the allotment of 05 nos. of plots (with structure) situated at old Kandla for the purpose of liquid storage tanks (products permitted in the earlier lease deed/allotment letter) on 30 years lease on as is where is basis. | 1081.77 | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 13.07.2023, date of downloading tender 13.07.2023, pre-bid meeting held on 24.07.2023, Date of opening of tender extended up to 15.04.2024 |
| 110 | e-tender cum e-auction for allotment of plots for the purpose of development of green hydrogen & its derivatives and allied infrastructure (excluding renewable energy and exclusive storage) situated between Kharirohar and Padana on 30 years lease on as is where is basis. | RS. 28166.15 PER ANNUM/PER ACRE | …… | ….. | …… | ….. | Shri Chetan Jenia XEN(KL) | NIT published on 19.10.2023, date of downloading tender 19.10.2023, pre-bid meeting held on 02.11.2023, Preliminary date & Technical bid opened on 28.12.2023. E-auction carried out on 20.03.2024 to 04.04.2024 |
| 111 | E-Tender cum E-Auction for the allotment of plot Admg. 4000 Sq/Mtrs situated Kandla for the purpose of Barge Repairing/Beaching on 10 years lease basis on as where is basis. | 282.66 |  |  |  |  | Shri Chetan Jenia XEN(KL) | NIT published on 20.11.2023, date of downloading tender 20.11.2023, pre-bid meeting held on 04.12.2023, Date of opening of tender extended upto 08.04.2024 |
| 112 | E-tender cum e-auction for the allotment of 02 nos. of plots situated at old Kandla for the purpose of liquid storage tanks on 30 years lease on as is where is basis. | 1081.77 | 1113.44 | (1) LW/PL/3588-I/781 DATED 07.03.2024 (2)LW/PL/3588-I/782 DATED 07.03.2024 | (1)RISHI KIRAN TERMINALS PVT LTD (2) RISHI KIRAN LOGISTICS PVT LTD. |  | Shri Chetan Jenia XEN(KL) | NIT published on 14.07.2023, date of downloading tender 14.07.2023, pre-bid meeting held on 09.08.2023, technical bid opened on 05.10.2023. e-auction will be carried out on 12.01.2024 |
| 113 | E-allotment of plots for various purpose on 30 years lease on as is where is basis as per the provisions of the policy guidelines on land management, 2015. | 245.96 |  |  |  |  | Shri Chetan Jenia XEN(KL) | NIT published on 22.01.2024, date of downloading tender 22.01.2024, pre-bid meeting will be held on 05.02.2024, technical bid opened on 03.04.2024. |
| 114 | E-tender cum e-auction for the allotment of 03 nos. of plots (with structure) situated at old Kandla for the purpose of liquid storage tanks (products permitted in the earlier lease deed/allotment letter) on 30 years lease on as is where is basis. | 1103.41 |  |  |  |  | Shri Chetan Jenia XEN(KL) | NIT published on 15.03.2024, date of downloading tender 11.03.2024, pre-bid meeting will be held on 22.03.2024, last date of online submission 09.04.2024, technical bid will be opened on 09.04.2024. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

4.	MARINE DEPARTMENT							                                                                                      AS ON 31.03.2024

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh . | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commence-ment of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Design, Construction and supply of 01 No. Speed Boat (Patrolling Boat) for waterfront security of Deendayal Port. | 948.11 Cr. | 960.61 Cr. | 7.226% above | Yet not executed | M/s. A.H. Wadia Boar Builders, Billmora | 05/01/2024 | 04/01/2029 5 years | Capt. Pradeep Mohanty, Deputy Conservator | LOA issued on 23/11/2023. Work Order issued on 05/01/2024. |
| 2. | Hiring or 2 Nos. of Tugs on Charter / Rate per year for the period of 10 years, extendable for one year. | 214.87Cr. | 209.87 Cr. | 0.86% below | Executed on 15/03/2023 | M/s. Ocean Sparkle Ltd. Hyderabad | Tug 1: 9/5/23 Tug 2: 16/5/23 | 10 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 19/04/2023 |
| 3. | Supply, installation & Commissioning and AMC of Radiological Detection Equipment. | 30.11 Cr. | 30.11 Cr. | - | Executed on 09/03/2022 | M/s. Electronics Corporation of India Ltd., Hyderabad | 25/11/2021 | 24 months for supply, installation and commissioning AMC 10 years after installation. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 10/06/2018. Work Order issued on 31/01/2019. Supply & Installation work completed on 25/11/2020. AMC work in progress. |
| 4 | Hiring or 2 Nos. of Steel Hull Mooring Launches and Moorings Gangs at Deendayal Port, Kandla for a period of 5 years. | 14.60 Cr. | 10.76 Cr. | 26.24% below | Executed on 16/06/2021 27/11/2022 | M/s. Pacific Shipping Services, Mumbai | 04/01/2024 | 03/01/2024 5 years. | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 21/05/2021 Work Order issued on 02/11/2022. The commence-ment of work delayed due to non-submission of IRS certificate, etc. LD levied as per tender condition. |
| 5 | Hiring of 04 Nos. of 50/60 Ton Bollard Pull Tug on Charter/Rate per day for the period of ten years extendable further by one year. | 7.70 Cr. for each Tug | 3.08 Cr. | 19.89% below. 20.08% below | Executed on 14/10/2016 Executed on 10/07/2016 | Ocean Sparkle Ltd, Hyderabad KNK Ship Management, Mumbai | 1) 03/12/2016 2) 15/12/2016 3) 20/12/2016 4) 06/12/2016 | 1) 03/12/2026 2) 15/12/2026 3) 20/12/2026 4) 06/12/2026 | Capt. Pradeep Mohanty,, Deputy Conservator | W.O. has been issued on 03/10/2016 & 22/09/2016. |
| 6 | Hiring of 165 Nos. of Manpower in the cadre at Firefighters for Port services at DPA, Kandla on Contractual basis for a period of 3 years. | 6.58 Cr. | 6.38 Cr. | 12.93% below | Executed on 27/04/2023 | M/s. Krishna Industrial Security & Fire Services Pacific Shipping Services , Anand | 14/04/2023 | 13/04/2026 3 years | Capt. Pradeep Mohanty,, Deputy Conservator | LOA issued on 13/02/2023. |
| 7 | Appointment of Agency for providing manning services /VTS operations at Kandla & Vadinar Port monitoring stations - VTS for the period of 3 years. | 5.41 Cr. | 5.93 Cr. | 9.69% above | Executed on 19/04/2023. | M/s. Admiral Marine Services P, Ltd., Chennai | 01/04/2023 | 31/03/2026 3 years | Capt. Pradeep Mohanty,, Deputy Conservator | LOA issued on 20/02/2023 Work Order issued on 20/03/2023. |
| 8 | Hiring of Hydrographic Survey Equipment on Board M.L. Nirikshak for 05 years at Kandla. | 2.62 Cr. | 2.33 Cr. | 10.82% below estimated cost | Executed on 22/10/2020 | M/s. Horizon Survey Company India Ltd., Mumbai | 26/04/2021 | 25/04/2026 5 years | Capt. Pradeep Mohanty, Deputy Conservator. | LOA issued on 13/10/2020. Work Order issued on 05/01/2021. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

5.	GENERAL ADMINISTRATION DEPARTMENT			                                				                              AS ON 31.03.2024

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / Lakh | Tendered Cost (Rs.) in Crore / Lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Hiring of brand new make of 64 Nos. of vehicles Model-2023) EV/Diesel / Petrol, on monthly hired basis and hiring of vehicles not earlier than 2022 on äs and when required basis "for a period of 3 years. | 19.33 Cr. | 16.02 Cr. | 17.16% below | Executed. Work Order No. GA/GN/5400/2023-25/815 dated 10/03/2023 | M/s. Rishabh Enterprises, Gandhidham. | 01/04/2023 | 31/03/2026 | Shri Deepak Rane, Dy. Secretary | Work in progress. |
| 2. | Hiring of 11 Nos. 51+1 (seater) capacity of brand new 2019 model readymade diesel buses for transportation of DPT employees / CISF personnel and their children for a period of 04 years | 9.85 Cr. | 8.52 Cr. | 13.5% below | Executed. Work Order No. LB/WK/1083(Bus-2019)/65 dated 18/01/2020 | M/s. Rishabh Enterprises, Gandhidham. | 01/01/2020 | 31/12/2023 Extension granted upto 30/06/2024 | Shri Ravi K. Maheshwari, Personnel Officer (I/c) | Work in progress. |
| 3. | Engagement of Security Agency for providing Watch & Ward Security Supervisors & Security Guards without arms for various Departments of DPA for the period of 02 years. | 5.92 Cr. | 5.13 Cr. | 13.34% blow | Executed Work Order No. ES/SR/2443/ Security/1 dated 26.03.2021 ES/SR/2443/ Security/2 dated 26.03.2021 ES/SR/2443/ Security/3 dated 26.03.2021 | M/s. Shakti Secuirty, Surat. M/s. Panther Surveillance, Ahmedabad. M/s. Rajput Security Services, Ahmedabad. | 26/03/2021 | 25/03/2023 Further Extended upto 31/03/2024 | Shri Omprakash Dadlani, TP & PRO & Nodal Officer, (Security) | Work in progress. The proposal for extension of contract form 01/04/2024 to 30/09/2024 submitted to competent authority for approval. |

TENDERS / CONTRACTS UNDER INTEGRITY PACT

6.	MEDICAL DEPARTMENT										                                            AS ON 31.03.2024

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supply of Allopathic, Homeopathic Ayurvedic medicines & surgical disposals through Outlets at Port Hospitals, New Kandla, Gopalpuri, Adipur and Vadinar | Estimated volume of yearly business 8.00 Cr. | Party offered 22% discount on the monthly bill amount. | 22% discount on the monthly bill amount. | MH/SP/51/ 2020-21 dated 22/01/2021 | M/s. Mars Remedies, Jamnagar | 22/01/2021 | 3 years. Extension granted upto 24/04/2024 | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |
| 2 | Outsourcing of Vadinar Hospital for treatment of employees of DPA, CISF Personnel and CISF employees engaged by DPA and IOCL and their family members as well as other persons as decided by DPA at Vadinar | 2.88 Cr. | 2.07 Cr. | 26.80% below | MH/SP/85/ 2020-21 | M/s. Shree Samarpan Wellness Pvt. Ltd., Rajkot | 16/05/2022 | 3 years. | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat. | Nil |
| 3. | Hiring of two Ambulances on monthly basis for DPA | 1.39 Cr. | 1.15 Cr. |  | GEMC-511687774163859 dated 18/01/2024 | M/s. Rishabh Enterprises, Gandhidham | 05/02/2024 | 04/02/2029 5 years | Dr. Anil Chellani, Chief Medical Officer, Port Hospital, Gopalpuri 370240, Kutch District, Gujarat | Contract awarded through Gem Portal |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

7.	TRAFFIC DEPARTMENT											                	AS ON 31.03.2024

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer-in-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Engagement of manpower service provider for providing various categories of outsourced staff to carry out railway operation inside Cargo Jetty area for a period of 3 years. | 3.88 Cr. | 2.87 Cr. | 26.00% below | Executed on dated 26/07/2021 | M/s. Dhanjibhai K. Patel, Anjar. | 01/05/2021 | 30/04/2024 | Shri N.M. Parmar, ATM (Railway), | Work in progress. |
| 2. | Outsourcing of Establishing and operating of occupational health services at Deendayal Port Authority, New Kandla for the period for 5 years. | 3.54 Cr. | 2.98 Cr. | 16.59% below | Executed on dated 15/12/2021 | M/s. Accord Multispecialty Hospital, Bhuj | 15/12/2021 | 14/12/2026 | Shri Bavesh Mandvi, Safety Officer | Work in progress. |
| 3. | Engagement of Consultant to authenticate / validate the reports submitted by the PPP Operator for three (3) years | 2.56 Cr. | 2.77 Cr. | 9.99% Above | Executed on dated 10/10/2022 | M/s. Aarvee Associates Architects Engineering & Consultant Pvt. Ltd., Hyderabad | 17/10/2022 | 16/10/2025 | Shri Thushar Patel, Asstt. Traffic Manager (PPP) | Work in progress. |

*****

TENDERS / CONTRACTS UNDER INTEGRITY PACT

8.	FINANCE DEPARTMENT										                                     AS ON 31.03.2024

| Sr. No. | Name of work & location | Estimated Cost (Rs.) in Crore / lakh | Tendered Cost (Rs.) in Crore / lakh | % Above / Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of Completion | Name & Address of the Engineer In-charge / Engineer | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| .............. N I L ................... |  |  |  |  |  |  |  |  |  |  |

*****