## Sheet1
Category wise Seniority List For Pending Application for Dry Docking As on 30/05/2024
Sr. | Description | Date of Application receipt | Last updation Date | Name of the Party | Name of the Vessel. | LOA (mtrs) | Page No. | File No 1131-XXVII | Tentative no. of days req. | Remarks
No.
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | a) Port Vessels
2 | b) Repair & maintenance to SFDD : |  |  | DPA | Pantoon No. 6(Self) | 27 |  |  | 90
3 | c) Vessels belongs to Navy/Coast guard/Govt. Deptt.:
4 | The Agencies / contracts or having | 05.02.2024 |  | Genesis Shipping Services | Ocean Lancer | 36 | 752A |  | 22 | Ready for Docking
5 | General Category
| 1 | 02.08.2023 |  | Arcoffshore india | Ocean Delight | 31.34 | 675 |  | 15 | No Response
| 2 | 14.09.2023 |  | Genesis Shipping Services | M.T. AEL II | 80.2 | 691 |  | 15 | Cannot be dry docked due to technical reason
| 4 | 16.11.2023 |  | Genesis Shipping Services | Tug Adel 2 | 32 | 720 |  | 20 | Cannot be dry docked due to technical reason
| 5 | 06.12.2023 |  | Noorani Shipping Services | Tug Ashwini | 32.08 | 723 |  | 20 | Slot req. 2nd week of June'24
| 6 | 12.12.2023 |  | Polestar Maritime Ltd., | Tug Jasmine Star | 30 | 728 |  | 13 | Slot req. 4th week of June'24
| 7 | 12.12.2023 |  | Polestar Maritime Ltd., | Tug Sunflower Star | 32 | 726 |  | 12 | Slot req. 4th week of July'24
| 8 | 12.12.2023 |  | Genesis Shipping Services | Ocean Coral | 60 | 728 |  | 15 | Slot req.last week of June'24
| 9 | 20.12.2023 |  | Jevan Dredgin Ltd., | MV Vivekprem | 32 | 724 |  | 25 | Ready for Docking
| 10 | 05.02.2024 |  | Genesis Shipping Services | Ocean Zest | 32 | 756 |  | 15 | Slot Req.2nd week of July'24
| 11 | 05.02.2024 |  | Genesis Shipping Services | Ocean Pride | 30 | 752 |  | 15 | Slot Req.2nd week of July'24
| 12 | 10.02.2024 |  | Adani Harbour Services Ltd., | Dolphin No. 04 | 34 | 763 |  | 16 | Last Week of Aug'24
| 13 | 28.02.2024 |  | Patel Engineering Works | Reltug 19 | 31.26 | 775 |  | 22 | 1st week of July 24
| 14 | 28.02.2024 |  | Patel Engineering Works | Reltug 18 | 31.26 | 769 |  | 22 | 1st week of July 24
| 15 | 19.03.2024 |  | Patel Engineering Works | Ambuja Mukund | 97 | 786 |  | 35 | 1st wek of July 24
| 16 | 19.03.2024 |  | Patel Engineering Works | Ambuja Shakti | 80 | 783 |  | 55 | 1st week of June'24
| 17 | 29.03.2024 |  | Polestar Maritime Ltd., | Tug Iris | 25.25 | 791 |  | 12 | 1st week of Oct'24
| 18 | 18.04.2024 |  | Amrut Dredging & Shipping | Kamal xxi | 77.9 | 796 |  | 30 | Last Week of Aug'24
| 19 | 15.05.2024 |  | Genesis Shipping Services | Adel 1 | 32 | 800 |  | 20 | Slot Req. 3rd Week of Oct'24
| 20 | 17.05.2024 |  | Malara Shipping Pvt. Ltd., | MV Persistance | 36 | 808 |  | 20 | Slot Req. 2nd weekofJune24
| 21 | 29.05.2024 |  | Patel Engineering Works | Reltug 03 | 35.3 | 812 |  | 32 | Slot Req. 1st week of Oct'24
| A E ( F /C ) | [6 empty] | SE ( M )
| Deendayal Port Authority | [5 empty] | Deendayal Port Authority